## SUMMARY
SUSPENSION DRAWING SUMMARY
E1000036-v8, 14 May 2010
E1000036-v9, 27 May 2010
E1000036-v10, 11 June 2010
E1000036-v11, 14 June 2010
E1000036-v12, 15 June 2010
E1000036-v13, 08 July 2010
E1000036-v14, 08 July 2010
E1000036-v15, 04 August 2010
E1000036-v16, 04 August 2010
E1000036-v17, 25 August 2010 |  | (R.JONES, updates to "Glass & Welding Tooling" & "CO2 Machine & Characterizing")
E1000036-v17, 06 September 2010
E1000036-v18, 06 September 2010
E1000036-v19, 08 September 2010
E1000036-v20, 09 September 2010 |  | (R.JONES, updates to "Glass & Welding Tooling" & "CO2 Machine & Characterizing")
E1000036-v21, 01 October 2010 |  | (R.JONES, updates to "Glass & Welding Tooling" & "CO2 Machine & Characterizing")
E1000036-v22, 06 October 2010
E1000036-v23, 08 October 2010
E1000036-v24, 08 November 2010
E1000036-v25, 07 December 2010
E1000036-v26, 07 December 2010
E1000036-v27, 07 January 2011
E1000036-v28, 06 February 2011
E1000036-v29, 06 February 2011
E1000036-v30, 15 February 2011 |  | (R.JONES, updates to "Glass & Welding Tooling" & "CO2 Machine & Characterizing" - all on DCC)
E1000036-v31, 8 March 2011
E1000036-v32, 8 March 2011
E1000036-v33, 6 April 2011
E1000036-v34, 23 April 2011
SUSPENSION | DRAWING TOTAL
HLTS Mechanical | 248
HSTS Mechanical | 222
OMC Mechanical | 119
Quad Mechanical | 327
BS Mechanical | 117
Monolithic | 234
Electronics | 103
Suspensions Total | 1370

## HLTS Mechanical
HLTS Mechanical Drawing Completion Status
Subsystem: | SUS
Reporter: | Derek Bridges
Date: | 2011-07-08
Drawing Completion Legend:
< 80% | Drawing in progress.
80% | Minor changes needed to drawing.
90% | Drawing complete, but needs to be reviewed.
95% | Drawing uploaded to DCC; awaiting signatures.
100% | Drawing approved.
Line # | Assembly # | Sub-Assy # | Part # | Title | BOM | No. of Dwgs | Model Status | Drawing Status | CDR | PDR | Delta- PDR | FDR | Production Revision | Unique Drawing #
1 | D080718-v1 |  |  | HLTS Overall Assembly and Assembly Fixtures | E080329-v1 | 248 | 100% | 100% |  |  |  | x |  | 1
2 | D070447-v2 |  |  | HLTS Overall Assembly |  | 134 | 100% | 95% |  |  |  |  | x | 2 | 1
3 |  | D070537-v2 |  | Structure, HLTS |  | 9 | 100% | 100% |  |  |  |  | x | 3 | 2 | 1
4 |  | D070442-v6 |  | Structural Weldment, HLTS |  | 7 | 100% | 100% |  |  |  |  | x | 4 | 3 | 2 | 1
5 |  |  | D070575-v3 | Base Plate, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 5 | 4 | 3 | 2
6 |  |  | D070580-v2 | Top Gusset, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 6 | 5 | 4 | 3
7 |  |  | D070579-v2 | Upper Front Gusset, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 7 | 6 | 5 | 4
8 |  |  | D070576-v2 | Lower Front Gusset, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 8 | 7 | 6 | 5
9 |  |  | D070578-v2 | Side Strut, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 9 | 8 | 7 | 6
10 |  |  | D070577-v2 | Side Gusset, Structural Weldment, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 10 | 9 | 8 | 7
11 |  | D0900626-v2 |  | Mounting Pad Assembly |  | 4 | 100% | 100% |  |  |  |  | x | 11 | 10 |  | 1
12 |  |  | D070374-v2 | Mounting Pad Body |  | 1 | 100% | 100% |  |  |  |  | x | 12 | 11 | 9 | 2
13 |  |  | D0900627-v2 | Front Bracket, Mounting Pad |  | 1 | 100% | 100% |  |  |  |  | x | 13 | 12 |  | 3
14 |  |  | D0900628-v2 | Side Bracket, Mounting Pad |  | 1 | 100% | 100% |  |  |  |  | x | 14 | 13 |  | 4
15 |  | D070332-v5 |  | HLTS Suspension Assembly |  | 77 | 100% | 95% |  |  |  |  | x | 15 | 14 | 1
16 |  | D070326-v3 |  | Rotational Adjuster |  | 14 | 100% | 95% |  |  |  |  | x | 16 | 15 | 2 | 1
17 |  |  | D070327-v2 | Base Plate, Rotational Adjuster |  | 1 | 100% | 100% |  |  |  |  | x | 17 | 16 | 3 | 2
18 |  |  | D070328-v2 | Rotating Plate, Rotational Adjuster |  | 1 | 100% | 100% |  |  |  |  | x | 18 | 17 | 4 | 3
19 |  |  | D1001914-v2 | Shim, 2mm, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 19 | 18 | 5 | 4
20 |  |  | D1003104-v1 | Shim, 1.5mm, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 20 | 19 | 6 | 5
21 |  |  | D070331-v3 | Shim, 1mm, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 21 | 20 | 7 | 6
22 |  |  | D1002973-v2 | Shim, 0.5mm, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 22 | 21 | 8 | 7
23 |  |  | D1003105-v1 | Shim, 0mm, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 23 | 22 | 9 | 8
24 |  |  | D020622-v3 | Blade Clamp (0.0 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 24 | 23 | 10 | 9
25 |  |  | D020617-v2 | Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 25 | 24 | 11 | 10
26 |  |  | D020601-v2 | Blade Clamp (0.0 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 26 | 25 | 12 | 11
27 |  |  | D070330-v2 | Push Plate |  | 1 | 100% | 100% |  |  |  |  | x | 27 | 26 | 13 | 12
28 |  |  | D0900990-v2 | SHCS, #8-32 X 1.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x | 28 | 27 | 14 | 13
29 |  |  | D070329-v2 | Pull Plate |  | 1 | 100% | 100% |  |  |  |  | x | 29 | 28 | 15 | 14
30 |  | D070340-v2 |  | Upper Wire Assembly |  | 6 | 100% | 95% |  |  |  |  | x | 30 | 29 | 16 | 1
31 |  |  | D020611-v4 | Upper Clamp, Upper Wire, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 31 | 30 | 17 | 2
32 |  |  | D070341-v3 | Upper Clamp, Upper Wire, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 32 | 31 | 18 | 3
33 |  |  | D020652-v2 | C-Clamp, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x | 33 | 32 | 19 | 4
34 |  |  | D020610-v3 | Lower Clamp, Upper Wire, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 34 | 33 | 20 | 5
35 |  |  | D020624-v3 | Lower Clamp, Upper Wire, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 35 | 34 | 21 | 6
36 |  | D070335-v4 |  | Upper Mass Assembly |  | 23 | 100% | 100% |  |  |  |  | x | 36 | 35 | 22 | 1
37 |  |  | D020605-v3 | Main Section, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x | 37 | 36 | 23 | 2
38 |  |  | D080221-v2 | Guard, Lower Blade |  | 1 | 100% | 100% |  |  |  |  | x | 38 | 37 | 24 | 3
39 |  |  | D030025-v1 | SHCS, #8-32 X 1 Long, Fully Threaded, Rounded End, Ag-Plated |  | 1 | 100% | 100% |  |  |  |  | x | 39 | 38 | 25 | 4
40 |  |  | D020602-v2 | Blade Clamp (0.0 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 40 | 39 | 26 | 5
41 |  |  | D020615-v2 | Lower Blade |  | 1 | 100% | 100% |  |  |  |  | x | 41 | 40 | 27 | 6
42 |  |  | D020623-v2 | Blade Clamp (0.0 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 42 | 41 | 28 | 7
43 |  |  | D020607-v3 | T-Piece, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x | 43 | 42 | 29 | 8
44 |  |  | D1001669-v1 | Pitch Offset, T-Piece, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x | 44 | 43 | 30 | 9
45 |  |  | D030139-v2 | Roll Offset, T-Piece, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x | 45 | 44 | 31 | 10
46 |  |  | D020653-v2 | Screwdrive System |  | 1 | 100% | 100% |  |  |  |  | x | 46 | 45 | 32 | 11
47 |  |  | D0900990-v2 | SHCS, #8-32 X 1.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 12
48 |  |  | D1001699-v1 | Magnet Holder, BOSEM, HLTS |  | 1 | 100% | 100% |  |  |  |  | x | 47 | 46 | 33 | 13
49 |  | D1001695-v2 |  | Magnet and Flag Assembly, BOSEM |  | 5 | 100% | 100% |  |  |  |  | x | 48 | 47 | 34 | 14 | 1
50 |  |  | D1001697-v1 | Magnet Retainer, BOSEM |  | 1 | 100% | 100% |  |  |  |  | x | 49 | 48 | 35 | 15 | 2
51 |  |  | D1001534-v1 | Magnetic Plug |  | 1 | 100% | 100% |  |  |  |  | x | 50 | 49 | 36 | 16 | 3
52 |  |  | D1100574-v3 | BOSEM Flat Flag Disk |  | 1 | 100% | 100% |  |  |  |  | x | 51 | 50 | 37 | 17 | 4
53 |  |  | D1100573-v4 | BOSEM Flag |  | 1 | 100% | 100% |  |  |  |  | x | 52 | 51 | 38 | 18 | 5
54 |  |  | D1001230-v1 | Additional Mass Disk, 10g |  | 1 | 100% | 100% |  |  |  |  | x | 53 | 52 | 39 | 19
55 |  |  | D1001229-v1 | Additional Mass Disk, 20g |  | 1 | 100% | 100% |  |  |  |  | x | 54 | 53 | 40 | 20
56 |  |  | D0901405-v2 | Additional Mass Disk, 50g |  | 1 | 100% | 100% |  |  |  |  | x | 55 | 54 | 41 | 21
57 |  |  | D070333-v2 | Additional Mass Disk, 100g |  | 1 | 100% | 100% |  |  |  |  | x | 56 | 55 | 42 | 22
58 |  |  | D080263-v2 | Additional Mass Disk, 150g |  | 1 | 100% | 100% |  |  |  |  | x | 57 | 56 | 43 | 23
59 |  | D070393-v2 |  | Intermediate Wire Assembly |  | 6 | 100% | 95% |  |  |  |  | x | 58 | 57 | 44 | 1
60 |  |  | D070585-v4 | Upper Clamp, Intermediate Wire, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 59 | 58 | 45 | 2
61 |  |  | D070394-v3 | Upper Clamp, Intermediate Wire, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 60 | 59 | 46 | 3
62 |  |  | D030149-v2 | Intermediate Wire Breakoff, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 61 | 60 | 47 | 4
63 |  |  | D070405-v3 | Lower Clamp, Intermediate Wire, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 62 | 61 | 48 | 5
64 |  |  | D070406-v3 | Lower Clamp, Intermediate Wire, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 63 | 62 | 49 | 6
65 |  | D070334-v3 |  | Intermediate Mass Assembly |  | 22 | 100% | 100% |  |  |  |  | x | 64 | 63 | 50 | 1
66 |  |  | D070336-v3 | Main Section, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 65 | 64 | 51 | 2
67 |  | D080181-v2 |  | Intermediate Mass Changer Assembly |  | 12 | 100% | 95% |  |  |  |  | x | 66 | 65 | 52 | 3 | 1
68 |  |  | D030155-v2 | Center Offset, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 67 | 66 | 53 | 4 | 2
69 |  |  | D080182-v2 | Collar, Upper, 100g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 68 | 67 | 54 | 5 | 3
70 |  |  | D080183-v2 | Collar, Lower, 100g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 69 | 68 | 55 | 6 | 4
71 |  |  | D080223-v2 | Collar, Upper, 300g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 70 | 69 | 56 | 7 | 5
72 |  |  | D080232-v2 | Collar, Lower, 300g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 71 | 70 | 57 | 8 | 6
73 |  |  | D080225-v2 | Collar, Upper, 500g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 72 | 71 | 58 | 9 | 7
74 |  |  | D080234-v2 | Collar, Lower, 500g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 73 | 72 | 59 | 10 | 8
75 |  |  | D080227-v2 | Collar, Upper, 700g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 74 | 73 | 60 | 11 | 9
76 |  |  | D080236-v2 | Collar, Lower, 700g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 75 | 74 | 61 | 12 | 10
77 |  |  | D080229-v2 | Collar, Upper, 900g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 76 | 75 | 62 | 13 | 11
78 |  |  | D080238-v2 | Collar, Lower, 900g, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 77 | 76 | 63 | 14 | 12
79 |  |  | D030156-v2 | Side Offset, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 78 | 77 | 64 | 15
80 |  |  | D1001230-v1 | Additional Mass Disk, 10g |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 16
81 |  |  | D1001229-v1 | Additional Mass Disk, 20g |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 17
82 |  |  | D0901405-v2 | Additional Mass Disk, 50g |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 18
83 |  |  | D070333-v2 | Additional Mass Disk, 100g |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 19
84 |  |  | D080263-v2 | Additional Mass Disk, 150g |  | 1 | 100% | 100% |  |  |  |  | x |  |  |  | 20
85 |  |  | D970075-v2 | Dumbbell Standoff |  | 1 | 100% | 100% |  |  |  |  | x | 79 | 78 | 65 | 21
86 |  |  | D0901927-v1 | Sintered SmCo Magnet, 0.075 X 0.125 |  | 1 | 100% | 100% |  |  |  |  | x | 80 | 79 | 66 | 22
87 |  | D070436-v3 |  | Lower Loop Wire Assembly |  | 3 | 100% | 95% |  |  |  |  | x | 81 | 80 | 67 | 1
88 |  |  | D030148-v2 | Lower Wire Breakoff, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 82 | 81 | 68 | 2
89 |  |  | D070438-v4 | Clamp, Lower Loop Wire |  | 1 | 100% | 100% |  |  |  |  | x | 83 | 82 | 69 | 3
90 |  | D070337-v6 |  | Bottom Mass Assembly |  | 8 | 100% | 95% |  |  |  |  | x | 84 | 83 | 70 | 1
91 |  |  | D070338-v4 | Metal Bottom Mass |  | 1 | 100% | 100% |  |  |  |  | x | 85 | 84 | 71 | 2
92 |  | D0902432-v1 |  | Magnet/Standoff Assembly |  | 3 | 100% | 100% |  |  |  |  | x | 86 | 85 | 72 | 3 | 1
93 |  |  | D0902431-v1 | Magnet Standoff |  | 1 | 100% | 100% |  |  |  |  | x | 87 | 86 | 73 | 4 | 2
94 |  |  | D0900040-v1 | Sintered SmCo Magnet, 2mm X 0.5mm |  | 1 | 100% | 100% |  |  |  |  | x | 88 | 87 | 74 | 5 | 3
95 |  |  | D080124-v3 | Prism Breakoff, Lower Wire |  | 1 | 100% | 100% |  |  |  |  | x | 89 | 88 | 75 | 6
96 |  |  | D1100197-v1 | Spacer, Bottom Mass Optics, HLTS/HSTS |  | 1 | 100% | 100% |  |  |  |  | x | 90 | 89 | 76 | 7
97 |  |  | D0901286-v2 | Secondary Metal Prism Breakoff |  | 1 | 100% | 100% |  |  |  |  | x | 91 | 90 | 77 | 8
98 |  | D070308-v2 |  | Top Blade Guard Assembly |  | 4 | 100% | 100% |  |  |  |  | x | 92 | 91 | 1
99 |  |  | D070309-v2 | Top Blade Guard Riser |  | 1 | 100% | 100% |  |  |  |  | x | 93 | 92 | 2
100 |  |  | D070310-v2 | Top Blade Guard Bar |  | 1 | 100% | 100% |  |  |  |  | x | 94 | 93 | 3
101 |  |  | D0900999-v3 | SHCS, 1/4-20 X 2 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x | 95 | 94 | 4
102 |  | D1001754-v1 |  | Coil Holder/Upper Mass Assembly |  | 30 | 100% | 100% |  |  |  |  | x | 96 | 95
103 |  | D080677-v2 |  | Coil Holder Assembly |  | 7 | 100% | 100% |  |  |  |  | x | 97 | 96 | 1
104 |  |  | D070449-v2 | Coil Holder (Tablecloth) |  | 1 | 100% | 100% |  |  |  |  | x | 98 | 97 | 2
105 |  |  | D030023-v3 | SHCS, 1/4-20 X 1 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x | 99 | 98 | 3
106 |  | D1002133-v1 |  | Mounting Bracket, Coil Holder |  | 3 | 100% | 100% |  |  |  |  | x | 100 | 99 | 4 | 1 |  | 1
107 |  |  | D1002134-v1 | Mounting Bracket Lateral Section |  | 1 | 100% | 100% |  |  |  |  | x | 101 | 100 | 5 | 2 |  | 2
108 |  |  | D1002135-v1 | Mounting Bracket Longitudinal Section |  | 1 | 100% | 100% |  |  |  |  | x | 102 | 101 | 6 | 3 |  | 3
109 |  |  | D060218-C | BOSEM Assembly |  | 1 | 100% | 100% |  |  |  |  | x | 103 | 102 | 7
110 |  |  | D0900004-v1 | UHV-Compatible Cable Clamp |  | 1 | 100% | 100% |  |  |  | x |  | 104 | 103
111 |  | D080726-v2 |  | Earthquake Stop Assembly, Long Mount |  | 7 | 100% | 95% |  |  |  |  | x | 105 | 104 | 1
112 |  |  | D070460-v2 | Earthquake Stop Mount, Long |  | 1 | 100% | 100% |  |  |  |  | x | 106 | 105 | 2
113 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x | 107 | 106 | 3 | 1
114 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x | 108 | 107 | 4 | 2
115 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x | 109 | 108 | 5 | 3
116 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x | 110 | 109 | 6 | 4
117 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x | 111 | 110 | 7 | 5
118 |  | D080727-v2 |  | Earthquake Stop Assembly, Long Bracket |  | 7 | 100% | 95% |  |  |  |  | x | 112 | 111 | 1
119 |  |  | D070322-v2 | Earthquake Stop Bracket, Long |  | 1 | 100% | 100% |  |  |  |  | x | 113 | 112 | 2
120 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x |  |  | 3 | 1
121 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 4 | 2
122 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 5 | 3
123 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6 | 4
124 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7 | 5
125 |  | D1002821-v1 |  | Earthquake Stop Assembly, Bottom Mass, Lower |  | 9 | 100% | 100% |  |  |  |  | x | 114 | 113 | 1
126 |  | D1002822-v1 |  | Earthquake Stop Bracket Assembly, Bottom Mass, Lower |  | 3 | 100% | 100% |  |  |  |  | x | 115 | 114 | 2 | 1
127 |  |  | D1002823-v1 | Earthquake Stop Bracket Back, Bottom Mass, Lower |  | 1 | 100% | 100% |  |  |  |  | x | 116 | 115 | 3 | 2
128 |  |  | D1002824-v1 | Earthquake Stop Bracket Side, Bottom Mass, Lower |  | 1 | 100% | 100% |  |  |  |  | x | 117 | 116 | 4 | 3
129 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x |  |  | 5 | 1
130 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6 | 2
131 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7 | 3
132 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 8 | 4
133 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 9 | 5
134 |  | D070319-v2 |  | Earthquake Stop Assembly, Bridge |  | 8 | 100% | 100% |  |  |  |  | x | 118 | 117 | 1
135 |  |  | D070321-v2 | Earthquake Stop Bridge Crossbar |  | 1 | 100% | 100% |  |  |  |  | x | 119 | 118 | 2
136 |  |  | D0901241-v2 | Earthquake Stop Mount, Bridge |  | 1 | 100% | 100% |  |  |  |  | x | 120 | 119 | 3
137 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x |  |  | 4 | 1
138 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 5 | 2
139 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6 | 3
140 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7 | 4
141 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 8 | 5
142 |  | D0902024-v4 |  | Upper AOSEM Alignment Assembly, Intermediate Mass |  | 8 | 100% | 95% |  |  |  |  | x | 121 | 120 | 1
143 |  |  | D0902025-v2 | Upper AOSEM Mounting Bracket, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 122 | 121 | 2
144 |  |  | D0901492-v3 | AOSEM Alignment Bracket, Intermediate Mass |  | 1 | 100% | 95% |  |  |  |  | x | 123 | 122 | 3
145 |  |  | D0901065-v1 | AOSEM Assembly |  | 1 | 100% | 100% |  |  |  |  | x | 124 | 123 | 4
146 |  |  | D1002858-v1 | AOSEM Adjustment Collar (Reverse Side) |  | 1 | 100% | 100% |  |  |  |  | x | 125 | 124 | 5
147 |  |  | D1000659-v1 | AOSEM Adjuster Shaft |  | 1 | 100% | 100% |  |  |  |  | x | 126 | 125 | 6
148 |  |  | D1002865-v1 | Adjustment Nut, Thick, AOSEM Alignment Assembly |  | 1 | 100% | 100% |  |  |  |  | x | 127 | 126 | 7
149 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 8
150 |  | D0901551-v4 |  | Lower AOSEM Alignment Assembly, Intermediate Mass |  | 8 | 100% | 95% |  |  |  |  | x | 128 | 127 | 1
151 |  |  | D0901493-v2 | Lower AOSEM Mounting Bracket, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 129 | 128 | 2
152 |  |  | D0901492-v3 | AOSEM Alignment Bracket, Intermediate Mass |  | 1 | 100% | 95% |  |  |  |  | x |  |  | 3
153 |  |  | D0901065-v1 | AOSEM Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 4
154 |  |  | D1002858-v1 | AOSEM Adjustment Collar (Reverse Side) |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 5
155 |  |  | D1000659-v1 | AOSEM Adjuster Shaft |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6
156 |  |  | D1002865-v1 | Adjustment Nut, Thick, AOSEM Alignment Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7
157 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 8
158 |  | D0901552-v4 |  | Upper AOSEM Alignment Assembly, Bottom Mass |  | 12 | 100% | 95% |  |  |  |  | x | 130 | 129 | 1
159 |  |  | D0901550-v2 | Upper AOSEM Mounting Bracket, Bottom Mass |  | 1 | 100% | 100% |  |  |  |  | x | 131 | 130 | 2
160 |  |  | D0901549-v3 | AOSEM Alignment Bracket, Bottom Mass |  | 1 | 100% | 95% |  |  |  |  | x | 132 | 131 | 3
161 |  |  | D0901065-v1 | AOSEM Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 4
162 |  |  | D1002858-v1 | AOSEM Adjustment Collar (Reverse Side) |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 5
163 |  |  | D1000659-v1 | AOSEM Adjuster Shaft |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6
164 |  |  | D1002865-v1 | Adjustment Nut, Thick, AOSEM Alignment Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7
165 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x |  |  | 8 | 1
166 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 9 | 2
167 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 10 | 3
168 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 11 | 4
169 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 12 | 5
170 |  | D0901553-v4 |  | Lower AOSEM Alignment Assembly, Test Mass |  | 12 | 100% | 95% |  |  |  |  | x | 133 | 132 | 1
171 |  |  | D0900340-v2 | Lower AOSEM Mounting Bracket, Bottom Mass |  | 1 | 100% | 100% |  |  |  |  | x | 134 | 133 | 2
172 |  |  | D0901549-v3 | AOSEM Alignment Bracket, Bottom Mass |  | 1 | 100% | 95% |  |  |  |  | x |  |  | 3
173 |  |  | D0901065-v1 | AOSEM Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 4
174 |  |  | D1002858-v1 | AOSEM Adjustment Collar (Reverse Side) |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 5
175 |  |  | D1000659-v1 | AOSEM Adjuster Shaft |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 6
176 |  |  | D1002865-v1 | Adjustment Nut, Thick, AOSEM Alignment Assembly |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 7
177 |  | D080725-v2 |  | Earthquake Stop for Metal or Glass |  | 5 | 100% | 100% |  |  |  |  | x |  |  | 8 | 1
178 |  |  | D030021-v2 | SHCS, 1/4-20 X 2.5 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 9 | 2
179 |  |  | D080724-v3 | Mounting Cap, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 10 | 3
180 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 11 | 4
181 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x |  |  | 12 | 5
182 |  |  | D080723-v2 | Cap Body, Resin, Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x | 135 | 134
183 | D080265-v3 |  |  | Upper Blade Bake Fixture |  | 7 | 100% | 100% |  |  |  |  | x | 136 | 1
184 |  |  | D080268-v2 | Base Plate, Upper Blade Bake Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 137 | 2
185 |  |  | D1003305-v1 | Stop Block, Upper Blade Bake Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 138 | 3
186 |  |  | D1003307-v1 | Holddown Bar, Upper Blade Bake Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 139 | 4
187 |  |  | D1003306-v1 | Side Support, Upper Blade Bake Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 140 | 5
188 |  |  | D080267-v2 | Top Bridge, Upper Blade Bake Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 141 | 6
189 |  |  | D0900999-v3 | SHCS, 1/4-20 X 2 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  | 7
190 | D0900665-v3 |  |  | Library of Clamps, Upper Blade |  | 18 | 100% | 100% |  |  |  |  | x | 142 | 1
191 |  |  | D0900666-v2 | Base Plate, Library of Clamps, Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x | 143 | 2
192 |  |  | D020622-v3 | Blade Clamp (0.0 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x |  | 3
193 |  |  | D0900667-v3 | Blade Clamp (0.5 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 144 | 4
194 |  |  | D0900668-v3 | Blade Clamp (1.0 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 145 | 5
195 |  |  | D0900669-v3 | Blade Clamp (1.5 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 146 | 6
196 |  |  | D0900670-v3 | Blade Clamp (2.0 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 147 | 7
197 |  |  | D0900671-v3 | Blade Clamp (2.5 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 148 | 8
198 |  |  | D0900672-v3 | Blade Clamp (3.0 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 149 | 9
199 |  |  | D0900673-v3 | Blade Clamp (3.5 Degree), Upper Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 150 | 10
200 |  |  | D020601-v2 | Blade Clamp (0.0 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x |  | 11
201 |  |  | D0900674-v2 | Blade Clamp (0.5 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 151 | 12
202 |  |  | D0900675-v2 | Blade Clamp (1.0 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 152 | 13
203 |  |  | D0900676-v2 | Blade Clamp (1.5 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 153 | 14
204 |  |  | D0900677-v2 | Blade Clamp (2.0 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 154 | 15
205 |  |  | D0900678-v2 | Blade Clamp (2.5 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 155 | 16
206 |  |  | D0900679-v2 | Blade Clamp (3.0 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 156 | 17
207 |  |  | D0900680-v2 | Blade Clamp (3.5 Degree), Upper Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 157 | 18
208 | D020660-v1 |  |  | Blade Pulldown Device, HAM Suspensions |  | 11 | 100% | 100% |  |  |  |  | x | 158 | 1
209 |  |  | D010266-v1 | Wire Clamp Cylinder |  | 1 | 100% | 100% |  |  |  |  | x | 159 | 2
210 |  |  | D010261-v1 | Lower Wire Clamp Plate |  | 1 | 100% | 100% |  |  |  |  | x | 160 | 3
211 |  |  | D010268-v1 | Lower Wire Clamp |  | 1 | 100% | 100% |  |  |  |  | x | 161 | 4
212 |  |  | D1003362-v1 | Base Plate, Blade Pulldown Device |  | 1 | 100% | 100% |  |  |  |  | x | 162 | 5
213 |  |  | D0901814-v1 | Upper Clamp, Upper Wire, Inside, HLTS (Blade Characterization Stand) |  | 1 | 100% | 100% |  |  |  |  | x | 163 | 6
214 |  |  | D070341-v3 | Upper Clamp, Upper Wire, Outside |  | 1 | 100% | 100% |  |  |  |  | x |  | 7
215 |  |  | D0901815-v1 | Upper Clamp, Int. Wire, Inside, HLTS (Blade Characterization Stand) |  | 1 | 100% | 100% |  |  |  |  | x | 164 | 8
216 |  |  | D0901813-v1 | Upper Clamp, Int. Wire, Outside, HLTS (Blade Characterization Stand) |  | 1 | 100% | 100% |  |  |  |  | x | 165 | 9
217 |  |  | D20132-v2 | HSTS Lower Blade Wire Clamp, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 166 | 10
218 |  |  | D0901855-v1 | Upper Clamp, Int. Wire, Outside, OMC/HSTS (Blade Characterization Stand) |  | 1 | 100% | 100% |  |  |  |  | x | 167 | 11
219 | D0900594-v2 |  |  | Upper Wire Jig Assembly |  | 8 | 100% | 100% |  |  |  |  | x | 168 | 1
220 |  |  | D0900595-v2 | Base Plate, Upper Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 169 | 2
221 |  |  | D0900563-v3 | Pin Support, Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 170 | 3
222 |  |  | D0900596-v2 | Blade Clamp Mount, Upper Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 171 | 4
223 |  |  | D0900597-v2 | Wire Clamp Mount, Upper Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 172 | 5
224 |  |  | D0900603-v2 | Wire Start Clamp, Inside, Upper Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 173 | 6
225 |  |  | D020380-v2 | Wire Start Clamp, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 174 | 7
226 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x | 175 | 8
227 | D0900681-v2 |  |  | Library of Clamps, Lower Blade |  | 18 | 100% | 100% |  |  |  |  | x | 176 | 1
228 |  |  | D0900689-v2 | Base Plate, Library of Clamps, Lower Blade |  | 1 | 100% | 100% |  |  |  |  | x | 177 | 2
229 |  |  | D020602-v2 | Blade Clamp (0.0 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 178 | 3
230 |  |  | D0900682-v2 | Blade Clamp (0.5 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 179 | 4
231 |  |  | D0900683-v2 | Blade Clamp (1.0 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 180 | 5
232 |  |  | D0900684-v2 | Blade Clamp (1.5 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 181 | 6
233 |  |  | D0900685-v2 | Blade Clamp (2.0 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 182 | 7
234 |  |  | D0900686-v2 | Blade Clamp (2.5 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 183 | 8
235 |  |  | D0900687-v2 | Blade Clamp (3.0 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 184 | 9
236 |  |  | D0900688-v2 | Blade Clamp (3.5 Degree), Lower Blade, Inside |  | 1 | 100% | 100% |  |  |  |  | x | 185 | 10
237 |  |  | D020623-v2 | Blade Clamp (0.0 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 186 | 11
238 |  |  | D0900690-v2 | Blade Clamp (0.5 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 187 | 12
239 |  |  | D0900691-v2 | Blade Clamp (1.0 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 188 | 13
240 |  |  | D0900692-v2 | Blade Clamp (1.5 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 189 | 14
241 |  |  | D0900693-v2 | Blade Clamp (2.0 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 190 | 15
242 |  |  | D0900694-v2 | Blade Clamp (2.5 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 191 | 16
243 |  |  | D0900695-v2 | Blade Clamp (3.0 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 192 | 17
244 |  |  | D0900696-v2 | Blade Clamp (3.5 Degree), Lower Blade, Outside |  | 1 | 100% | 100% |  |  |  |  | x | 193 | 18
245 | D1002500-v1 |  |  | Magnetic Plug Installation Fixture Arrangement |  | 2 | 100% | 100% |  |  |  |  | x | 194 | 1
246 |  |  | D1000244-v1 | Magnetic Plug Installation Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 195 | 2
247 | D0900630-v1 |  |  | Intermediate Wire Jig Assembly |  | 8 | 100% | 100% |  |  |  |  | x | 196 | 1
248 |  |  | D0900633-v2 | Base Plate, Intermediate Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 197 | 2
249 |  |  | D0900563-v3 | Pin Support, Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x |  | 3
250 |  |  | D0900631-v2 | Blade Clamp Mount, Intermediate Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 198 | 4
251 |  |  | D0900632-v2 | Wire Clamp Mount, Intermediate Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 199 | 5
252 |  |  | D0900634-v2 | Wire Start Clamp, Inside, Intermediate Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 200 | 6
253 |  |  | D020380-v2 | Wire Start Clamp, Outside |  | 1 | 100% | 100% |  |  |  |  | x |  | 7
254 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 8
255 | D1002371-v1 |  |  | Magnet Gluing Fixture Assembly |  | 4 | 100% | 100% |  |  |  |  | x | 201 | 1
256 |  |  | D1002372-v1 | Magnet Gluing Holder |  | 1 | 100% | 100% |  |  |  |  | x | 202 | 2
257 |  |  | D1002373-v1 | Magnet Gluing Clamping Block |  | 1 | 100% | 100% |  |  |  |  | x | 203 | 3
258 |  |  | D1100757-v1 | Magnet Gluing Fixture, Base Plate |  | 1 | 100% | 100% |  |  |  |  | x | 204 | 4
259 | D0901461-v2 |  |  | Magnet Placement Fixture, Intermediate Mass |  | 11 | 100% | 100% |  |  |  |  | x | 205 | 1
260 |  |  | D0902060-v2 | Base Plate, Magnet Placement Fixture, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 206 | 2
261 |  |  | D0902062-v2 | Vertical Locating Block, Magnet Placement Fixture, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x | 207 | 3
262 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 4
263 |  | D0902444-v2 |  | Positioning Standoff, Magnet Placement Fixture, Intermediate Mass |  | 5 | 100% | 100% |  |  |  |  | x | 208 | 5 | 1
264 |  |  | D0902445-v2 | Standoff Plate |  | 1 | 100% | 100% |  |  |  |  | x | 209 | 6 | 2
265 |  |  | D1002342-v1 | Standoff Block for HSTS Ring Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 210 | 7 | 3
266 |  |  | D0902452-v2 | Standoff Side Plate, Short |  | 1 | 100% | 100% |  |  |  |  | x | 211 | 8 | 4
267 |  |  | D0900999-v3 | SHCS, 1/4-20 X 2 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  | 9 | 5
268 |  |  | D1002341-v1 | Magnet Bushing for HSTS Ring Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 212 | 10
269 |  |  | D1100043-v1 | Magnet Gluing Weight |  | 1 | 100% | 100% |  |  |  |  | x | 213 | 11
270 | D0901419-v2 |  |  | Lower Loop Wire Jig Assembly |  | 7 | 100% | 100% |  |  |  |  | x | 214 | 1
271 |  |  | D0901433-v2 | Base Plate, Lower Loop Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 215 | 2
272 |  |  | D0900563-v3 | Pin Support, Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x |  | 3
273 |  |  | D0901435-v3 | Wire Start Clamp, Inside, Lower Loop Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 216 | 4
274 |  |  | D020380-v2 | Wire Start Clamp, Outside |  | 1 | 100% | 100% |  |  |  |  | x |  | 5
275 |  |  | D0901436-v2 | Wire Clamp Mount, Lower Loop Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x | 217 | 6
276 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 7
277 | D0901460-v2 |  |  | Magnet Placement Fixture, Bottom Mass, HLTS |  | 14 | 100% | 100% |  |  |  |  | x | 218 | 1
278 |  | D1100356-v2 |  | Optic Base Assembly, Magnet Placement Fixture |  | 5 | 100% | 100% |  |  |  |  | x | 219 | 2 | 1
279 |  |  | D0902064-v2 | Base Plate, Optic Base Assembly |  | 1 | 100% | 100% |  |  |  |  | x | 220 | 3 | 2
280 |  |  | D1100360-v1 | Optic Base Riser, Magnet Placement Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 221 | 4 | 3
281 |  |  | D0902066-v2 | Optic Rest Block |  | 1 | 100% | 100% |  |  |  |  | x | 222 | 5 | 4
282 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 6 | 5
283 |  | D0902087-v2 |  | Positioning Standoff, Magnet Placement Fixture, Bottom Mass |  | 6 | 100% | 100% |  |  |  |  | x | 223 | 7 | 1
284 |  |  | D0902068-v2 | Standoff Ring |  | 1 | 100% | 100% |  |  |  |  | x | 224 | 8 | 2
285 |  |  | D1002342-v1 | Standoff Block for HSTS Ring Fixture |  | 1 | 100% | 100% |  |  |  |  | x |  | 9 | 3
286 |  |  | D1002405-v1 | Locating Stop, Magnet Fixture |  | 1 | 100% | 100% |  |  |  |  | x | 225 | 10 | 4
287 |  |  | D990148-v1 | Fluorel Tip, 1/4-20 |  | 1 | 100% | 100% |  |  |  |  | x | 226 | 11 | 5
288 |  |  | D0900999-v3 | SHCS, 1/4-20 X 2 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x |  | 12 | 6
289 |  |  | D1002341-v1 | Magnet Bushing for HSTS Ring Fixture |  | 1 | 100% | 100% |  |  |  |  | x |  | 13
290 |  |  | D1100043-v1 | Magnet Gluing Weight |  | 1 | 100% | 100% |  |  |  |  | x |  | 14
291 | D0902459-v1 |  |  | Sapphire Prism Placement Fixture |  | 17 | 100% | 100% |  |  |  | x |  | 227 | 1
292 |  | D0902658-v1 |  | Optic Holder, HAM Triple Suspension |  | 5 | 100% | 100% |  |  |  | x |  | 228 | 2 | 1
293 |  |  | D0902460-v1 | Base Plate, Optic Holder |  | 1 | 100% | 100% |  |  |  | x |  | 229 | 3 | 2
294 |  |  | D0902461-v1 | Optic Rest Wedge, Optic Holder |  | 1 | 100% | 100% |  |  |  | x |  | 230 | 4 | 3
295 |  |  | D0902585-v1 | Optic Rest Plate, Optic Holder |  | 1 | 100% | 100% |  |  |  | x |  | 231 | 5 | 4
296 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 6 | 5
297 |  | D0902661-v1 |  | Sapphire Prism Bonding Jig |  | 11 | 100% | 100% |  |  |  | x |  | 232 | 7 | 1
298 |  | D0902662-v1 |  | Sapphire Prism Bonding Fixture |  | 6 | 100% | 100% |  |  |  | x |  | 233 | 8 | 2 | 1
299 |  |  | D0902665-v1 | Bonding Template Front, Sapphire Prism |  | 1 | 100% | 100% |  |  |  | x |  | 234 | 9 | 3 | 2
300 |  |  | D0902666-v1 | Bonding Template Side, Sapphire Prism |  | 1 | 100% | 100% |  |  |  | x |  | 235 | 10 | 4 | 3
301 |  |  | D080409-v1 | Alignment Guide |  | 1 | 100% | 100% |  |  |  | x |  | 236 | 11 | 5 | 4
302 |  |  | D0902721-v1 | Sapphire Prism Holder Guide |  | 1 | 100% | 100% |  |  |  | x |  | 237 | 12 | 6 | 5
303 |  |  | D0902669-v1 | Support Cylinder, Sapphire Prism Bonding Fixture |  | 1 | 100% | 100% |  |  |  | x |  | 238 | 13 | 7 | 6
304 |  | D0902663-v1 |  | Sapphire Prism Holder Assembly |  | 4 | 100% | 100% |  |  |  | x |  | 239 | 14 | 8 | 1
305 |  |  | D0902664-v1 | Sapphire Prism Holder |  | 1 | 100% | 100% |  |  |  | x |  | 240 | 15 | 9 | 2
306 |  |  | D0902722-v1 | Sapphire Prism Holder Extension |  | 1 | 100% | 100% |  |  |  | x |  | 241 | 16 | 10 | 3
307 |  |  | D080468-v1 | SHCS, #2-56 X 0.375 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  | x |  | 242 | 17 | 11 | 4
308 |  |  | D1002743-v1 | Ergo Arm Vacuum Plate, SR3/PR3/F-PR3 Optic |  | 1 | 100% | 0% |  |  |  |  | x | 243
309 |  |  | D1101127-v1 | HLTS Optics Cap |  | 1 | 100% | 90% |  |  |  |  | x | 244
310 | D1000960-v1 |  |  | HAM Suspension Testing Cover Assembly |  | 5 | 100% | 100% |  |  |  |  | x | 245 | 1
311 |  |  | D1000961-v1 | HAM Suspension Testing Cover Weldment |  | 1 | 100% | 100% |  |  |  |  | x | 246 | 2
312 |  |  | D980184-v2 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x |  | 3
313 |  |  | D1001085-v1 | HAM Suspension Testing Cover Door Weldment |  | 1 | 100% | 100% |  |  |  |  | x | 247 | 4
314 |  |  | D1001133-v2 | HAM Suspension Testing Cover |  | 1 | 100% | 90% |  |  |  |  | x | 248 | 5
[5 empty] | TOTAL | 248

## HSTS Mechanical
HSTS Mechanical Drawing Completion Status
Drawing Completion Legend:
Subsystem: | SUS |  |  | <80% - Drawing in progress. The closer to 80%, the closer it is to completion
Reporter: | Mike Meyer |  |  | 80% - Minor changes needed to drawing
Date: | 2010-09-08 |  |  | 90% - Drawing complete but needs to be reviewed and uploaded to DCC
95% - Drawing uploaded to DCC but awaiting signatures
100% - Drawing approved
[7 empty] | % Complete |  | Design Maturity Level
Line # | Assembly # | Sub-Assy # | Part # | Title | BOM | No. of Dwgs | Model Status | Drawing Status | CDR | PDR | Delta- PDR | FDR | Production Revision
1 | D040391-v1 |  |  | HAM SMALL TRIPLE SUSPENSION OVERALL ASSEMBLY AND ASSEMBLY FIXTURES | E1000035-v1 | 1 | 75% | 75% |  |  |  | x
2 |  | D020700-v1 |  | HAM SMALL TRIPLE SUSPENSION OVERALL ASSEMBLY |  | 1 | 100% | 90% |  |  |  | x
3 |  | D020023-v2 |  | STRUCTURAL WELDMENT ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
4 |  |  | D070052-v2 | Connector Bracket, OMC |  | 1 | 100% | 100% |  |  |  |  | x
5 |  | D0902462-v1 |  | UHV COMPATIBLE CABLE CLAMP ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
6 |  |  | D0900004-v1 | UHV Compatible Cable Clamp |  | 1 | 100% | 100% |  |  |  |  | x
7 |  | D0901934-v1 |  | TOP BLADE GUARD ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
8 |  |  | D0901935-v1 | Blade Guard Crosspiece, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
9 |  |  | D0901936-v1 | Blade Guard Riser, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
10 |  |  | D0900999-v1 | SHCS, 1/4-20 x 2, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  |  | x
11 |  | D1000045-v1 |  | ROTATIONAL ADJUSTER ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
12 |  |  | D030448-v2 | Base Plate |  | 1 | 100% | 100% |  |  |  |  | x
13 |  |  | D030447-v2 | Rotating Plate |  | 1 | 100% | 100% |  |  |  |  | x
14 |  |  | D1001812-v1 | Upper Blade |  | 1 | 100% | 100% |  |  |  |  | x
15 |  |  | D030450-v2 | Pull Plate |  | 1 | 100% | 100% |  |  |  |  | x
16 |  |  | D030449-v2 | Push Plate |  | 1 | 100% | 100% |  |  |  |  | x
17 |  | D020677-v1 |  | LIBRARY OF CLAMPS ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
18 |  |  | D020116-v2 | Upper Blade Clamp, Upper Side, 0.0 Degree |  | 1 | 100% | 100% |  |  |  |  | x
19 |  |  | D020325-v2 | Upper Blade Clamp, Upper Side, Angled 0.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
20 |  |  | D020328-v2 | Upper Blade Clamp, Upper Side, Angled 2.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
21 |  |  | D020312-v2 | Upper Blade Clamp, Upper Side, Angled 2.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
22 |  |  | D020327-v2 | Upper Blade Clamp, Upper Side, Angled 1.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
23 |  |  | D020326-v2 | Upper Blade Clamp, Upper Side, Angled 1.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
24 |  |  | D020679-v2 | Upper Blade Clamp, Lower Side Shim, 1mm |  | 1 | 100% | 100% |  |  |  |  | x
25 |  |  | D020680-v2 | Upper Blade Clamp, Lower Side Shim, 2mm |  | 1 | 100% | 100% |  |  |  |  | x
26 |  |  | D020340-v2 | Lower Blade Clamp, Upper Side, Angled 2.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
27 |  |  | D020336-v2 | Lower Blade Clamp, Lower Side, Angled 2.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
28 |  |  | D020313-v2 | Lower Blade Clamp, Lower Side, Angled 2.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
29 |  |  | D020314-v2 | Lower Blade Clamp, Upper Side, Angled 2.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
30 |  |  | D020339-v2 | Lower Blade Clamp, Upper Side, Angled 1.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
31 |  |  | D020335-v2 | Lower Blade Clamp, Lower Side, Angled 1.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
32 |  |  | D020334-v2 | Lower Blade Clamp, Lower Side, Angled 1.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
33 |  |  | D020338-v2 | Lower Blade Clamp, Upper Side, Angled 1.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
34 |  |  | D020333-v2 | Lower Blade Clamp, Lower Side, Angled 0.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
35 |  |  | D020337-v2 | Lower Blade Clamp, Upper Side, Angled 0.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
36 |  |  | D020682-v2 | Lower Blade Clamp, Shim, 1mm |  | 1 | 100% | 100% |  |  |  |  | x
37 |  |  | D020119-v2 | Lower Blade Clamp, Upper Side, 0.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
38 |  |  | D020308-v2 | Lower Blade Clamp, Lower Side, 0.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
39 |  |  | D020689-v2 | Upper Blade Clamp, Upper Side, Angled 3.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
40 |  |  | D020690-v2 | Upper Blade Clamp, Upper Side, Angled 3.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
41 |  |  | D030459-v2 | RA Upper Blade Clamp Lower Side 0.0 Degree |  | 1 | 100% | 100% |  |  |  |  | x
42 |  |  | D030460-v2 | RA Upper Blade Clamp Lower Side, Angled 0.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
43 |  |  | D030461-v2 | RA Upper Blade Clamp Lower Side, Angled 1.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
44 |  |  | D030462-v2 | RA Upper Blade Clamp Lower Side, Angled 1.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
45 |  |  | D030463-v2 | RA Upper Blade Clamp Lower Side, Angled 2.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
46 |  |  | D030464-v2 | RA Upper Blade Clamp Lower Side, Angled 2.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
47 |  |  | D030465-v2 | RA Upper Blade Clamp Lower Side, Angled 3.0 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
48 |  |  | D030466-v2 | RA Upper Blade Clamp Lower Side, Angled 3.5 Degrees |  | 1 | 100% | 100% |  |  |  |  | x
49 |  | D0901854-v1 |  | HSTS UPPER WIRE ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
50 |  |  | D020481-v1 | Upper Mass C-Clamp |  | 1 | 100% | 100% |  |  |  |  | x
51 |  |  | D0901999-v1 | Upper Mass Wire Clamp, Inside, Angled |  | 1 | 100% | 100% |  |  |  |  | x
52 |  |  | D0901998-v1 | Upper Mass Wire Clamp, Outside, Angled |  | 1 | 100% | 100% |  |  |  |  | x
53 |  |  | D020198-v1 | Upper Blade Wire Clamp |  | 1 | 100% | 100% |  |  |  |  | x
54 |  |  | D0901994-v1 | Upper Blade Wire Clamp, Outside, Angled |  | 1 | 100% | 100% |  |  |  |  | x
55 |  |  | D020346-v1 | Coilholder (Table Cloth) Bracket |  | 1 | 100% | 100% |  |  |  |  | x
56 |  | D020535-v1 |  | UPPER MASS AND COILHOLDER ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
57 |  |  | D020239-v1 | HSTS Coilholder (Table Cloth) |  | 1 | 100% | 100% |  |  |  |  | x
58 |  | D020534-v1 |  | UPPER MASS ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
59 |  |  | D020134-v1 | Main Section, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
60 |  |  | D020136-v1 | T-Section, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
61 |  |  | D020137-v1 | Pitch Insert for T-Section |  | 1 | 100% | 100% |  |  |  |  | x
62 |  |  | D020676-v1 | Roll Insert for T-Section |  | 1 | 100% | 100% |  |  |  |  | x
63 |  |  | D0902030-v1 | Blade Guard, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
64 |  |  | D080761-v2 | Lower Blade |  | 1 | 100% | 100% |  |  |  |  | x
65 |  |  | D0902493-v1 | Base Plate, Magnet/Flag Assembly, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
66 |  |  | D020199-v1 | Magnet-Flag Base (Short), Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
67 |  |  | D020211-v1 | Magnet Holder Brace |  | 1 | 100% | 100% |  |  |  |  | x
68 |  | D0902492-v1 |  | MAGNET/FLAG ASSEMBLY (SHORT), UPPER MASS |  | 1 | 100% | 100% |  |  |  |  | x
69 |  |  | D0902494-v1 | Magnet Holder (Short), Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
70 |  | D0902418-v1 |  | MAGNET/FLAG ASSEMBLY (LONG), UPPER MASS |  | 1 | 100% | 100% |  |  |  |  | x
71 |  |  | D0902423-v1 | Magnet Holder (Long), Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
72 |  |  | D020482-v2 | Screw Drive System, Upper Mass |  | 1 | 100% | 100% |  |  |  |  | x
73 |  |  | D030025-v1 | SHCS, #8-32 x 1, Fully Threaded, Rounded End (Ag-Plated) |  | 1 | 100% | 100% |  |  |  |  | x
74 |  | D0901905-v1 |  | INTERMEDIATE WIRE ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
75 |  |  | D020132-v1 | Lower Blade Wire Clamp |  | 1 | 100% | 100% |  |  |  |  | x
76 |  |  | D030044-v1 | Lower Blade Wire Clamp Plate, Angled |  | 1 | 100% | 100% |  |  |  |  | x
77 |  |  | D0901904-v1 | Intermediate Wire Clamp Mount, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
78 |  |  | D0901903-v1 | Intermediate Wire Clamp, Outside, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
79 |  | D0901873-v2 |  | INTERMEDIATE MASS ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
80 |  |  | D0901792-v1 | Intermediate Mass, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
81 |  | D020661-v1 |  | MAGNET AND DUMBBELL ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
82 |  |  | D970075-v1 | Dumbbell Standoff |  | 1 | 100% | 100% |  |  |  |  | x
83 |  |  | D0901927-v1 | Sintered SmCo Magnet, 0.075" x 0.125" Long) |  | 1 | 100% | 100% |  |  |  |  | x
84 |  |  | D020350-v2 | 100g Add-on Mass |  | 1 | 100% | 100% |  |  |  |  | x
85 |  |  | D020531-v1 | 50g Add-on Mass |  | 1 | 100% | 100% |  |  |  |  | x
86 |  |  | D030078-v1 | 20g Add-on Mass |  | 1 | 100% | 100% |  |  |  |  | x
87 |  | D0902203-v1 |  | BARREL EQ STOP ASSEMBLY, HSTS INTERMEDIATE WIRE |  | 1 | 100% | 100% |  |  |  |  | x
88 |  |  | D0901925-v1 | Barrel EQ Stop Crossbar, Intermediate Wire |  | 1 | 100% | 100% |  |  |  |  | x
89 |  | D0902007-v1 |  | BARREL EQ STOP BRACKET ASSEMBLY |  | 1 | 100% | 100% |  |  |  |  | x
90 |  |  | D0902008-v1 | Barrel EQ Stop Bracket |  | 1 | 100% | 100% |  |  |  |  | x
91 |  |  | D0902009-v1 | Barrel EQ Stop Base |  | 1 | 100% | 100% |  |  |  |  | x
92 |  | D0900932-v1 |  | EQ STOP FOR GLASS (GLASS TIP), SIMPLIFIED, 2 INCH |  | 1 | 100% | 100% |  |  |  |  | x
93 |  |  | D0900906-v1 | EQ Stop Adjuster and Mount, 2 Inch |  | 1 | 100% | 100% |  |  |  |  | x
94 |  |  | D060546-v2 | Impact Absorber for Glass Stops |  | 1 | 100% | 100% |  |  |  |  | x
95 |  |  | D060548-v1 | Fused Silica Earthquake Stop |  | 1 | 100% | 100% |  |  |  |  | x
96 |  | D0902413-v1 |  | FACE EQ STOP ASSEMBLY, INTERMEDIATE MASS |  | 1 | 100% | 100% |  |  |  |  | x
97 |  |  | D0902204-v1 | Face EQ Stop Bracket, HSTS Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x
98 |  |  | D0901923-v1 | Face EQ Stop Base, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
99 |  | D0901924-v1 |  | AOSEM ALIGNMENT ASSEMBLY, INTERMEDIATE MASS |  | 1 | 100% | 100% |  |  |  |  | x
100 |  |  | D0902414-v1 | AOSEM Alignment Bracket, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x
101 |  |  | D0901548-v1 | AOSEM Adjustment Collar |  | 1 | 100% | 100% |  |  |  |  | x
102 |  |  | D0902206-v1 | AOSEM Alignment Bracket Mount, Intermediate Mass |  | 1 | 100% | 100% |  |  |  |  | x
103 |  | D0901902-v1 |  | LOWER WIRE ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
104 |  |  | D020202-v1 | Lower Wire Clamp Mount |  | 1 | 100% | 100% |  |  |  |  | x
105 |  |  | D020203-v1 | Lower Wire Clamp |  | 1 | 100% | 100% |  |  |  |  | x
106 |  | D0901791-v1 |  | METAL Lower MASS ASSEMBLY (MC), HSTS |  | 1 | 100% | 100% |  |  |  |  | x
107 |  |  | D020234-v1 | Metal Lower Mass (MC), HSTS |  | 1 | 100% | 100% |  |  |  |  | x
108 |  |  | D0901790-v1 | Primary Metal Breakoff Prism, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
109 |  | D0902432-v1 |  | MAGNET/STANDOFF ASSEMBLY, HSTS LOWER MASS |  | 1 | 100% | 100% |  |  |  |  | x
110 |  |  | D0902431-v1 | Magnet Standoff, HSTS Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
111 |  |  | D0901278-v1 | HSTS Secondary Metal Prism |  | 1 | 100% | 100% |  |  |  |  | x
112 |  | D0902333-v1 |  | METAL LOWER MASS ASSEMBLY (PR/SR), HSTS |  | 1 | 100% | 100% |  |  |  |  | x
113 |  |  | D0902332-v1 | Metal Lower Mass (PR/SR), HSTS |  | 1 | 100% | 100% |  |  |  |  | x
114 |  |  | D0901790-v1 | Primary Metal Breakoff Prism, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
115 |  | D0902201-v1 |  | BARREL EQ STOP ASSEMBLY, HSTS LOWER WIRE |  | 1 | 100% | 100% |  |  |  |  | x
116 |  |  | D0902202-v1 | Barrel EQ Stop Crossbar, Lower Wire |  | 1 | 100% | 100% |  |  |  |  | x
117 |  | D0902207-v1 |  | UPPER AOSEM ALIGNMENT ASSEMBLY, LOWER MASS |  | 1 | 100% | 100% |  |  |  |  | x
118 |  |  | D0902417-v1 | AOSEM Alignment Bracket, Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
119 |  |  | D0902416-v1 | Upper AOSEM Alignment Bracket Mount, Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
120 |  | D0902208-v1 |  | LOWER AOSEM ALIGNMENT ASSEMBLY, LOWER MASS |  | 1 | 100% | 100% |  |  |  |  | x
121 |  |  | D0902417-v1 | AOSEM Alignment Bracket, Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
122 |  |  | D0902415-v1 | Lower AOSEM Alignment Bracket Mount, Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
123 |  | D0902205-v1 |  | FACE EQ STOP ASSEMBLY, LOWER MASS |  | 1 | 100% | 100% |  |  |  |  | x
124 |  |  | D0901922-v1 | Face EQ Stop Bracket, HSTS Lower Mass |  | 1 | 100% | 100% |  |  |  |  | x
125 |  | D0902108-v1 |  | UPPER WIRE JIG ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
126 |  |  | D0902109-v1 | Base Plate, Upper Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x
127 |  |  | D0900563-v1 | Pin Support, Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x
128 |  |  | D0900603-v1 | Wire Start Clamp, Inside |  | 1 | 100% | 100% |  |  |  |  | x
129 |  |  | D020380-v1 | Wire Start Clamp, Outside |  | 1 | 100% | 100% |  |  |  |  | x
130 |  |  | D0900597-v1 | Wire Clamp Mount, Upper Wire |  | 1 | 100% | 100% |  |  |  |  | x
131 |  |  | D0900596-v1 | Blade Clamp Mount, Upper Wire |  | 1 | 100% | 100% |  |  |  |  | x
132 |  |  | D980184-v1 | LOS Clamp, Long |  | 1 | 100% | 100% |  |  |  |  | x
133 |  | D0902526-v1 |  | INTERMEDIATE WIRE JIG ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
134 |  |  | D0902535-v1 | Base Plate, Intermediate Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x
135 |  |  | D0902533-v1 | Mass Wire Clamp Bracket, Intermediate Wire |  | 1 | 100% | 100% |  |  |  |  | x
136 |  |  | D0902532-v1 | Blade Wire Clamp Bracket, Intermediate Wire |  | 1 | 100% | 100% |  |  |  |  | x
137 |  | D0902524-v1 |  | LOWER WIRE JIG ASSEMBLY, HSTS |  | 1 | 100% | 100% |  |  |  |  | x
138 |  |  | D0902540-v1 | Base Plate, Lower Wire Jig |  | 1 | 100% | 100% |  |  |  |  | x
139 |  |  | D0902539-v1 | Wire Clamp Block, Lower Wire |  | 1 | 100% | 100% |  |  |  |  | x
140 |  |  | D0901435-v1 | Wire Start Clamp, Inside |  | 1 | 100% | 100% |  |  |  |  | x
141 |  |  | D020494-v1 | Alignment Target (For Local Sensors) |  | 1 | 100% | 0% |  |  |  | x
142 |  | D020458-v1 |  | BASIC ALUMINUM CATCHER ASSEMBLY FOR INTERMEDIATE AND TEST MASS |  | 1 | 100% | 0% |  |  |  | x
143 |  |  | D020445-v1 | V-Clamp for Bar Catcher |  | 1 | 100% | 90% |  |  |  | x
144 |  |  | D020448-v1 | Catcher Bar for Intermediate Mass |  | 1 | 100% | 90% |  |  |  | x
145 |  |  | D020446-v1 | Bar Attachment, Lower |  | 1 | 100% | 90% |  |  |  | x
146 |  |  | D020447-v1 | Bar Attachment, Upper |  | 1 | 100% | 90% |  |  |  | x
147 |  |  | D020449-v1 | Catcher Bar for Lower Mass |  | 1 | 100% | 90% |  |  |  | x
148 |  |  | D040259-v1 | Tablecloth and Upper Mass Table Jig |  | 1 | 100% | 90% |  |  |  | x
149 |  |  | D020450-v1 | Bar Plate (Fixture Assembly) |  | 1 | 100% | 90% |  |  |  | x
150 |  |  | D020350-v1 | Upper Mass, 100g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
151 |  |  | D020531-v1 | Upper Mass, 50g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
152 |  |  | D030468-v1 | 40g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
153 |  |  | D030457-v1 | Spacer, 120g Mass |  | 1 | 100% | 90% |  |  |  | x
154 |  |  | D030456-v1 | Spacer, 75g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
155 |  |  | D030455-v1 | Spacer, 35g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
156 |  |  | D030454-v1 | Spacer, 60g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
157 |  |  | D030079-v1 | Upper Mass, 10g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
158 |  |  | D030078-v1 | Upper Mass, 20g Add-On Mass |  | 1 | 100% | 90% |  |  |  | x
159 |  | D020660-v1 |  | INTERMEDIATE BLADE DEFLECTION JIG ASSEMBLY |  | 1 | 100% | 90% |  |  |  | x
160 |  |  | D010264-v1 | Intermediate Blade Wire Clamp |  | 1 | 100% | 90% |  |  |  | x
161 |  |  | D010266-v1 | Intermediate Blade Mass Clamp Cylinder |  | 1 | 100% | 90% |  |  |  | x
162 |  |  | D010261-v1 | Intermediate Blade Mass Clamp |  | 1 | 100% | 90% |  |  |  | x
163 |  |  | D010265-v1 | Intermediate Wire Clamp Plate |  | 1 | 100% | 90% |  |  |  | x
164 |  |  | D010268-v1 | Intermediate Blade Mass Clamp Plate |  | 1 | 100% | 90% |  |  |  | x
165 |  | D030269-v1 |  | BLADE DAMPER ASSEMBLY |  | 1 | 100% | 90% |  |  |  | x
166 |  |  | D030264-v1 | Blade Damper Arm |  | 1 | 100% | 0% |  |  |  | x
167 |  |  | D030263-v1 | Copper Sleeve |  | 1 | 100% | 0% |  |  |  | x
168 |  |  | D020466-v1 | Nickel Plated Magnet |  | 1 | 100% | 0% |  |  |  | x
169 |  |  | D020215-v1 | Small Catcher for Lower Blades |  | 1 | 100% | 90% |  |  |  | x
170 |  | D020427-v1 |  | MAGNET PLACEMENT FIXTURE ASSEMBLY |  | 1 | 100% | 100% |  |  |  | x
171 |  |  | D0902542-v1 | Magnet Placement Ring, HSTS |  | 1 | 100% | 100% |  |  |  | x
172 |  |  | D1002342-v1 | Standoff Block |  | 1 | 100% | 100% |  |  |  | x
173 |  |  | D990148-v1 | Fluorel Tip, 1/4-20 |  | 3 | 100% | 90% |  |  |  | x
174 |  |  | D1002341-v1 | Magnet Bushing for HSTS Ring Fixture |  | 1 | 100% | 100% |  |  |  | x
175 |  | D0902543-v1 |  | HSTS PRISM FIXTURE ASSEMBLY |  | 15 | 50% | 0% |  |  |  | x
176 |  |  | D0902538-v1 | Dog Clamp, HSTS |  | 1 | 100% | 100% |  |  |  | x
177 |  | D1002606-v1 |  | Intermediate Magnet Placement Fixture Assembly |  | 1 | 100% | 100% |  |  |  | x
178 |  |  | D1002607-v1 | Intermediate Magnet Placement Ring, HSTS |  | 1 | 100% | 100% |  |  |  | x
179 |  |  | D1100043-v1 | Magnet Gluing weight |  | 1 | 100% | 100%
180 |  |  | D1002341 | Magnet Bushing For HSTS Ring Fixture |  | 1 | 100% | 100%
181 |  | D1002371-v1 |  | HSTS Magnet Gluing Fixture Assembly |  | 1 | 100% | 100% |  |  |  | x
182 |  |  | D1002372-v1 | HSTS Magnet Gluing Holder |  | 1 | 100% | 100% |  |  |  | x
183 |  |  | D1002373-v1 | HSTS Magnet Gluing Clamping Block |  | 1 | 100% | 100% |  |  |  | x
184 |  | D1002440-v1 |  | Upper Blade Baking Fixture |  | 4 | 100% | 100% |  |  |  | x
185 |  |  | D1002445 | Upper Blade Baking Fixture Base Plate, HSTS |  | 1 | 100% | 100% |  |  |  | x
186 |  |  | D030447 | Rotating Plate |  | 1 | 100% | 100% |  |  |  | x
187 |  |  | D020680 | Upper Blade Clamp Lowerside Shim 2mm |  | 1 | 100% | 100% |  |  |  | x
188 |  |  | D1001812 | HSTS Upper Blade |  | 1 | 100% | 100% |  |  |  | x
189 |  |  | D020116 | Upper Blade Clamp Upperside 0.0 Degree |  | 1 | 100% | 100% |  |  |  | x
190 |  |  | D1002444 | Upper Blade Baking Fixture Standoff, HSTS |  | 1 | 100% | 100% |  |  |  | x
191 |  |  | D1002443 | Upper Blade Baking Fixture Crossbar, HSTS |  | 1 | 100% | 100% |  |  |  | x
192 |  |  | D030459 | RA Upper Blade Clamp Lowerside 0.0 Degree |  | 1 | 100% | 100% |  |  |  | x
193 |  |  | D030023 | Screw, Socket Head Cap, 1/4-20 UNC-3A X 1 Long, Fully Threaded, Rounded End |  | 1 | 100% | 100% |  |  |  | x
194 |  | D1100393 |  | Prism Bonding Fixture, HSTS |  | 1 | 100% | 90%
195 |  |  | D0902460 | Base Plate |  | 1 | 100% | 90%
196 |  |  | D0902461 | Optic Rest Wedge |  | 1 | 100% | 90%
197 |  |  | D0902585 | Optic Rest Plate |  | 1 | 100% | 90%
198 |  |  | D1100394 | Prism Bonding Alignment Tool |  | 1 | 100% | 90%
199 |  |  | D1100395 | Bonding Template Front, HSTS |  | 1 | 100% | 90%
200 |  |  | D080409 | Alignment Guide |  | 1 | 100% | 90%
201 |  |  | D0902721 | Sapphire Prism Holder Guide |  | 1 | 100% | 90%
202 |  |  | D0902666 | Bonding Template Side |  | 1 | 100% | 90%
203 |  |  | D1100415 | Prism Holder, HSTS Prism Fixture |  | 1 | 100% | 90%
204 |  |  | D080468 | Screw, SHCS, #2-56 X 0.375", Fully Threaded, Rounded End |  | 1 | 100% | 90%
205 |  |  | D0902719 | Support Cylinder |  | 1 | 100% | 90%
[5 empty] | TOTAL | 224

## OMC Mechanical
OMC Mechanical Drawing Completion Status
Subsystem: | SUS
Reporter: | Mike Meyer
Date: | 2010-02-13
[7 empty] | % Complete |  | Design Maturity Level
Line # | Assembly # | Sub-Assy # | Part # | Title | BOM | No. of Dwgs | Model Status | Drawing Status | CDR | PDR | Delta- PDR | FDR | Production Revision
1 | D0900293-v1 |  |  | OUTPUT MODE CLEANER OVERALL ASSEMBLY WITH FIXTURES | E0900061-v1 | 119 | 100% | 100% |  |  |  | x | v1
[5 empty] | TOTAL | 119

## Quad Mech
ETM/ITM Suspension Mechanical Drawing Completion Status
Subsystem: | SUS
Reporter: | Janeen Romie
Date: | 2010-02-15
[7 empty] | % Complete |  | Design Maturity Level
Line # | Assembly # | Sub-Assy # | Part # | Title | BOM | No. of Dwgs | Model Status | Drawing Status | CDR | PDR | Delta- PDR | FDR | Production Revision
1 | D0901346-v2 |  |  | Advanced LIGO Quadruple Suspension | E0900167-v4 | 327 | 100% | 100% |  |  |  | x
[5 empty] | TOTAL | 327

## BS Mech
BS Suspension Mechanical Drawing Completion Status
Subsystem: | SUS
Reporter: | Janeen Romie
Date: | 2010-02-15
[7 empty] | % Complete |  | Design Maturity Level
Line # | Assembly # | Sub-Assy # | Part # | Title | BOM | No. of Dwgs | Model Status | Drawing Status | CDR | PDR | Delta- PDR | FDR | Production Revision
1 | D080536-v1 |  |  | Advanced LIGO, SUS, THIS, BS COMBINED ENVELOPE AND ASSEMBLY | T1000003-v2 | 117 | 100% | 100% |  |  |  | x
[5 empty] | TOTAL | 117

## Electronics
Suspension Electronics Drawing Completion Status
Subsystem: | SUS
Reporter: | Jay Heefner
Date: | 2010-02-12
Schematic & PCB layout
Line # | Assembly # | Sub-Assy # | Part # | Title | No. of Dwgs | Dwg % complete
1 | D0902810 |  |  | aLIGO HAM2 Suspension Controls Wiring Diagrams | 1 | 50%
2 | D1000TBD |  |  | aLIGO HAM3 and HAM4 Suspension Controls Wiring Diagrams | 1 | 0%
3 | D1000TBD |  |  | aLIGO HAM5 and HAM6 Suspension Controls Wiring Diagrams | 1 | 0%
4 | D1000TBD |  |  | aLIGO BSC-ITMX-ITMY Suspension Controls Wiring Diagrams | 1 | 0%
5 | D1000TBD |  |  | aLIGO ESD-FMX-FMY Suspension Controls Wiring Diagrams | 1 | 0%
6 | D1000TBD |  |  | aLIGO ETMX Suspension Controls Wiring Diagrams | 1 | 0%
7 | D1000TBD |  |  | aLIGO ETMY Suspension Controls Wiring Diagrams | 1 | 0%
8 | D0902783 |  |  | aLIGO Anti-Alias Chassis Top Assembly Drawing (standard chassis) | 1 | 50%
9 |  |  |  | LIGO-D0902782: aLIGO Anti-Alias Chassis Front Panel | 1 | 50%
10 |  |  |  | LIGO-D0902784: aLIGO Anti-Alias Chassis Back Panel | 1 | 50%
11 |  |  |  | LIGO-D0902790: aLIGO Anti-Alias Chassis DC In Switch Cable | 1 | 50%
12 |  |  |  | LIGO-D0902792: aLIGO Anti-Alias Chassis LED Cable Assembly | 1 | 50%
13 |  |  |  | LIGO-D070101-v1: DAC AI Interface Board | 1 | 50%
14 |  |  |  | LIGO-D070100-v1: ADC AA Interface | 1 | 50%
15 |  |  |  | LIGO-D0902785: aLIGO Anti-Alias Chassis AA Data cable (M-F)-A | 1 | 50%
16 |  |  |  | LIGO-D0902786: aLIGO Anti-Alias Chassis AA Data cable (M-F)-B | 1 | 50%
17 |  |  |  | LIGO-D0902787: aLIGO Anti-Alias Chassis AI Data cable (F-F)-A | 1 | 50%
18 |  |  |  | LIGO-D0902788: aLIGO Anti-Alias Chassis AI Data cable (F-F)-B | 1 | 50%
19 |  |  |  | LIGO-D0902789: aLIGO Anti-Alias Chassis Power Supply Cable | 1 | 50%
20 |  |  |  | LIGO-D0902793: aLIGO Anti-Alias Chassis DC In Connector | 1 | 50%
21 |  |  |  | LIGO-D0902794: aLIGO Anti-Alias Chassis DC on/off Switch | 1 | 50%
22 |  |  |  | LIGO-D070012-v2: 1U Chassis | 1 | 50%
23 |  |  |  | LIGO-D070081-v2: AdL AA and AI Filter Board | 1 | 100%
24 |  |  |  | LIGO-D060279 Chassis Power Supply Board | 1 | 100%
25 | D1000305 |  |  | aLIGO Anti-Image Chassis Top Assembly Drawing (standard18-bit chassis) | 17 | 0%
26 | D1000TBD |  |  | aLIGO Anti-Alias Chassis Top Assembly Drawing (monitor chassis) | 17 | 0%
27 |  |  | D0902747 | Circuit Diagrams for the Production Top Boards | 1 | 100%
28 |  |  | D070483 | PUM Driver Board Circuit Diagrams | 1 | 100%
29 |  |  | D0900956 | UIM Circuits | 1 | 100%
30 |  |  | D0901047 | AdL Triple Suspension Acquisition Coil Driver | 1 | 100%
31 |  |  | D0901284 | Satellite Box Circuit Diagrams | 1 | 100%
32 |  |  | D0900975 | Monitor Circuit | 1 | 100%
33 |  |  | D060278 | 8 Channel Coil Driver | 1 | 90%
34 |  |  | D080276 | AdL 4 Channel Satellite Amplifier | 1 | 90%
35 | D080180 |  |  | AdL SUS LASTI Noise Prototype Controls Wiring | 1 | 100%
36 | D060294 |  |  | LASTI AdL SUS Triple Controls Wiring | 1 | 100%
37 | D080446 |  |  | AdL RM Test Stand Wiring Diagram | 1 | 100%
38 | D080273 |  |  | AdL SUS BSC Test Stand Wiring | 1 | 100%
39 | D1000TBD |  |  | aLIGO Triple Suspension Test Stand Wiring | 1 | 0%
40 | D1000TBD |  |  | aLIGO HAM-A Test Stand Wiring | 1 | 0%
41 | D1000TBD |  |  | aLIGO Trans Mon SUS Test Stand Wiring | 1 | 0%
42 |  |  | D1000TBD | aLIGO Quad Top Vacuum Harness | 1 | 0%
43 |  |  | D1000TBD | aLIGO Quad UIM Vacuum Harness | 1 | 0%
44 |  |  | D1000TBD | aLIGO Quad PUM Vacuum Harness | 1 | 0%
45 |  |  | D1000TBD | aLIGO Triple Top Vacuum Harness | 1 | 0%
46 |  |  | D1000TBD | aLIGO Triple Middle Stage Vacuum Harness | 1 | 0%
47 |  |  | D1000TBD | aLIGO Triple Bottom Stage Vacuum Harness | 1 | 0%
48 |  |  | D1000TBD | aLIGO Quad ESD Vacuum Harness | 1 | 0%
49 |  |  | D1000TBD | aLIGO HAM-A SUS Vacuum Harness | 1 | 0%
50 |  |  | D1000TBD | aLIGO SUS BI DB37 to DB9 Cable Diagram | 1 | 0%
51 |  |  | D1000TBD | aLIGO SUS BO DB37 to DB9 Cable Diagram | 1 | 0%
52 | D1000TBD |  |  | aLIGO BI Breakout Chassis Top Level Assembly | 10 | 0%
53 | D1000TBD |  |  | aLIGO BO Breakout Chassis Top Level Assembly | 10 | 0%
54
55
56
57
58
59
60
|  |  |  | TOTAL | 103

## Monolithic -R.Jones (hidden)
Current design
|  | Author(s) | purpose | Y/N | RJ notes
2005
(LASTI) NP-TYPE GLASS MASSES
D050421 | ALIGO SUS N-PTYPE ETM QUAD PENULTIMATE MASS |  | - | Y | NP-type only
D050420 | ALIGO SUS N-PTYPE QUAD ETM REACTION TEST MASS |  | - | Y | NP-type only
2006
(LASTI) NP-TYPE PRISMS
D060099 | Advanced LIGO SUS N-Ptype Penultimate Mass Breakoff Prism | Russell Jones | Fibres | Y | For NP-type
D060166 | Advanced LIGO SUS N-Ptype Reaction Test Mass Break-off Prism | Russell Jones | Fibres | Y | For NP-type ERM only (which has flats)
(LASTI) NP-TYPE Electrostatic Drive Evaporation Mask (ERM only)
D060189 | Advanced LIGO SUS N-Ptype ETM Reaction Test Mass Electrostatic Drive Evaporation Mask | Russell Jones | Fibres | Y | For NP-type ERM only
(LASTI) NP-TYPE Bonded Penultimate Mass
D060437 | ALIGO SUS ETM N-Ptype Fully Bonded Penultimate Mass Assembly | D060437-00-K | - | - | Update for revised ear design?
D060425 | ALIGO SUS ETM N-Ptype Reaction Mass Blank | D060425-00-K | - | - | NP-type only
CO2 Machine Assemblies (Top level only, not individual parts)
D060213 | ALIGO_SUS_CO2 Laser Machine_Overall Assembly [CO2_GLA_ASM_OVERALL] | D060213-00-K | CO2 Machine | Y
D060152 | ALIGO_SUS_CO2 Laser Machine_Pull Assembly_[CO2_GLA_ASM_07] | D060152-00-D | CO2 Machine | Y
D060151 | ALIGO_SUS_CO2 Laser Machine_Galvanometer Feed Assembly_[CO2_GLA_ASM_06] | D060151-00-D | CO2 Machine | Y
D060150 | ALIGO_SUS_CO2 Laser Machine_Conical Mirror Feed Assembly_[CO2_GLA_ASM_05] | D060150-00-D | CO2 Machine | Y
D060149 | ALIGO_SUS_CO2 Laser Machine_Spinning Mirror Assembly_[CO2_GLA_ASM_04] | D060149-00-D | CO2 Machine | Y
D060148 | ALIGO_SUS_CO2 Laser Machine_Horizontal Drive Unit_[CO2_GLA_ASM_03] | D060148-00-D | CO2 Machine | Y
D060147 | ALIGO_SUS_CO2 Laser Machine_Motor/Drive Assembly_[CO2_GLA_ASM_02] | D060147-00-D | CO2 Machine | Y
D060146 | ALIGO_SUS_CO2 Laser Machine_Twin Ballscrew and Support Frame_[CO2_GLA_ASM_01] | D060146-00-D | CO2 Machine | Y
(LASTI) NP-TYPE Bonded OPTIC
D060039 | ADVANCED LIGO SUS ETM ASSEMBLY SILICA TEST MASS | D060039-00-D | - | ? | Update for revised ear design?
2007
Fibre Characterisation: Proof/Bounce Tester
D070076 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE |  | Characterization | Y
D070077 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_TESTMACHINE_TOPPLATE |  | Characterization | Y
D070078 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJARMWITHBRACKET_SUB-ASSEMBLY |  | Characterization | Y
D070079 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJUSTMENTARM |  | Characterization | Y
D070080 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJ-ARM-BRACKET |  | Characterization | Y
D070116 | ADVANCED LIGO SUS UK PROOFBOUNCE TESTERFORFIBRE_OSEM HOLDER |  | Characterization | Y
D070279 | ADVANCED LIGO SUS ETM PENULTIMATE MASS METAL WIRE STAND-OFF | Russell Jones | - | Y | For NP-type metal wire (test) hang only (Jan2009).
D070391 | ALIGO SUS ETM NP-type (Glass Mass) Ear Bonding Jig GA (General Arrangement) | Russell Jones | Ribbons | Y | For NP-type metal wire (test) hang only (Jan2009).
(LASTI) NP-TYPE ERM Prism Bonding
D070504 | ALIGO SUS ETM Reaction Mass (ERM) Bonding Template | Russell Jones | - | - | For NP-type ERM only (which has flats)
D070505 | ALIGO SUS ETM Reaction Mass (ERM) ERM Prism holder_bonding | Russell Jones | - | - | For NP-type ERM only (which has flats)
D070507 | ALIGO SUS ETM NP-type Reaction Mass (ERM) ERM Prism Bonding Jig | Russell Jones | - | - | For NP-type ERM only (which has flats)
CO2 Machine Overall Assembly ( not individual parts)
D070560 | ALIGO SUS CO2 Laser Machine_Overall Assembly_[CO2_GLA_ASM_OVERALL] | D070560 | CO2 Machine | Y | MODS REQUIRED TO UPDATE, THIS WILL MEAN ADDITIONAL PARTS?ASSEMBLIES
(NOTE: additional parts will be added in this category.)
D070555 | Fuse end | Russell Jones | Fibres | Y | Fibre production - key interface piece
D070555 | ALIGO_SUS_CO2 Laser Machine_Fork Holster_[CO2_GLA_069] | D070555 | CO2 Machine | Y | Updates required for change to fbres
D070554 | ALIGO_SUS_CO2 Laser Machine_Fuse Assembly_[CO2_GLA_ASM_011 ] | D070554 | CO2 Machine | Y
D070553 | ALIGO_SUS_CO2 Laser Machine_Base_Fuse Jig_all metal_[CO2_GLA_071 ] | D070553 | CO2 Machine | Y
D070551 | ALIGO_SUS_CO2 Laser Machine_Ribbon Fuse Jig_[CO2_GLA_ASM_10] | D070551 | CO2 Machine | Y
(NOTE: these parts are being modified for fibres)
D070525 | ALIGO SUS_CO2 Laser Machine_Laser Support Leg | D070525 | CO2 Machine | Y
Fibre Characterisation: PROFILER (Main Assemblies only)
D070524 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Lighting Assembly | D070524 | Characterization | Y
D070523 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Base Tower Assembly | D070523 | Characterization | Y
D070522 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Upper Clamping Frame Assembly | D070522 | Characterization | Y
D070521 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Camera Assembly | D070521 | Characterization | Y
D070520 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Base Assembly | D070520 | Characterization | Y
D070519 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Overall Assembly | D070519 | Characterization | Y
(LASTI) NP-TYPE CP PRISM
D070033 | ALIGO_SUS_N-Ptype_Compensator Plate_Wire Break-off Prism | D070033 | - | Y
2008
aLIGO Glass Production (UK deliverables)
D080116 | ALIGO SUS ETM QUAD End Reaction Mass (ERM) | Russell Jones | - | Y | aLIGO production
D080117 | ALIGO SUS ETM QUAD Penultimate Mass | Russell Jones | - | Y | aLIGO production
D080128 | ALIGO SUS ITM QUAD Penultimate Mass | Russell Jones | - | Y | aLIGO production
aLIGO Prism Production (UK deliverables)
D080765 | ALIGO SUS Beam Splitter (BS) Wire Break-off Prism | Russell Jones | - | Y | aLIGO production
D080750 | ALIGO SUS End Reaction Mass (ERM) Wire Break-off Prism | Russell Jones | - | Y | aLIGO production
LASTI wire test hang (Jan2009)
D080721 | ALIGO SUS ETM NP-type_Pseudo-Monolithic Test Suspension_Silica Test Mass_Wire Break-off Prism and Locator Assembly | Russell Jones | - | Y | For NP-type metal wire (test) hang only (Jan2009).
D080720 | ALIGO SUS ETM NP-type_Pseudo-Monolithic Test Suspension_Silica Test Mass_Wire Break-off Prism (for optic) | Russell Jones | - | Y | For NP-type metal wire (test) hang only (Jan2009).
Monolithic Test Equipment (weld practice)
D080687 | ALIGO SUS ETM/ITM MonolithicTest Assembly_40kg Mock Silica Mass Assembly | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080686 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert Assembly | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080685 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert Fixture | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080684 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080669 | ALIGO_SUS_ETM_Monolithic Test Assembly_40kg (Mock Silica) Mass | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
aLIGO Prism Production (UK deliverables)
D080479 | ALIGO_SUS_ETM/ITM QUAD_Penultimate Mass (PM)_Wire Break-off Prism | Russell Jones | - | Y | Production sapphire prisms
(LASTI) NP-TYPE Laser Pulling/Welding
D080412 | ALIGO_SUS_NP-type_Monolithic Assembly_Large Welding Screen Assembly | Russell Jones | - | Y | NP-type only
D080404 | ALIGO SUS NP-type_ Monolithic Assembly_(Fibre) Fuse Assembly | Russell Jones | - | Y | [RJ: Check for recent adaptations
CO2 Laser Welding equipment
D080399 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Lockdown Spacer | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080396 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Hub_Micrometer Interface Boss | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080395 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch GoalPost | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080394 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch Crossbar | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080393 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch Hanger Strut | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080392 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold Assembly | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080390 | ALIGO SUS NP-type_ETM_Monolithic Stage_Welding Hub_3-hole Plate | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080389 | ALIGO SUS NP-type_ETM_Monolithic Stage_Welding Hub_Bearing holder | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080380 | ALIGO SUS CO2 Laser Machine_Welding_Galvo Box_Bearing Pad | Russell Jones | - | Y
D080379 | ALIGO SUS CO2 Laser Machine_Welding_Galvo Box_Shelf interface stalk | Russell Jones | - | Y
D080362 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Base | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080361 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Cross Bar | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080360 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Leg | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080359 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080048 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Articulated Arm Connector | Russell Jones | - | Y | Laser welding equipment
D080047 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_sunroof | Russell Jones | - | Y | Laser welding equipment
D080046 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Side wall | Russell Jones | - | Y | Laser welding equipment
D080045 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Base-plate | Russell Jones | - | Y | Laser welding equipment
D080044 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Galvo Holder | Russell Jones | - | Y | Laser welding equipment
D080041 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Mounting Bracket | Russell Jones | - | Y | Laser welding equipment
D080040 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box (Birdhouse) Assembly | Russell Jones | - | Y | Laser welding equipment
D080036 | ALIGO SUS NP-type_ETM_Monolithic Assembly_Welding Shelf |  | - | Y | Laser welding equipment
PROOF/BOUNCE TESTER PARTS
2009
aLIGO Ear Production (UK deliverables)
D080751 | Advanced LIGO, Suspension, ETM Test Mass, Test Ear Redesign | Marielle van Veggel | Fibres | N
D090007 | Advanced LIGO, Suspension, ETM Test Mass,Test Ear Redesign with Recess | Marielle van Veggel | F | Y | UK glass production ears
D090xxx | Advanced LIGO, Suspension, ETM Test Mass, FIBRE PROFILE |  | F | Y | DCC number to be ordered for the baseline fibre shape.
CO2 Laser Welding equipment
D0900172 | Hub-side weld mirror support | Liam Cunningham | - | ?
D0900173 | Mass-side weld mirror support | Liam Cunningham | - | ?
D0900194 | ALIGO_SUS_ETM_Monolithic Testing_Bonding Jig_Revised Disc Insert | Russell Jones | Fibres | Y | NP-type: used for bonding of D080751 to
D0900373 | ALIGO SUS ETM/ITM Monolithic Assembly_Advanced Welding Hub | Giles Hammond, Russell Jones, Marielle van Veggel | Fibres | Y
D0900950 | ALIGO SUS ETM/ITM monolithic assembly - Welding mirror left side | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres | Y
D0900951 | ALIGO SUS ETM/ITM monolithic assembly - welding mirror right side | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres | Y
D0900957 | ALIGO SUS ETM/ITM monolithic assembly - spring clamp for weld mirror on weld hub | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres | Y
D0901302 | Mass jack assembly | Liam Cunningham | - | Y
D0901303 | Mass jack lower support plate | Liam Cunningham | - | Y
D0901304 | Mass jack upper support plate | Liam Cunningham | - | Y
D0901305 | Mass jack guide angle Liam Cunningham Suspensions | Liam Cunningham | - | Y
D0901306 | Mass jack optic support pad | Liam Cunningham | - | Y
D0901307 | Mass jack support channel | Liam Cunningham | - | Y
D0901308 | Mass jack linear bearing shaft | Liam Cunningham | - | Y
D0901309 | Mass jack linear bearing housing block | Liam Cunningham | - | Y
D0901310 | Mass jack clamp | Liam Cunningham | - | Y
D0901591 | BASEPLATE - NP-type bonding jig | Marielle van Veggel | - | Y
D0901592 | ASSEMBLY DRAWING - NP-type bonding jig | Marielle van Veggel | - | Y
Fibre Guard
D0902504 | Fibre Guard Assembly Installation | Marielle van Veggel | - | Y
D0902505 | Fibre Guard Assembly all parts | Marielle van Veggel | - | Y
D0902506 | Fibre guard assembly | Marielle van Veggel | - | Y
D0902507 | Fibre guard Main Body | Marielle van Veggel | - | Y
D0902508 | Fibre guard Separator | Marielle van Veggel | - | Y
D0902509 | Fibre guard angle section 1 | Marielle van Veggel | - | Y
D0902510 | Fibre guard angle section 2 | Marielle van Veggel | - | Y
D0902511 | Fibre guard angle section 3 | Marielle van Veggel | - | Y
D0902512 | Fibre guard angle section 4 | Marielle van Veggel | - | Y
D0902513 | Fibre guard angle section 5 | Marielle van Veggel | - | Y
D0902514 | Fibre guard angle section 6 | Marielle van Veggel | - | Y
D0902515 | Fibre guard angle section 7 | Marielle van Veggel | - | Y
D0902516 | Fibre guard angle section 8 | Marielle van Veggel | - | Y
D0902517 | Fibre guard angle section 9 | Marielle van Veggel | - | Y
D0902518 | Fibre guard angle section 10 | Marielle van Veggel | - | Y
D0902519 | Fibre guard angle section 11 | Marielle van Veggel | - | Y
D0902780 | Mass jack optic support block | Liam Cunningham | - | Y
D0902798 | Arm offset piece | Liam Cunningham | - | Y
D0902799 | Arm offset piece side 2 | Liam Cunningham | - | Y
2010
CO2 Laser Welding equipment - CUTTER AND BOW
D1000358 | Slider Block Lower Side 1 |  | - | Y
D1000357 | Fibre cutting jig assembly drawing |  | - | Y
D1000363 | fibre bow spacer |  | - | Y
D1000362 | fibre bow shield plate |  | - | Y
D1000361 | fibre cutter clamping plate |  | - | Y
D1000360 | fibre cutter slider upper |  | - | Y
D1000359 | Slider Block Lower Side 2 |  | - | Y
|  |  | - | Y
(NOTE: additional parts will be added in this category.)
Fibre Storage |  |  | -
D1000019 | Fibre storage rack - fibre support peg |  | - | Y
D1000018 | Fibre storage rack - horizontal tie bar |  | - | Y
D1000017 | Fibre storage rack - inner cross rib |  | - | Y
D1000016 | Fibre storage rack - inner rib |  | - | Y
D1000015 | Fibre storage rack - long side rib |  | - | Y
D1000014 | Fibre storage rack - Cross rib |  | - | Y
D1000013 | Fibre storage rack - fibre support crossbar |  | - | Y
D1000012 | Fibre storage rack - horizontal rail side 2 |  | - | Y
D1000011 | Fibre storage rack - horizontal rail side 1 |  | - | Y
D1000010 | Fibre storage rack - vertical support |  | - | Y
D1000009 | Fibre storage rack - baseplate |  | - | Y
D1000008 | Fibre storage rack |  | - | Y
(NOTE: additional parts will be added in this category.) |  |  | - | Y

## Monolithic-All - R.Jones (hidden)
|  |  |  | Current design | RJ notes
|  | Author(s) | purpose | Y/N
2005
D050421 | SUS N-PTYPE ETM QUAD PENULTIMATE MASS |  | - | Y | NP-type only
D050420 | ALIGO SUS N-PTYPE QUAD ETM REACTION TEST MASS |  | - | Y | NP-type only
2006
D060055 | ADVANCED LIGO_SUS_N-Ptype_Refined Ear (Type A) | Russell Jones | Ribbons | N | Ribbons no longer baseline
D060056 | ADVANCED LIGO_SUS_N-Ptype_Refined Ear (Type B) | Russell Jones | Ribbons | N | Ribbons no longer baseline
D060099 | Advanced LIGO SUS N-Ptype Penultimate Mass Breakoff Prism | Russell Jones | Fibres | Y | For NP-type
D060166 | Advanced LIGO SUS N-Ptype Reaction Test Mass Break-off Prism | Russell Jones | Fibres | Y | For NP-type ERM only (which has flats)
D060189 | Advanced LIGO SUS N-Ptype ETM Reaction Test Mass Electrostatic Drive Evaporation Mask | Russell Jones | Fibres | Y | For NP-type ERM only
D060543 | ALIGO SUS N-Ptype ETM Monolithic Testing_Mock Bonded Flat_Weld Test Horn Fixture | D060543-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060542 | ALIGO SUS N-Ptype ETM Monolithic Testing_Mock Bonded Flat_Disc Holder | D060542-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060541 | ALIGO SUS N-Ptype ETM Monolithic Testing_Weld Test Horn_Restrictor | D060541-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060540 | ALIGO SUS N-Ptype ETM_Monolithic Testing_Weld Test Horn Holder | D060540-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060437 | ALIGO SUS ETM N-Ptype Fully Bonded Penultimate Mass Assembly | D060437-00-K | - | - | NP-type only
D060425 | ALIGO SUS ETM N-Ptype Reaction Mass Blank | D060425-00-K | - | - | NP-type only
D060286 | ALIGO SUS N-Ptype Monolithic Testing_Disc Insert | D060286-00-K | Ribbons
D060213 | ALIGO_SUS_CO2 Laser Machine_Overall Assembly [CO2_GLA_ASM_OVERALL] | D060213-00-K | CO2 Machine | Y
D060152 | ALIGO_SUS_CO2 Laser Machine_Pull Assembly_[CO2_GLA_ASM_07] | D060152-00-D | CO2 Machine | Y
D060151 | ALIGO_SUS_CO2 Laser Machine_Galvanometer Feed Assembly_[CO2_GLA_ASM_06] | D060151-00-D | CO2 Machine | Y
D060150 | ALIGO_SUS_CO2 Laser Machine_Conical Mirror Feed Assembly_[CO2_GLA_ASM_05] | D060150-00-D | CO2 Machine | Y
D060149 | ALIGO_SUS_CO2 Laser Machine_Spinning Mirror Assembly_[CO2_GLA_ASM_04] | D060149-00-D | CO2 Machine | Y
D060148 | ALIGO_SUS_CO2 Laser Machine_Horizontal Drive Unit_[CO2_GLA_ASM_03] | D060148-00-D | CO2 Machine | Y
D060147 | ALIGO_SUS_CO2 Laser Machine_Motor/Drive Assembly_[CO2_GLA_ASM_02] | D060147-00-D | CO2 Machine | Y
D060146 | ALIGO_SUS_CO2 Laser Machine_Twin Ballscrew and Support Frame_[CO2_GLA_ASM_01] | D060146-00-D | CO2 Machine | Y
D060049 | ALIGO_SUS_N-Ptype_Ribbon_Fabrication_Slide(5x0.5mm) | D060049-00-K | Ribbons | N
D060039 | ADVANCED LIGO SUS ETM ASSEMBLY SILICA TEST MASS | D060039-00-D | Ribbons | ? | Update for revised ear design?
D060026 | ALIGO_SUS_N-Ptype_Ribbon_Fabrication_Slide(1.5x3x75) | D060026-00-K | Ribbons | N
D060023 | ALIGO SUS N-Ptype Bond Strength Test Disk_SA_1.7cm^2 | D060023-00-K | Ribbons | N
D060022 | ALIGO SUS N-Ptype GLASS Ribbon Fabrication Piece (1.5 x 5) | D060022-00-D | Ribbons | N
D060021 | ALIGO SUS N-Ptype GLASS Ribbon Fabrication Piece (1.5x3) | D060021-00-D | Ribbons | N
D060019 | Advanced LIGO SUS N-Ptype Weld Test Horn | D060019-00-D | Ribbons | N
D060018 | Advanced LIGO SUS N-Ptype Test Mass Refined Test Ear | D060018-00-D | Ribbons | N
2007
D070076 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE |  | Characterization | Y
D070077 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_TESTMACHINE_TOPPLATE |  | Characterization | Y
D070078 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJARMWITHBRACKET_SUB-ASSEMBLY |  | Characterization | Y
D070079 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJUSTMENTARM |  | Characterization | Y
D070080 | ALIGO_SUS_UK_PROOFBOUNCETESTERFORFIBRE_ADJ-ARM-BRACKET |  | Characterization | Y
D070116 | ADVANCED LIGO SUS UK PROOFBOUNCE TESTERFORFIBRE_OSEM HOLDER |  | Characterization | Y
D070279 | ADVANCED LIGO SUS ETM PENULTIMATE MASS METAL WIRE STAND-OFF | Russell Jones | -
D070391 | ALIGO SUS ETM NP-type (Glass Mass) Ear Bonding Jig GA (General Arrangement) | Russell Jones | Ribbons | N
D070504 | ALIGO SUS ETM Reaction Mass (ERM) Bonding Template | Russell Jones | - | - | For NP-type ERM only (which has flats)
D070505 | ALIGO SUS ETM Reaction Mass (ERM) ERM Prism holder_bonding | Russell Jones | - | - | For NP-type ERM only (which has flats)
D070507 | ALIGO SUS ETM NP-type Reaction Mass (ERM) ERM Prism Bonding Jig | Russell Jones | - | - | For NP-type ERM only (which has flats)
D070555 | Fuse end | Russell Jones | Fibres | Y
D070560 | ALIGO SUS CO2 Laser Machine_Overall Assembly_[CO2_GLA_ASM_OVERALL] | D070560 | CO2 Machine | Y
D070555 | ALIGO_SUS_CO2 Laser Machine_Fork Holster_[CO2_GLA_069] | D070555 | CO2 Machine | Y
D070554 | ALIGO_SUS_CO2 Laser Machine_Fuse Assembly_[CO2_GLA_ASM_011 ] | D070554 | CO2 Machine | Y
D070553 | ALIGO_SUS_CO2 Laser Machine_Base_Fuse Jig_all metal_[CO2_GLA_071 ] | D070553 | Ribbons | Y
D070551 | ALIGO_SUS_CO2 Laser Machine_Ribbon Fuse Jig_[CO2_GLA_ASM_10] | D070551 | Ribbons | Y
D070550 | ALIGO_SUS_CO2 Laser Machine_Ribbon Pull Assembly_[CO2_GLA_ASM_08] | D070550 | Ribbons | Y
D070525 | ALIGO SUS_CO2 Laser Machine_Laser Support Leg | D070525 | CO2 Machine | Y
D070524 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Lighting Assembly | D070524 | Profiler | Y
D070523 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Base Tower Assembly | D070523 | Profiler | Y
D070522 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Upper Clamping Frame Assembly | D070522 | Profiler | Y
D070521 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Camera Assembly | D070521 | Profiler | Y
D070520 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Base Assembly | D070520 | Profiler | Y
D070519 | ALIGO SUS Monolithic Assembly Ribbon/Fibre Profiler Overall Assembly | D070519 | Profiler | Y
D070517 | ALIGO SUS NP-type ETM Monolithic Stage_Welding Hub Assembly | D070517 | Ribbons | N
D070516 | ALIGO SUS NP-type ETM Monolithic Stage_Axle_Ta Reflector_welding | D070516 | Ribbons | N
D070515 | ALIGO SUS NP-type ETM Monolithic Stage Ta Reflector_welding | D070515 | Ribbons | N
D070514 | ALIGO SUS NP-type ETM Monolithic Stage Welding Hub | D070514 | Ribbons | N
D070506 | ALIGO SUS NP-type ETM Penultimate Mass Prism Holder | D070506 | test equipment | N
D070453 | ALIGO SUS NP-type Monolithic Testing_Weld Hub_test horn set-up | D070453 | test equipment | N
D070280 | ALIGO SUS NP-type _PRISM HOLDER_groove cutting tests | D070280 | test equipment | N
D070033 | ALIGO_SUS_N-Ptype_Compensator Plate_Wire Break-off Prism | D070033 | - | Y
2008
D080076 | N-Ptype break-off_holder | Liam Cunningham | - | N | for holding prisms during laser ablation
D080077 | N-Ptype Reaction mass Wire Break Off | Liam Cunningham | - | N | development concept, not tested or used
D080078 | N-Ptype Penultimate mass Wire Break Off | Liam Cunningham | - | N | development concept, not tested or used
D080116 | ALIGO SUS ETM QUAD End Reaction Mass (ERM) | Russell Jones | - | Y | aLIGO production
D080116 | End Reaction Mass (ERM) | Russell Jones | - | Y | aLIGO production
D080117 | ALIGO SUS ETM QUAD Penultimate Mass | Russell Jones | - | Y | aLIGO production
D080128 | ALIGO SUS ITM QUAD Penultimate Mass | Russell Jones | - | Y | aLIGO production
D080701 | Advanced LIGO, SUS, Monolithic Assembly, Confirmation of Tooling Holes | Russell Jones | - | N
D080765 | ALIGO SUS Beam Splitter (BS) Wire Break-off Prism | Russell Jones | - | Y | aLIGO production
D080750 | ALIGO SUS End Reaction Mass (ERM) Wire Break-off Prism | Russell Jones | - | Y | aLIGO production
D080721 | ALIGO SUS ETM NP-type_Pseudo-Monolithic Test Suspension_Silica Test Mass_Wire Break-off Prism and Locator Assembly | Russell Jones | - | Y | NP-type only: In use for wire test hang at LASTI
D080720 | ALIGO SUS ETM NP-type_Pseudo-Monolithic Test Suspension_Silica Test Mass_Wire Break-off Prism (for optic) | Russell Jones | - | Y | NP-type only: In use for wire test hang at LASTI
D080687 | ALIGO SUS ETM/ITM MonolithicTest Assembly_40kg Mock Silica Mass Assembly | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080686 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert Assembly | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080685 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert Fixture | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080684 | ALIGO SUS ETM/ITM MonolithicTest Assembly_Revised Disc Insert | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080669 | ALIGO_SUS_ETM_Monolithic Test Assembly_40kg (Mock Silica) Mass | Russell Jones | test equipment | Y | In use at LASTI, pre monolithic
D080557 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Alumina Press | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080556 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Guide Pin (Welding Press) | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080555 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Compact Welding Press | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080484 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Small TopPlate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080483 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Lrg TopPlate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080482 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Screw Plate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080481 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Pusher Base | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080480 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly | Russell Jones/Liam Cunningham | Ribbons | N
D080479 | ALIGO_SUS_ETM/ITM QUAD_Penultimate Mass (PM)_Wire Break-off Prism | Russell Jones | - | Y | Production sapphire prisms
D080413 | ALIGO SUS NP-type Monolithic Assembly_Small (Shelf mounted) Welding Screen | Russell Jones | Ribbons | N | Obsolete: shelf mounted guard for welding
D080412 | ALAIG_SUS_NP-type_Monolithic Assembly_Large Welding Screen Assembly | Russell Jones | - | Y | NP-type only
D080404 | ALIGO SUS NP-type_ Monolithic Assembly_(Fibre) Fuse Assembly | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080399 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Lockdown Spacer | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080396 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Hub_Micrometer Interface Boss | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080395 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch GoalPost | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080394 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch Crossbar | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080393 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold_Bosch Hanger Strut | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080392 | ALIGO SUS NP-type ETM_Monolithic Stage_Welding Scaffold Assembly | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080390 | ALIGO SUS NP-type_ETM_Monolithic Stage_Welding Hub_3-hole Plate | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080389 | ALIGO SUS NP-type_ETM_Monolithic Stage_Welding Hub_Bearing holder | Russell Jones | - | Y | [RJ: Check for recent adaptations
D080388 | ALIGO SUS NP-type_Fibre Storage Assembly_Storage Rack_Bosch Horizontal | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080387 | ALIGO SUS NP-type_Fibre Storage Assembly_Storage Rack_Bosch Upright | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080386 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Bosch Parking Space | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080385 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Rack Locator | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080384 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Table Leg | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080383 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Table Top | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080382 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080381 | ALIGO SUS NP-type_Fibre Storage Assembly | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080380 | ALIGO SUS CO2 Laser Machine_Welding_Galvo Box_Bearing Pad | Russell Jones | - | Y
D080379 | ALIGO SUS CO2 Laser Machine_Welding_Galvo Box_Shelf interface stalk | Russell Jones | - | Y
D080362 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Base | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080361 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Cross Bar | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080360 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Leg | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080359 | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly | Russell Jones | - | Y | NP-type only: check still part of welding procedure
D080334 | ALIGO SUS NP-type Fibre Storage_Storage Rack | Russell Jones | Ribbons | N | Obsolete
D080333 | ALIGO SUS NP-type Fibre Storage_Storage Cartridge Assembly | Russell Jones | Ribbons | N | Obsolete
D080332 | ALIGO SUS NP-type Fibre Storage_Storage cartridge_ledge | Russell Jones | Ribbons | N | Obsolete
D080331 | ALIGO SUS NP-type Fibre Storage_Storage cartridge_Transportation Extrusion | Russell Jones | Ribbons | N | Obsolete
D080330 | ALIGO SUS NP-type Fibre Storage_Storage rack_Fibre Dock | Russell Jones | Ribbons | N | Obsolete
D080279 | IGR_MKII Strength Testing Machine_Drive/Pull Module_Coupling_Motor to UJ | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080220 | IGR_MKII Strength Testing Machine_Worm Wheel Drive Assembly_Worm Scarf Plate | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080219 | IGR_MKII Strength Testing Machine_Worm Assembly (WH2-1) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080218 | IGR_MKII Strength Testing Machine_Adjustable Achoring Assembly_Gusset | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080217 | IGR_MKII Strength Testing Machine_Extending Support_Collet | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080216 | IGR_MKII Strength Testing Machine_Adjustable Anchoring Assembly_Adjustable Top Plate | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080215 | IGR_MKII Strength Testing Machine_Extended Support Bearing Pole | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080214 | IGR_MKII Strength Testing Machine_Aluminium Spine (extrusion) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080213 | IGR_MKII Strength Testing Machine_Pivot Test Assembly_Pivot Clamp Plate | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080212 | IGR_MKII Strength Testing Machine_Pivot Test Assembly_Pivoting Bar | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080211 | IGR_MKII Strength Testing Machine_Load Cell Pull Assembly_Spacer (Pull) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080210 | IGR_MKII Strength Testing Machine_Load Cell Pull Assembly_(Load Cell) Force Plate | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080209 | IGR_MKII Strength Testing Machine_Load Cell Pull Assembly_Pull Bar | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080208 | IGR_MKII Strength Testing Machine_Worm Wheel Drive Assembly_Worm Shaft | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080207 | IGR_MKII Strength Testing Machine_Worm Wheel Drive Assembly_Worm Wheel Housing | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080206 | IGR_MKII Strength Testing Machine_Drive/Pull Module_bearing pole (load cell balance) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080205 | IGR_MKII Strength Testing Machine_Drive/Pull Module_short extrusion (drive module) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080204 | IGR_MKII Strength Testing Machine_Drive/Pull Module_Endplate (drive module) | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080203 | IGR_MKII Strength Testing Machine_Drive/Pull Module_Base Plate_drive mount | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080202 | IGR_MKII Strength Testing Machine_Adjustable Anchoring Assembly | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080201 | IGR_MKII Strength Testing Machine_Pivot Test Assembly | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080200 | IGR_MKII Strength Testing Machine_Worm Wheel Drive Assembly | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080199 | IGR_MKII Strength Testing Machine_Load Cell Pull Assembly | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080198 | IGR_MKII Strength Testing Machine_Drive/Pull Module | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080197 | IGR_MKII Strength Testing Machine_Overall Assembly | Russell Jones | test equipment GLA | - | Used for destructive testing of welds in development phase
D080191 | ALIGO SUS ETM NP-type_Monolithic Assembly_Weld Testing_Single Weld Horn Holder Assembly | Russell Jones | Ribbons | N
D080190 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Linear Bearing Interface Pulling Assembly | Russell Jones | Ribbons | N
D080189 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Linear Bearing Housing | Russell Jones | Ribbons | N
D080188 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Interface Pulling Plate | Russell Jones | Ribbons | N
D080187 | ALIGO SUS ETM NP-type_Molonilthic Assembly_Weld Testing_Single weld test saddle | Russell Jones | Ribbons | N
D080186 | ALIGO SUS ETM NP-type_Monolithic Assembly_40kg Dummy Mass_Weld Test Horn Holder Assembly (mock flat) | Russell Jones | Ribbons | N
D080162 | ALIGO SUS ETM NP-type_Monolithic Assembly_40kg Aluminium Dummy Mass_Disc Insert Fixture_Fully Bonded (mock flat) | Russell Jones | Ribbons | N
D080131 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Test Horn clamp plate | Russell Jones | Ribbons | N
D080130 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Double horn holder | Russell Jones | Ribbons | N
D080129 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Double Weld Test Assembly | Russell Jones | Ribbons | N
D080049 | ALIGO SUS NP-type_ETM_Monolithic Assembly_Spine (welding hub) | Russell Jones | Ribbons | N
D080048 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Articulated Arm Connector | Russell Jones | - | Y | Laser welding equipment
D080047 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_sunroof | Russell Jones | - | Y | Laser welding equipment
D080046 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Side wall | Russell Jones | - | Y | Laser welding equipment
D080045 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Base-plate | Russell Jones | - | Y | Laser welding equipment
D080044 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Galvo Holder | Russell Jones | - | Y | Laser welding equipment
D080041 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box_Mounting Bracket | Russell Jones | - | Y | Laser welding equipment
D080040 | ALIGO SUS_CO2 Laser Machine_Welding_Galvo Box (Birdhouse) Assembly | Russell Jones | - | Y | Laser welding equipment
D080036 | ALIGO SUS NP-type_ETM_Monolithic Assembly_Welding Shelf |  | - | Y | Laser welding equipment
2009
D080751 | Advanced LIGO, Suspension, ETM Test Mass, Test Ear Redesign | Marielle van Veggel | Fibres | N
D090007 | Advanced LIGO, Suspension, ETM Test Mass,Test Ear Redesign with Recess | Marielle van Veggel | F | Y | UK glass production ears
D0900108 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_3x3mm-bar-holder | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900109 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_25mm-stock-holder | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900110 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-part1 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900111 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-part2 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900112 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-assembly | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900113 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-part1 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900114 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-part2 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900115 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-assembly | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900171 | Weld test L-support | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900172 | Hub-side weld mirror support | Liam Cunningham | - | ?
D0900173 | Mass-side weld mirror support | Liam Cunningham | - | ?
D0900194 | ALIGO_SUS_ETM_Monolithic Testing_Bonding Jig_Revised Disc Insert | Russell Jones | Fibres | Y | NP-type: used for bonding of D080751 to
D0900373 | ALIGO SUS ETM/ITM Monolithic Assembly_Advanced Welding Hub | Giles Hammond, Russell Jones, Marielle van Veggel | Fibres
D0900950 | ALIGO SUS ETM/ITM monolithic assembly - Welding mirror left side | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres
D0900951 | ALIGO SUS ETM/ITM monolithic assembly - welding mirror right side | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres
D0900957 | ALIGO SUS ETM/ITM monolithic assembly - spring clamp for weld mirror on weld hub | Alan Cumming, Russell Jones, Giles Hammond, Marielle van Veggel | Fibres
D0901302 | Mass jack assembly | Liam Cunningham | -
D0901303 | Mass jack lower support plate | Liam Cunningham | -
D0901304 | Mass jack upper support plate | Liam Cunningham | -
D0901305 | Mass jack guide angle Liam Cunningham Suspensions | Liam Cunningham | -
D0901306 | Mass jack optic support pad | Liam Cunningham | -
D0901307 | Mass jack support channel | Liam Cunningham | -
D0901308 | Mass jack linear bearing shaft | Liam Cunningham | -
D0901309 | Mass jack linear bearing housing block | Liam Cunningham | -
D0901310 | Mass jack clamp | Liam Cunningham
D0901591 | BASEPLATE - NP-type bonding jig | Marielle van Veggel
D0901592 | ASSEMBLY DRAWING - NP-type bonding jig | Marielle van Veggel
D0902504 | Fibre Guard Assembly Installation | Marielle van Veggel
D0902505 | Fibre Guard Assembly all parts | Marielle van Veggel
D0902506 | Fibre guard assembly | Marielle van Veggel
D0902507 | Fibre guard Main Body | Marielle van Veggel
D0902508 | Fibre guard Separator | Marielle van Veggel
D0902509 | Fibre guard angle section 1 | Marielle van Veggel
D0902510 | Fibre guard angle section 2 | Marielle van Veggel
D0902511 | Fibre guard angle section 3 | Marielle van Veggel
D0902512 | Fibre guard angle section 4 | Marielle van Veggel
D0902513 | Fibre guard angle section 5 | Marielle van Veggel
D0902514 | Fibre guard angle section 6 | Marielle van Veggel
D0902515 | Fibre guard angle section 7 | Marielle van Veggel
D0902516 | Fibre guard angle section 8 | Marielle van Veggel
D0902517 | Fibre guard angle section 9 | Marielle van Veggel
D0902518 | Fibre guard angle section 10 | Marielle van Veggel
D0902519 | Fibre guard angle section 11 | Marielle van Veggel
D0902780 | Mass jack optic support block | Liam Cunningham
D0902798 | Arm offset piece | Liam Cunningham
D0902799 | Arm offset piece side 2 | Liam Cunningham
2010
D1000358 | Slider Block Lower Side 1
D1000357 | Fibre cutting jig assembly drawing
D1000363 | fibre bow spacer
D1000362 | fibre bow shield plate
D1000361 | fibre cutter clamping plate
D1000360 | fibre cutter slider upper
D1000359 | Slider Block Lower Side 2
D1000019 | Fibre storage rack - fibre support peg
D1000018 | Fibre storage rack - horizontal tie bar
D1000017 | Fibre storage rack - inner cross rib
D1000016 | Fibre storage rack - inner rib
D1000015 | Fibre storage rack - long side rib
D1000014 | Fibre storage rack - Cross rib
D1000013 | Fibre storage rack - fibre support crossbar
D1000012 | Fibre storage rack - horizontal rail side 2
D1000011 | Fibre storage rack - horizontal rail side 1
D1000010 | Fibre storage rack - vertical support
D1000009 | Fibre storage rack - baseplate
D1000008 | Fibre storage rack

## Obsolete - R. Jones (hidden)
|  |  |  | Current design | RJ notes
|  | Author(s) | purpose | Y/N
2005
2006
D060055 | ADVANCED LIGO_SUS_N-Ptype_Refined Ear (Type A) | Russell Jones | Ribbons | N | OBSOLETE: Ribbons no longer baseline
D060056 | ADVANCED LIGO_SUS_N-Ptype_Refined Ear (Type B) | Russell Jones | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D060543 | ALIGO SUS N-Ptype ETM Monolithic Testing_Mock Bonded Flat_Weld Test Horn Fixture | D060543-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060542 | ALIGO SUS N-Ptype ETM Monolithic Testing_Mock Bonded Flat_Disc Holder | D060542-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060541 | ALIGO SUS N-Ptype ETM Monolithic Testing_Weld Test Horn_Restrictor | D060541-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060540 | ALIGO SUS N-Ptype ETM_Monolithic Testing_Weld Test Horn Holder | D060540-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060286 | ALIGO SUS N-Ptype Monolithic Testing_Disc Insert | D060286-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060049 | ALIGO_SUS_N-Ptype_Ribbon_Fabrication_Slide(5x0.5mm) | D060049-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060026 | ALIGO_SUS_N-Ptype_Ribbon_Fabrication_Slide(1.5x3x75) | D060026-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060023 | ALIGO SUS N-Ptype Bond Strength Test Disk_SA_1.7cm^2 | D060023-00-K | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060022 | ALIGO SUS N-Ptype GLASS Ribbon Fabrication Piece (1.5 x 5) | D060022-00-D | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060021 | ALIGO SUS N-Ptype GLASS Ribbon Fabrication Piece (1.5x3) | D060021-00-D | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060019 | Advanced LIGO SUS N-Ptype Weld Test Horn | D060019-00-D | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D060018 | Advanced LIGO SUS N-Ptype Test Mass Refined Test Ear | D060018-00-D | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
2007
D070279 | ADVANCED LIGO SUS ETM PENULTIMATE MASS METAL WIRE STAND-OFF | Russell Jones | - |  | Obsolete: back up design, not reqiuired
D070391 | ALIGO SUS ETM NP-type (Glass Mass) Ear Bonding Jig GA (General Arrangement) | Russell Jones | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070517 | ALIGO SUS NP-type ETM Monolithic Stage_Welding Hub Assembly | D070517 | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070516 | ALIGO SUS NP-type ETM Monolithic Stage_Axle_Ta Reflector_welding | D070516 | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070515 | ALIGO SUS NP-type ETM Monolithic Stage Ta Reflector_welding | D070515 | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070514 | ALIGO SUS NP-type ETM Monolithic Stage Welding Hub | D070514 | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070506 | ALIGO SUS NP-type ETM Penultimate Mass Prism Holder | D070506 | Ribbons | N | OBSOLETE:Ribbons no longer baseline
D070453 | ALIGO SUS NP-type Monolithic Testing_Weld Hub_test horn set-up | D070453 | Ribbons | N | OBSOLETE: Test equipment for fabrication/welding of ribbons
D070280 | ALIGO SUS NP-type _PRISM HOLDER_groove cutting tests | D070280 | test equipment | N | Obsolete: manufacturing test sample, not reqiuired
2008
D080076 | N-Ptype break-off_holder | Liam Cunningham | - | N | Part for holding prisms during laser ablation for NP-type prisms
D080077 | N-Ptype Reaction mass Wire Break Off | Liam Cunningham | - | N | development concept, not tested or used
D080078 | N-Ptype Penultimate mass Wire Break Off | Liam Cunningham | - | N | development concept, not tested or used
D080701 | Advanced LIGO, SUS, Monolithic Assembly, Confirmation of Tooling Holes | Russell Jones | - | N | Historical reference prior to change from ribbons to fibres
D080557 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Alumina Press | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080556 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Guide Pin (Welding Press) | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080555 | ALIGO SUS NP-type_ETM Monolithic Stage_Welding Hub Assembly_Compact Welding Press | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080484 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Small TopPlate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080483 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Lrg TopPlate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080482 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Screw Plate | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080481 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly_Pusher Base | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080480 | ALIGO SUS NP-type ETM Monolithic Assembly_Welding_Alumina Pusher Assembly | Russell Jones/Liam Cunningham | Ribbons | N | for obsolete NP-type ears - (ribbons)
D080388 | ALIGO SUS NP-type_Fibre Storage Assembly_Storage Rack_Bosch Horizontal | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080387 | ALIGO SUS NP-type_Fibre Storage Assembly_Storage Rack_Bosch Upright | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080386 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Bosch Parking Space | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080385 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Rack Locator | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080384 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Table Leg | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080383 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station_Table Top | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080382 | ALIGO SUS NP-type_Fibre Storage Assembly_Docking Station | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080381 | ALIGO SUS NP-type_Fibre Storage Assembly | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080334 | ALIGO SUS NP-type Fibre Storage_Storage Rack | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080333 | ALIGO SUS NP-type Fibre Storage_Storage Cartridge Assembly | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080332 | ALIGO SUS NP-type Fibre Storage_Storage cartridge_ledge | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080331 | ALIGO SUS NP-type Fibre Storage_Storage cartridge_Transportation Extrusion | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080330 | ALIGO SUS NP-type Fibre Storage_Storage rack_Fibre Dock | Russell Jones | Ribbons | N | Obsolete: tested at LASTI, ruled out for future assembly work
D080191 | ALIGO SUS ETM NP-type_Monolithic Assembly_Weld Testing_Single Weld Horn Holder Assembly | Russell Jones | test equipment | N | Obsolete: manufacturing test sample, not reqiuired
D080190 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Linear Bearing Interface Pulling Assembly | Russell Jones | test equipment | N | Reworks to A. Heptonstall's strength tester, which was sent to LASTI from Glasgow when Alastair began employment with LIGO.
D080189 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Linear Bearing Housing | Russell Jones | test equipment | N | Reworks to A. Heptonstall's strength tester, which was sent to LASTI from Glasgow when Alastair began employment with LIGO.
D080188 | IGR_Ribbon/Fibre Breaking Strength Machine 1_Upgrade components_Interface Pulling Plate | Russell Jones | test equipment | N | Reworks to A. Heptonstall's strength tester, which was sent to LASTI from Glasgow when Alastair began employment with LIGO.
D080187 | ALIGO SUS ETM NP-type_Molonilthic Assembly_Weld Testing_Single weld test saddle | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080186 | ALIGO SUS ETM NP-type_Monolithic Assembly_40kg Dummy Mass_Weld Test Horn Holder Assembly (mock flat) | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080162 | ALIGO SUS ETM NP-type_Monolithic Assembly_40kg Aluminium Dummy Mass_Disc Insert Fixture_Fully Bonded (mock flat) | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080131 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Test Horn clamp plate | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080130 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Double horn holder | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080129 | ALIGO SUS NP-type_Monolithic Assembly_Welding Tests_Double Weld Test Assembly | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
D080049 | ALIGO SUS NP-type_ETM_Monolithic Assembly_Spine (welding hub) | Russell Jones | Ribbons | N | OBSOLETE:Test pieces, ribbons no longer baseline
2009
D0900108 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_3x3mm-bar-holder | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900109 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_25mm-stock-holder | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900110 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-part1 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900111 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-part2 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900112 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_10mm-stock-holder-assembly | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900113 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-part1 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900114 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-part2 | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900115 | AdLIGO_SUS_ETM_NP-type_Monolithic-Assembly_weld-test-holders_square-ear-holder-assembly | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
D0900171 | Weld test L-support | Liam Cunningham | - | N | Used for destructive testing of welds in development phase
2010

## Glass & Welding Tooling
| 1=complete, 0=work to do |  |  |  | Last altered: 01/10/10, R.JONES
For drawing count | [5 empty] | ENGINEERING DRAWINGS
Number | status | comment | who | status | Assembly / Part Name | Assembly Number | Part Number | DCC | PDM works? | NOTES
MONOLITHIC ASSEMBLIES / EARS / PRISMS
1 | 1 | complete | Russell |  | ALIGO_SUS_ETM_NP-type_Monolithoc Assembly | D1000758 |  | Y (edrwg, v1)
2 | 1 | complete |  |  | N-Ptype Fully Bonded Penulitmate Mass Assembly | D060437 | - | Y (v2) | Y
3 | 1 | complete |  |  | NP-type Penultimate Mass | - | D050421 | Y (v1) | Y | Bonding described by T1000114-v1
4 | 1 | complete |  |  | aLIGO_SUS_ETM_ITM_QUAD_PM_ Production Ear_with recess | - | D090007 | Y (v2) | Y
- |  | - |  |  | NP-type Penultimate Mass Break off Prism | - | D060099 | Y (v1) | Y | Shim added as spacer as per T1000114-v1
5 | 1 | - | Russell |  | NP-type Monolithic Assembly_(mock) Penultimate wire loop (no source file) | - | D1001028 | edrawing + SW part | Y
6 | 1 | complete |  |  | NP-type Monolithic Assembly_Silica Fibre | - | D1001024 | Y (v2) | Y
- |  | -
7 | 1 | complete | Russell |  | (LASTI) ETM_Silica_Test_Mass Assembly | D060039 | - | Y (v3) | Y
8 | 1 | complete |  |  | NP-type Optic (US responsibility) | - | D040431 | (US responsibility) | Y | Bonding described by T1000114-v1
9 | 1 | complete |  |  | aLIGO_SUS_ETM_ITM_QUAD_Production Ear | - | D080751 | Y (v2) | Y
- |  | -
10 | 1 | complete | Russell |  | ALIGO_SUS_ETM_Production_Monolthic Assembly | D1000759 | - | Y | Y
11 | 1 | complete |  |  | ADVANCED LIGO ETM PM WITH PRISMS AND EARS ASSEMBLY | D0902823 | - | Y | Y
12 | 1 | complete |  |  | ETM Penultimate Mass | - | D080117 | Y | Y
- |  | - |  |  | aLIGO_SUS_ETM_ITM_QUAD_PM_ Production Ear_with recess | - | D090007 | Y | Y
13 | 1 | complete |  |  | ALIGO_SUS_ETM/ITM QUAD_Penultimate Mass (PM)_Wire Break-off Prism | - | D080479 | Y | Y
- |  | - | Russell |  | NP-type Monolithic Assembly_(mock) Penultimate wire loop | - | D1001028 | edrawing + SW part | Y
- |  | - | Russell |  | NP-type Monolithic Assembly_Silica Fibre | - | D1001024 | Y | Y
- |  | -
14 | 1 | complete | Russell |  | ADVANCED LIGO ETM OPTIC WITH EARS ASSEMBLY | D0902455 | - | Y | Y
- |  | - |  |  | ETM Optic (US responsibility) | - | - | (US responsibility) | Y | -
- |  | - |  |  | aLIGO_SUS_ETM_ITM_QUAD_Production Ear | - | D080751 | Y | Y
- |  | -
15 | 1 | complete | Russell |  | ALIGO_SUS_ITM_Production_Monolthic Assembly | D1000760 | - | Y | Y
16 | 1 | complete |  |  | ADVANCED LIGO ITM PM WITH PRISMS AND EARS ASSEMBLY | D1001035 | - | Y | Y
17 | 1 | complete |  |  | ITM Penultimate Mass | - | D080128 | Y | Y
- |  | - |  |  | aLIGO_SUS_ETM_ITM_QUAD_PM_ Production Ear_with recess | - | D090007 | Y | Y
- |  | - |  |  | ALIGO_SUS_ETM/ITM QUAD_Penultimate Mass (PM)_Wire Break-off Prism | - | D080479 | Y | Y
- |  | - |  |  | NP-type Monolithic Assembly_(mock) Penultimate wire loop | - | D1001028 | N | Y
- |  | - |  |  | NP-type Monolithic Assembly_Silica Fibre | - | D1001024 | Y | Y
-
18 | 1 | complete | Russell |  | ADVANCED LIGO ITM OPTIC WITH EARS ASSEMBLY | D0902456 | - | (US responsibility) | Y
- |  | - |  |  | ITM Optic (US responsibility) | - | D080657 | (US responsibility) | Y
- |  | - |  |  | aLIGO_SUS_ETM_ITM_QUAD_Production Ear | - | D080751 | Y | Y
- |  | -
- |  | -
19 | 1 | - |  |  | 3. Bonding Jigs | D1000129 | - | N | N
20 | 1 | complete | Marielle |  | Ear bonding jig Assembly (aLIGO ETM/ITM PMs and optics) | D0901592 | - | Y (v2) | -
21 | 1 | complete |  |  | BASEPLATE - NP-type bonding jig | - | D0901591 | Y (v2) | -
22 | 1 | complete |  |  | aLIGO ETM/ITM ear bonding jig - T-piece | - | D1001633 | Y (v2) | -
23 | 1 | complete |  |  | Penultimate mass prism holder | - | D1000128 | Y (v3) | -
- |  | -
24 | 1 | complete | RJ/MVV |  | aLIGO BS/FM PRISM BONDING JIG | D1002147 | - | Y (v1) | -
25 | 1 | complete |  |  | aLIGO BS/FM PRISM BONDING FIXTURE | - | D1002148 | Y (v1)
26 | 1 | complete |  |  | aLIGO BS/FM PRISM BONDING BASEPLATE | - | D1002149 | Y (v1)
27 | 1 | complete |  |  | aLIGO BS/FM PRISM BONDING SUPPORT CYLINDER | - | D1002151 | Y (v2)
28 | 1 | complete |  |  | aLIGO BS/FM PRISM HOLDER ASSEMBLY | - | D1002152 | Y (v1)
29 | 1 | complete |  |  | aLIGO BS/FM PRISM HOLDER | - | D1002153 | Y (v1)
-
30 | 1 | complete | RJ/MVV |  | aLIGO ERM PRISM BONDING JIG | D1002201 | - | Y (v2) | -
31 | 1 | complete |  |  | aLIGO ERM PRISM BONDING FIXTURE | - | D1002202 | Y (v2)
32 | 1 | complete |  |  | aLIGO ERM PRISM BONDING BASEPLATE | - | D1002203 | Y (v2)
33 | 1 | complete |  |  | aLIGO ERM PRISM BONDING SUPPORT CYLINDER | - | D1002288 | Y (v1)
-
34 | 1 | complete | RJ/MVV |  | aLIGO TCP PRISM BONDING JIG | D1002140 | - | Y (v2) | -
35 | 1 | complete |  |  | aLIGO TCP PRISM BONDING FIXTURE | - | D1002141 | Y (v2)
36 | 1 | complete |  |  | aLIGO TCP PRISM BONDING BASEPLATE | - | D1002142 | Y (v2)
37 | 1 | complete |  |  | aLIGO TCP/ERM PRISM BONDING ALIGNMENT GUIDE | - | D1002143 | Y (v1)
38 | 1 | complete |  |  | aLIGO TCP PRISM BONDING SUPPORT CYLINDER | - | D1002144 | Y (v1)
39 | 1 | complete |  |  | aLIGO TCP/ERM PRISM HOLDER ASSEMBLY | D1002145 | - | Y (v1)
40 | 1 | complete |  |  | aLIGO TCP/ERM PRISM HOLDER | - | D1002146 | Y (v1)
41 | 1 | complete |  |  | aLIGO TCP/ERM PRISM HOLDER ALIGNMENT SCREW | - | D1002289 | Y (v1)
42 | 1 | complete |  |  | aLIGO TCP/ERM PRISM HOLDER ALIGNMENT BUSH | - | D1002290 | Y (v1)
43 | 1 | complete |  |  | aLIGO TCP/ERM PRISM HOLDER FIXING SCREW | - | D1002291 | Y (v1)
- |  | -
- |  | - |  |  | B. FIBRE TOOLING AND STORAGE (for NP-type) |  |  | DCC | Vault | NOTES
44 | 1 | complete | Russell |  | 1. Fuse Jig Assembly | D070551 |  | Y (v2) | v1
45 | 1 | complete | Russell |  | ALIGO_SUS_CO2 Laser Machine_Fuse Assembly_[CO2_GLA_ASM_011 ] | D080404 |  | Y (v1) | - | REPLACED BY D1001532
46 | 1 | complete | Russell |  | Fuse end | - | D080017 | Y (v1) | - | -
47 | 1 | complete | Russell |  | ALIGO_SUS_CO2 Laser Machine_Base_Fuse Jig_all metal_[CO2_GLA_071 ] | - | D070553 | Y (v2) | - | REPLACED BY D1001532
48 | 1 | complete | Liam |  | fuse end attachment jig | - | D1001532 | Y (v2) | -
- |  | -
49 | 1 | complete | Russell |  | 2. Fibre pulling clamps /cartridge | D1001504 | - | Y (v1) | -
50 | 1 | complete |  |  | Pulling Machine Clamp (CO2_GLA_070) | - | CO2_GLA_070 | Y (attached to cartridge DCC no.) |  | Maintaining IGR number as is part of CO2 Machine.
51 | 1 | complete |  |  | Clamp linkage_Lbracket | - | D1001609 | Y (v1) | -
- |  | -
52 | 1 | complete | Liam |  | 3. Fibre storage
53 | 1 | complete |  |  | FIBRE STORAGE RACK ASSEMBLY (MIT) | D1000008 |  | Y (v3) | -
54 | 1 | complete |  |  | fibre_storage_baseplate_MIT | - | D1000009 | Y (v2) | -
55 | 1 | complete |  |  | vertical_support_MIT | - | D1000010 | Y (v3) | -
56 | 1 | complete |  |  | horizontal_rail_MIT | - | D1000011 | Y (v2) | -
57 | 1 | complete |  |  | horizontal_rail_side2_MIT | - | D1000012 | Y (v2) | -
58 | 1 | complete |  |  | fibre_support_crossbar_MIT | - | D1000013 | Y (v2) | -
59 | 1 | complete |  |  | cross_rib_MIT | - | D1000014 | Y (v2) | -
60 | 1 | complete |  |  | long_side_rib_MIT | - | D1000015 | Y (v2) | -
61 | 1 | complete |  |  | inner_rib_MIT | - | D1000016 | Y (v2) | -
62 | 1 | complete |  |  | inner_cross_rib_MIT | - | D1000017 | Y (v2) | -
63 | 1 | complete |  |  | horizontal_tie-bar_MIT | - | D1000018 | Y (v2) | -
64 | 1 | complete |  |  | support_peg_MIT | - | D1000019 | Y (v3) | -
- |  | -
- |  | - |  |  | C: WELDING EQUIPMENT & FIBRE GUARD |  |  | DCC | PDMworks | NOTES
- |  | -
- |  | - | Liam |  | 1. Fibre Cutter
65 | 1 | complete |  |  | Fibre cutting jig assembly drawing | D1000357 |  | Y (v1) | N
66 | 1 | complete |  |  | Slider Block Lower Side 1 | - | D1000358 | Y (v1) | -
67 | 1 | complete |  |  | fibre bow spacer | - | D1000363 | Y (v1) | -
68 | 1 | complete |  |  | fibre bow shield plate | - | D1000362 | Y (v1) | -
69 | 1 | complete |  |  | fibre cutter clamping plate | - | D1000361 | Y (v1) | -
70 | 1 | complete |  |  | fibre cutter slider upper | - | D1000360 | Y (v1) | -
71 | 1 | complete |  |  | Slider Block Lower Side 2 | - | D1000359 | Y (v1) | -
72 | 1 | complete |  |  | Fuse end locator | - | D1001957 | Y (v1) | -
- |  | -
- |  | - | Liam |  | 2. BOW
73 | 1 | complete |  |  | Fibre bow assembly | D1001767 | - | Y (v1) | -
74 | 1 | complete |  |  | Fibre bow spine | - | D1001787 | Y (v1) | -
75 | 1 | complete |  |  | Fibre bow shield plate | - | D1000362 | Y (v1) | -
76 | 1 | complete |  |  | Fibre bow spacer | - | D1000363 | Y (v1) | -
77 | 1 | complete |  |  | Fibre bow tweezers | - | D1001786 | Y (v1) | -
78 | 1 | complete |  |  | Fibre bow linear stage assembly | D1001784 | - | Y (v1) | -
79 | 1 | complete |  |  | Fibre bow linear stage interface | - | D1002212 | Y (v1) | -
- |  | - |  |  | Newport-M-MT-X | - | - | - | -
- |  | - |  |  | Newport-M-MT-XY | - | - | - | -
- |  | - |  |  | Newport-MT-AB2 | - | - | - | -
- |  | -
- |  | -
- |  | - | Joe |  | 3. Lower Structure Assembly Tooling (LSAT) | D060305 | - | Y | Liam | Liam sent to Calum, (MAY 2010)
- |  | -
- |  | - | Russell |  | 4. Welding Shelf and Brackets and Screens | - | - | -
80 | 1 | complete |  |  | Welding Shelf | - | D080036 | Y (v4=03) | Y
81 | 1 | complete |  |  | MBS 80x80 brackets (slots required?) | - | - | - | Y | MBS ITEM, Part Number: 0.0.411.23
- |  | -
- |  | -
- |  | - | Liam |  | 5. Welding Scaffold / Weld Hub & Weld Mirrors
82 | 1 | complete |  |  | Welding Scaffold Assembly | D080392 | - | Y (v3) | -
83 | 1 | complete |  |  | Bearing holder | - | D080389 | Y (v4) | -
84 | 1 | complete |  |  | 3-hole plate | - | D080390 | Y (v4) | -
85 | 1 | complete |  |  | C-section side piece | - | D080393 | Y (v4) | -
86 | 1 | complete |  |  | Crossbar | - | D080394 | Y (v4) | -
87 | 1 | complete |  |  | Welding Hub | - | D0900373 | Y (v2) | -
88 | 1 | complete |  |  | Micrometer interface boss | - | D080396 | Y (v4)
89 | 1 | complete |  |  | Arm offset piece side 1 | - | D0902798 | Y (v2)
90 | 1 | complete |  |  | Arm offset piece side 2 | - | D0902799 | Y (v2)
91 | 1 | complete |  |  | weld scaffold guide rod | - | D1001823 | Y (v1)
92 | 1 | complete |  |  | Weld mirrror assembly | - | D1001748 | Y (v1)
93 | 1 | complete |  |  | Weld mirrror assembly opposite side | - | D1001749 | Y (v1)
94 | 1 | complete |  |  | ALIGO SUS ETM/ITM monolithic assembly - Welding mirror left side | - | D0900950 | Y (v2)
95 | 1 | complete |  |  | ALIGO SUS ETM/ITM monolithic assembly - welding mirror right side | - | D0900951 | Y (v2)
96 | 1 | complete |  |  | ALIGO SUS ETM/ITM monolithic assembly - spring clamp for weld mirror on weld hub | - | D0900957 | Y (v1)
97 | 1 | complete |  |  | ALIGO SUS ETM/ITM monolithic assembly - spring clamp for weld mirror on weld hub opposite side | - | D1001746 | Y (v2)
98 | 1 | complete |  |  | Weld mirror handle | - | D1001747 | Y (v1) | -
99 | 1 | complete |  |  | Welding baffle holder | - | D1001822 | Y (v1) | -
100 | 1 | complete |  |  | Straight welding baffle | - | D1001821 | Y (v1) | -
101 | 1 | complete |  |  | Curved welding baffle | - | D1001820 | Y (v1) | -
-
-
- |  |  | Russell |  | 6. ARTICULATED ARM / BIRDCAGE (update required for extended covers)
102 | 1 | complete |  |  | CO2 Laser Machine_Welding_Galvo Box (Birdhouse) Assembly | D080040 |  | Y (V3) | Y
103 | 1 | complete |  |  | Galvo Box_Mounting Bracket | - | D080041 | Y (v2) | Y
104 | 1 | complete |  |  | Galvo Box_Holder | - | D080044 | Y (v1) | Y
105 | 1 | complete |  |  | Galvo Box_base plate | - | D080045 | Y (v1) | Y
106 | 1 | complete |  |  | Galvo Box_side wall | - | D080046 | Y (v2) | Y
107 | 1 | complete |  |  | Galvo Box_sunroof | - | D080047 | Y (v2) | Y
108 | 1 | complete |  |  | Galvo Box_Arm Connector | - | D080048 | Y (v2) | Y
|  | complete |  |  | Galvo box_Side wall 2 | - | D1001803 | Y (v1) | -
- |  | - |  |  | Galvo Box_Shelf Interface Stalk | - | check | Y | Y | not required
- |  | - |  |  | Galvo Box_Bearing Pad | - | check | Y | Y | not required
- |  | -
- |  | - |  |  | 7. Welding Table (or turntable) CHECK USAGE IN ASSEMBLY PROCESS. |  |  |  |  | Superceded by a second set of Joe's design (D1000020)
- |  | - | obsolete |  | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly | D080359 | - | Y (v1) | Y | Superceded by a second set of Joe's design (D1000020)
- |  | - | obsolete |  | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Base | - | D080362 | Y (v1) | Y | Superceded by a second set of Joe's design (D1000020)
- |  | - | obsolete |  | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Cross Bar | - | D080361 | Y (v1) | Y | Superceded by a second set of Joe's design (D1000020)
- |  | - | obsolete |  | ALIGO_SUS_NP-type_Monolithic Assembly_Turntable Pallet Assembly_Pallet Leg | - | D080360 | Y (v1) | Y | Superceded by a second set of Joe's design (D1000020)
- |  | -
- |  | - | Liam |  | 8. Jack for optic
109 | 1 | complete |  |  | Mass Jack Assembly (for Optic) | D0901302 |  | Y (v3) | -
110 | 1 | complete |  |  | Mass jack lower support plate | - | D0901303 | Y (v2) | -
111 | 1 | complete |  |  | Mass jack upper support plate | - | D0901304 | Y (v2) | -
112 | 1 | complete |  |  | Mass jack guide angle | - | D0901305 | Y (v1) | -
113 | 1 | complete |  |  | Mass jack optic support pad | - | D0901306 | Y (v1) | -
114 | 1 | complete |  |  | Mass jack support channel | - | D0901307 | Y (v1) | -
115 | 1 | complete |  |  | Mass jack linear bearing shaft | - | D0901308 | Y (v1) | -
116 | 1 | complete |  |  | Mass jack linear bearing housing block | - | D0901309 | Y (v1) | -
117 | 1 | complete |  |  | Mass jack clamp | - | D0901310 | obsolete so no drawing on line
[5 empty] | Mass jack optic support block |  | D0902780 | Y(v3)
- |  | -
- |  | - | Liam |  | 8. Extraction
118 | 1 | complete |  |  | Weld extract assembly | D1001933 |  | Y (v1) | -
119 | 1 | complete |  |  | Extract assembly L-section | - | D1002213 | Y (v1) | -
120 | 1 | complete |  |  | Extract assembly cylindrical spacer | - | D1002214 | Y (v1) | -
121 | 1 | complete |  |  | Extract assembly extract pipe | - | D1002220 | Y (v1) | -
- |  | -
- |  | - |  |  | 9. Fibre Guard |  |  | Y | Y
122 | 1 | complete | Liam |  | Fibre_Guard_Assembly_Installation | D0902505 |  | Y (v3) | Y
123 | 1 | complete |  |  | Fibre_Guard_Assembly | - | D0902506 | Y (v3) | Y
124 | 1 | complete |  |  | Fibre_Guard_Main_Body | - | D0902507 | Y (v3) | Y
125 | 1 | complete |  |  | Fibre_Guard_Separator | - | D0902508 | Y (v3) | Y
126 | 1 | complete |  |  | Angle_Section_1 | - | D0902509 | Y (v3) | Y
127 | 1 | complete |  |  | Angle_Section_2 | - | D0902510 | Y (v3) | Y
128 | 1 | complete |  |  | Angle_Section_3 | - | D0902511 | Y (v3) | Y
129 | 1 | complete |  |  | Angle_Section_4 | - | D0902512 | Y (v3) | Y
130 | 1 | complete |  |  | Angle_Section_5 | - | D0902513 | Y (v3) | Y
131 | 1 | complete |  |  | Angle_Section_6 | - | D0902514 | Y (v3) | Y
132 | 1 | complete |  |  | Angle_Section_7 | - | D0902515 | Y (v3) | Y
133 | 1 | complete |  |  | Angle_Section_8 | - | D0902516 | Y (v3) | Y
134 | 1 | complete |  |  | Angle_Section_9 | - | D0902517 | Y (v3) | Y
135 | 1 | complete |  |  | Angle_Section_10 | - | D0902518 | Y (v3) | Y
136 | 1 | complete |  |  | Angle_Section_11 | - | D0902519 | Y (v3) | Y
- |  | -
- |  | -
- |  | - | Liam |  | 10. Fibre removal tooling |  |  |  |  | Update
137 | 1 | complete |  |  | Fibre removal tooling | D1001688 |  | Y (v1) | N
138 | 1 | complete |  |  | Fibre removal t-mount | - | D1001689 | Y (v1) | N
139 | 1 | complete |  |  | Fibre removal blade | - | D1001690 | Y (v1) | N
140 | 1 | complete |  |  | Fibre removal spine | - | D1001691 | Y (v1) | N
141 | 1 | complete |  |  | Fibre removal crossbar | - | D1001692 | Y (v1) | N
142 | 1 | complete |  |  | Fibre removal crossbar rod | - | D1001693 | Y (v1) | N
subtotal | 142
1

## CO2 Machine & Characterizing
| 1=complete, 0=work to do |  |  |  | ENGINEERING DRAWINGS
For drawing count
Number | complete | comment |  | Assembly / Part Name | Assembly Number | Part Number | ON DCC? | PDM works?
|  |  | RUSSELL | A. CO2 LASER PULLING MACHINE
143 | 1 | complete |  | ALIGO_SUS_CO2 Laser Machine_Overall Assembly [CO2_GLA_ASM_OVERALL] | D070560 | - | Y | N | Assembly files only on DCC, the many sub-components remain with IGR numbering.
144 | 1 | complete |  | Twin Ballscrew and Support Frame_[CO2_GLA_ASM_01] | D060146 | - | Y | Y | "
145 | 1 | complete | obsolete | Horizontal Drive Unit_[CO2_GLA_ASM_03] | D060148 | - | Y | Y | "
146 | 1 | complete |  | Motor/Drive Assembly_[CO2_GLA_ASM_02] | D060147 | - | Y | Y | "
147 | 1 | complete |  | Spinning Mirror Assembly_[CO2_GLA_ASM_04] | D060149 | - | Y | Y | "
148 | 1 | complete |  | Conical Mirror Feed Assembly_[CO2_GLA_ASM_05] | D060150 | - | Y | Y | "
149 | 1 | complete | obsolete | Galvanometer Feed Assembly_[CO2_GLA_ASM_06] | D060151 | - | Y | Y | "
150 | 1 | complete |  | Pull Assembly_[CO2_GLA_ASM_07] | D060152 | - | Y | Y | "
151 | 1 | complete | obsolete | Ribbon Pull Assembly [CO2_GLA_ASM_08] | D070550 | - | Y | Y | "
152 | 1 | complete |  | Clamp Interface Assembly [CO2_GLA_ASM_13] | D1000575 | - | Y | Y | "
153 | 1 | complete |  | aLIGO Fibre Cartridge Assembly | D1001504 |  | Y | N
B: PROFILER (all at \\Gigalum\Shared\ALUK\CO2 LASER PULLING MACHINE PROJECT_MASTER\CAD\PROFILER\PROFILER_SolidWorks)
154 | 1 | complete | RUSSELL | Ribbon/Fibre Profiler Overall Assembly | D070519 | - | Y (v1) | N | all files transferred to: \\Gigalum\Shared\ALUK\CO2 LASER PULLING MACHINE PROJECT_MASTER\CAD\PROFILER
155 | 1 | complete |  | Ribbon/Fibre Profiler Base Assembly | D070520 | - | Y (v1) | N | Assembly files only on DCC, components remain with IGR numbering.
156 | 1 | complete |  | Ribbon/Fibre Profiler Camera Assembly | D070521 | - | Y (v1) | N | Assembly files only on DCC, components remain with IGR numbering.
157 | 1 | complete |  | Ribbon/Fibre Profiler Upper Clamping Frame Assembly | D070522 | - | Y (v1) | N | Assembly files only on DCC, components remain with IGR numbering.
158 | 1 | complete |  | Ribbon/Fibre Profiler Base Tower Assembly | D070523 | - | Y (v1) | N | Assembly files only on DCC, components remain with IGR numbering.
159 | 1 | complete |  | Ribbon/Fibre Profiler Lighting Assembly | D070524 | - | Y (v1) | N | Assembly files only on DCC, components remain with IGR numbering.
|  |  | Liam | C: PROOF / BOUNCE TESTER
160 | 1 | complete |  | PROOF TESTER | D1002082 |  | Y | -
161 | 1 | complete |  | BOUNCE TESTER | D1002083 | - | Y | -
162 | 1 | complete |  | BOUNCE PROOF TESTER ENCLOSURE | D1002067 |  | Y | -
163 | 1 | complete |  | BOUNCE PROOF TESTER DOOR | D1002069 |  | Y | -
164 | 1 | complete |  | BOUNCE PROOFTESTER BASEPLATE | - | D1002105 | Y | -
165 | 1 | complete |  | BOUNCE PROOF TESTER TOPPLATE | - | D070077 | Y | -
166 | 1 | complete |  | BOUNCE PROOF TESTER SIDE PANEL | - | D1002155 | Y | -
167 | 1 | complete |  | BOUNCE PROOF TESTER BACK PANEL | - | D1002156 | Y | -
168 | 1 | complete |  | BOUNCE PROOF TESTER DOOR PANEL | - | D1002154 | Y | -
169 | 1 | complete |  | BOUNCE PROOF TESTER 15KG PROOF MASS | - | D1002071 | Y | -
170 | 1 | complete |  | BOUNCE PROOF TESTER 1KG MASS | - | D1002076 | Y | -
171 | 1 | complete |  | BOUNCE PROOF TESTER ADUSTMENT ARM | - | D070079 | Y | -
172 | 1 | complete |  | BOUNCE PROOF TESTER ADUSTMENT ARM BRACKET | - | D070080 | Y | -
173 | 1 | complete |  | BOUNCE PROOFTSTER JOINT FOR CLEVIS PIN | - | D070075 | Y | -
174 | 1 | complete | RUSSELL | D: IGR MKII Strength Testing Machine | D080197 | - | v2 | N | *****Described by T1000345 *****
175 | 1 | complete |  | Drive/Pull Module (Assembly) | D080198 | - | v1 | -
176 | 1 | complete |  | Baseplate_drive mount | - | D080203 | v1 | -
177 | 1 | complete |  | End plate (drive module) | - | D080204 | v1 | -
178 | 1 | complete |  | Short extrusion | - | D080205 | v1 | -
179 | 1 | complete |  | Bearing pole (load cell balance) | - | D080206 | v1 | -
180 | 1 | complete |  | Worm Wheel Drive Assembly | D080200 | - | v1 | -
181 | 1 | complete |  | Worm Wheel Housing | - | D080207 | v1 | -
182 | 1 | complete |  | Worm scarf plate | - | D080220 | v1 | -
183 | 1 | complete |  | Antibacklash Worm Wheel (ABM 2-40) | - | D1002157 | v1 | -
184 | 1 | complete |  | Universal Joint Remachine (U5-434 652) | - | D1002158 | v1 | -
185 | 1 | complete |  | Worm assembly (WH2-1) | D080219 | - | v1 edrwg | -
186 | 1 | complete |  | Worm shaft | - | D080208 | v1 | -
187 | 1 | complete |  | Worm Cap Assembly | D1002012 | - | v1 edrwg | -
188 | 1 | stl file on DCC |  | worm cap inner | - | D1002013 | v1 edrwg + stl file | -
189 | 1 | stl file on DCC |  | worm cap outer | - | D1002014 | v1 edrwg + stl file | -
190 | 1 | complete |  | Gearbox Protector | D1002009 | - | v1 edrwg | -
191 | 1 | stl file on DCC |  | cowling ring_inner | - | D1002010 | v1 edrwg + stl file | -
192 | 1 | stl file on DCC |  | cowling ring_outer | - | D1002011 | v1 edrwg + stl file | -
193 | 1 | complete |  | Load Cell Pull Assembly | D080199 | - | v1 | -
194 | 1 | complete |  | Pull bar | - | D080209 | v1 | -
195 | 1 | complete |  | Force Plate | - | D080210 | v1 | -
196 | 1 | complete |  | Spacer (pull) | - | D080211 | v1 | -
197 | 1 | complete |  | Adjustable Anchoring Assembly | D080202 | - | v1 + v1 edrwg | -
198 | 1 | complete |  | Gusset | - | D080218 | v1 | -
199 | 1 | complete |  | Adjustable Top Plate | - | D080216 | v4 | -
200 | 1 | complete |  | Bearing Pad | - | D1002160 | v1 | -
201 | 1 | edwg only |  | Pivot Test Assembly | D080201 | - | v1 edrwg only | - | Conceptual stage, not tested, no assembly drawing created.
202 | 1 | complete |  | Pivoting bar | - | D080212 | v1 | -
203 | 1 | complete |  | Pivot clamp plate |  | D080213 | v1 | -
204 | 1 | complete |  | Central Pull Assembly | D1001999 | - | v1 | -
205 | 1 | complete |  | Interface Pulling Plate | - | D1002000 | v2 | -
206 | 1 | complete |  | Central Pulling Hub | - | D1002001 | v1 | -
207 | 1 | complete |  | Bearing Housing | - | D1002002 | v2 | -
208 | 1 | complete |  | Linear Bearing Pulling Interface Assembly | D1002348 |  | v1 | - | Adapted from D080190_Linear Bearing Pulling Interface Assembly, in D1001879_IGR Strength Testing Machine Design (2002
209 | 1 | complete |  | Adapted linear bearing housing | - | D1002349 | v1 | -
210 | 1 | complete |  | Interface Pulling Plate | - | D080188 | v1 | - | Unchanged from D080190_Linear Bearing Pulling Interface Assembly, in D1001879_IGR Strength Testing Machine Design (2002
211 | 1 | complete |  | Table Assembly | D1002003 | - | v1 + edrwg | -
212 | 1 | complete |  | Leg | - | D1002004 | v1 + edrwg | -
213 | 1 | complete |  | Sole | - | D1002005 | v1 | -
214 | 1 | edwg only |  | Long Support | - | D1002006 | v1 edrwg | -
215 | 1 | edwg only |  | Short support | - | D1002007 | v1 edrwg | -
216 | 1 | complete |  | Black plastic tablecloth |  | D1002008 | v1 edrwg ,dxf | -
217 | 1 | complete |  | Table top |  | D1002159 | v1 | -
218 | 1 | complete |  | Phonebooth Assembly | D1002015 | - | v2 | - | Basic enclosure: as built in Glasgow.
219 | 1 | drawing not needed |  | Vertical strut | - | D1002016 | N | - | constructed from TARSCA aluminium speed frame (RS Stock No. 519-071) (L=1950mm)
220 | 1 | drawing not needed |  | Horizontal strut | - | D1002017 | N | - | constructed from TARSCAaluminium speed frame (RS Stock No. 519-071) (L=700mm)
221 | 1 | drawing not needed |  | Normal strut | - | D1002018 | N | - | constructed from TARSCA aluminium speed frame (RS Stock No. 519-071) (L=450mm)
222 | 1 | edwg only |  | Lexan side panel | - | D1002019 | v1 edrwg | - | 2m x 0.5m, t=4mm
223 | 1 | edwg only |  | Lexan top plate | - | D1002020 | v1 edrwg | - | 0.75m x 0.5m, t=4mm
224 | 1 | edwg only |  | Lexan front plate | - | D1002021 | v1 edrwg | - | 2m x 0.75m, t=4mm
- | - | - | [5 empty] | -
225 | 1 | complete |  | Aluminium Spine | - | D080214 | v1 | -
226 | 1 | complete |  | Extended Support Bearing pole | - | D080215 | v1 edrwg | - | Defined by the stock length of the specified component
227 | 1 | complete |  | Extending support Collet | - | D080217 | v1 edrwg | -
228 | 1 | complete |  | Triangulat end cap | - | D1002162 | v1 | -
229 | 1 | complete | RUSSELL | E: IGR Strength Testing Machine (2002) | D1001879 | - | edrawing | Y | part drawings on the PDM works vault
230 | 1 | complete | RUSSELL | F: Dummy 40kg Aluminium Mass Assemblies (+ disc inserts) | D080687 |  | v2 | -
231 | 1 | complete |  | Revised Disc Insert Assembly | D080686 |  | v2 | -
232 | 1 | complete |  | Revised Disc Insert Fixture | - | D080685 | v1 | -
233 | 1 | complete |  | Revised Disc Insert | - | D080684 | v1 | -
234 | 1 | complete |  | Bonding Jig_Revised Disc Insert | - | D0900194 | v1 | -
92
(DCC) |  | Overall Progress: | 100%