## Summary
GS-13 |  | Vertical | Horizontal | Total
Total completed | HAM | 44 | 43 | 87
| BSC | 43 | 44 | 87 | L1 need | H1 need | M1 need | I1 need
Needed | HAM | 48 | 48 | 96 | 30 | 30 | 6 | 30
| BSC | 45 | 45 | 90 | 30 | 30 | 0 | 30
Needed w/o India | HAM | 33 | 33 | 66
| BSC | 30 | 30 | 60
% Complete | HAM | 91.6667 | 89.5833 | 90.625
| BSC | 95.5556 | 97.7778 | 96.6667
% Complete w/o India | HAM | 133.3333 | 130.303 | 131.8182
| BSC | 143.3333 | 146.6667 | 145

## Details
| Count | 98 | 94 | 94 | 90 | 43 | 88 | 85 | 2 |  |  | 50 |  |  | Count | 99 | 97 | 97 | 97 | 44 | 89 | 83 | 11 |  |  | 69
E1000058-v46 | % of received | 100 | 95.9 | 95.9 | 91.8 | 43 | 89.8 | 94.4 |  |  |  | 51 |  |  | % of received |  | 98 | 98 | 98 | 42 | 89.9 | 85.6 |  |  |  | 69.7
2014-01-16 | Number of ISIs | 32.7 | 31.3 | 31.3 | 30 |  | 29.3 | 28.3 | 0.7 | [5 empty] | Number of ISIs | 33 | 32.3 | 32.3 | 32.3 |  | 29.7 | 27.7 | 3.7
D1000166 | Failure rate (%) |  | 5.1 |  | 7.2 | [11 empty] | 2 |  | 1
Verticals | Location | Received | AR QA | Modified | PM QA | Type | Ch S/N | Leak Checked | Used | Rework |  | Loctite | Issue | Horizontals | Location | Received | AR QA | Modified | PM QA | Type | Ch S/N | Leak Checked | Used | HAM Rework |  | Nylon Screws | Issue
676 | LLO | yes | pass | yes | pass | HAM | 41 | pass | India_2 | New | Yes | Yes |  | 775 | LLO | yes | pass | yes | pass | HAM | 85 | pass | India_1 | New | Yes | Yes
677 | LHO | yes | pass | yes | pass | BSC | 26 | pass | LHO_BSC8 | waived | Yes |  |  | 776 | LLO | yes | pass | yes | pass | HAM | 73 | pass | LLO_2 | waived | Yes | No
678 | MIT |  | no data | [10 empty] | 777 | LHO | yes | pass | yes | pass | BSC | 502 | pass | LHO | waived | yes | Yes
679 | LLO | yes | no data | yes | pass | HAM | 2 | pass | LLO_3 | waived | Yes |  |  | 778 | LHO | yes | pass | yes | pass | BSC | 95 |  | LHO_BSC6 |  | No!
680 | LLO | yes | no data | yes | pass | HAM | 32 | pass | LLO_2 | waived | Yes | No |  | 779 | LHO | yes | pass | yes | pass | HAM | 55 | pass |  | Reworked | Yes | Yes
681 | LLO | yes | pass | yes | pass | HAM | 64 | pass | LLO_4 | waived | Yes |  |  | 780 | High Bay Lab | yes | pass | yes | pass | HAM | 34 | pass |  | Reworked | No!
682 | LASTI | yes | pass | yes | pass | HAM | 6 | pass | LASTI | waived | Yes |  |  | 781 | LHO | yes | pass | yes | pass | BSC | 19 | pass | LHO | waived | Yes | Yes
683 | LLO | yes | pass | yes | pass | HAM | 60 | pass | LLO_3 | waived | Yes |  |  | 782 | LHO | yes | pass | yes | pass | HAM | 44 | pass | LHO_2 | Reworked | No!
684 | LLO | yes | pass | yes | pass | HAM | 8 | pass | LLO_5 | waived | Yes | No |  | 783 | LHO | yes | pass | yes | pass | BSC | 16 |  | LHO_BSC8 | waived | Yes
685 | LHO | yes | pass | yes | pass | HAM | 11 | pass | LHO_HAM2 | Reworked | Yes |  |  | 784 | LLO | yes | pass | yes | pass | HAM | 97 | pass | India_2 | New | Yes | Yes
686 | High Bay Lab | yes | pass | yes | pass | BSC | 29 |  |  |  | Yes | Yes |  | 785 | LASTI | yes | no data | yes | pass | HAM | 57 | pass | LASTI | waived | Yes | Yes | in SP???
687 | LHO | yes | pass | yes | pass | HAM | 74 | pass | LHO | Reworked | Yes | No |  | 786 | Lab | yes | pass | yes | pass | [6 empty] | Yes
688 | SPSR | yes | pass | yes | pass | [5 empty] | Yes | No | 1/2 signal | 787 | LLO | yes | pass | yes | pass | HAM | 39 | pass | LLO_2 | Reworked | Yes | No
689 | LLO | yes | pass | yes | pass | BSC | 88 | pass | LLO_3 | Reworked | Yes | No |  | 788 | LHO | yes | pass | yes | pass | HAM | 7 | pass | LHO_2 | Reworked | Yes
690 | LLO | yes | pass | yes | pass | HAM | 19 | pass | LLO_2 | waived | Yes | No |  | 789 | LASTI | yes | pass | yes | pass | HAM | 47 | pass | LASTI | waived | Yes
691 | LASTI | yes | no data | yes | pass | HAM | 4 | pass | LASTI | waived | Yes |  |  | 790 | LLO | yes | pass | yes | pass | HAM | 35 | pass | LLO_4 | waived | Yes | No
692 | LHO | yes | pass | yes | pass | HAM | 88 | pass | LHO_2 | Reworked | Yes | No |  | 791 | LHO | yes | pass |  | pass | HAM | 61 | pass | LHO | Reworked | Yes | Yes
693 | LHO | yes | pass | yes | pass | HAM | 14 | pass | LHO_2 | ???? | Yes |  |  | 792 | LHO | yes | pass | yes | pass | BSC | 33 | pass | LHO_BSC8 |  | Yes
694 | LHO | yes | pass | yes | pass | HAM | 5 | pass | LHO_HAM2 | Reworked | Yes |  |  | 793 | LLO | yes | pass | yes | pass | BSC | 41 | pass | LLO_5 |  | Yes | Yes
695 | SPSR | yes | pass | yes | pass | [5 empty] | Yes |  | frequency issue | 794 | LHO | yes | pass | yes | pass | HAM | 21 | pass | LHO | Reworked | Yes | Yes
696 | Geotech | yes | fail | [10 empty] | 795 | LLO | yes | pass | yes | pass | HAM | 92 | pass | LLO_4 | waived | Yes | No
697 | LLO | yes | pass | yes | fail | BSC | 11 | pass | LLO |  | Yes | Yes |  | 796 | LLO | yes | pass | yes | pass | HAM | 29 | pass | India_1 | New | Yes | Yes
698 | LLO | yes | pass | yes | pass | HAM | 31 | pass | LLO | Reworked | Yes | No |  | 797 | LASTI | yes | pass | yes | pass | HAM | 52 | pass | LASTI | waived | Yes
699 | LLO | yes | pass | yes | pass | HAM | 56 | pass | LLO_3 | waived | Yes |  |  | 798 | LVEA | yes | pass | yes | pass | BSC | 20 | pass | ready to ship | Reworked | Yes | Yes
700 | LLO | yes | pass | yes | pass | HAM | 63 | pass | LLO_5 | waived | Yes | No |  | 799 | LLO | yes | pass | yes | pass | HAM | 87 | pass | LLO | Reworked | Yes | Yes
701 | SPSR | yes | pass | yes | pass | [5 empty] | Yes |  | Spring mount broken | 800 | LHO | yes | pass | yes | pass | HAM | 62 | pass | LHO | Reworked | Yes | Yes
702 | LLO | yes | pass | yes | pass | HAM | 33 | pass | India_1 | New | Yes | Yes | former LHO test | 801 | LHO | yes | pass | yes | pass | BSC | 31 |  | LHO_BSC8 | waived | Yes
703 | LLO | yes | pass | yes | pass | BSC | 62 | pass | LLO_2 | Reworked | Yes |  |  | 802 | SPSR | yes | pass | yes | pass | HAM | 10 | pass |  |  | Yes | Yes
704 | LLO | yes | pass | yes | pass | HAM | 75 | pass | India_2 |  | Yes | No |  | 803 | LLO | yes | pass | yes | pass | [5 empty] | Yes | Yes
705 | LHO | yes | pass | yes | pass | HAM | 53 | pass | LHO | Reworked | Yes | Yes |  | 804 | LLO | yes | pass | yes | pass | HAM | 26 | pass | LLO_HAM4 | ??? | Yes | No
706 | SPSR | yes | pass | yes | pass | [5 empty] | Yes |  |  | 805 | LLO | yes | pass | yes | pass | HAM | 43 | pass | India_2 | New | Yes | Yes
707 | LASTI | yes | pass | yes | pass | HAM | 1 | pass | LASTI | waived | Yes |  |  | 806 | High Bay | yes | pass | yes | pass | [5 empty] | Yes
708 | LHO | yes | pass | yes | fail | HAM | 49 | pass | LHO | Reworked | Yes | No |  | 807 | LLO | yes | pass | yes | pass | HAM | 90 | pass | India_1 | New | Yes | Yes | Broken/Repaired
709 | LHO | yes | pass | yes | pass | HAM | 16 | pass | LHO | Reworked | Yes | Yes |  | 808 | LBR | yes | pass | yes | pass | [5 empty] | Yes
710 | LBR | yes | pass | yes | pass | [5 empty] | Yes |  |  | 809 | LLO | yes | pass | yes | pass | HAM | 46 |  | LLO_2 |  | Yes
711 | High Bay | yes | pass | yes | pass | HAM | 95 | pass |  | Reworked | Yes |  |  | 810 | LHO | yes | pass | yes | pass | HAM | 18 | pass | LHO_6 | Reworked | yes | Yes
712 | LLO | yes | pass |  | pass | BSC | 506 | pass | LLO |  | Yes | Yes |  | 811 | LLO | yes | pass | yes | pass | BSC | 2 | pass | LLO_3 |  | Yes | Yes
713 | LHO | yes | pass | yes | pass | HAM | 45 | pass | LHO | Reworked | Yes | Yes |  | 812 | LHO | yes | pass | yes | pass | HAM | 78 | pass | LHO | Reworked | Yes | Yes
714 | LASTI | yes | pass | yes | pass | HAM | 17 | pass | LASTI | No | Yes | No |  | 813 | LLO | yes | pass | yes | pass | HAM | 86 | pass | LLO_3 | ???? | Yes | No
715 | LHO | yes | pass | yes | pass | HAM | 30 | pass | LHO_2 | Reworked | Yes |  |  | 814 | LHO | yes | pass | yes | pass | HAM | 93 | pass | LHO | ??? | Yes
716 | LLO | yes | pass | yes | fail | BSC | 39 | pass | LLO |  | Yes | Yes |  | 815 | LLO | yes | pass | yes | pass | HAM | 83 | pass | India_2 | New | Yes | Yes
717 | LLO | yes | pass | yes | pass | HAM | 80 | pass | LLO_4 | waived | Yes |  |  | 816 | LLO | yes | pass | yes | pass | BSC | 92 | pass | LLO | Reworked | Yes | Yes
718 | SPSR | yes | pass | yes | pass | BSC | 22 | pass | LLO_1 |  | Yes | yes |  | 817 | LHO | yes | pass | yes | pass | HAM | 66 | pass | LHO_6 | Reworked | Yes | Yes
719 | SPSR | yes | pass | yes | pass | B SC | 98 | pass | ??? | ??? | Yes |  | dropped instrument-broken | 818 | LLO | yes | pass | yes | pass | BSC | 7 | pass |  |  |  | Yes
720 | SPSR | yes | pass | yes | fail | [6 empty] | Yes |  | 819 | LLO | yes | pass | yes | pass | BSC | 32 | pass |  | New | Yes | Yes
721 | LLO | yes | pass | yes | pass | HAM | 15 | pass | LLO_4 | waived | Yes |  |  | 820 | LHO | yes | pass | yes | pass | HAM | 13 | pass | LHO | Reworked | Yes | Yes
722 | LLO | yes | pass | yes | pass | BSC | 1 | pass | LLO_3 |  | Yes | Yes |  | 821 | LLO | yes | pass | yes | pass | BSC | 4 | pass |  | New |  | Yes
723 | LLO | yes | pass |  | fail | BSC | 60 | pass | LLO_1 |  | Yes |  |  | 822 | LLO | yes | pass | yes | pass | BSC | 65 | pass | LLO_2 | Reworked | Yes
724 | LHO | yes | pass | yes | pass | HAM | 48 | pass | LHO_HAM2 | Reworked | Yes |  |  | 823 | LLO | yes | pass | yes | pass | BSC | 15 | pass | LLO |  | Yes | Yes
725 | LHO | yes | pass | yes | pass | BSC | 55 | pass | LHO |  | Yes | Yes |  | 824 | LLO | yes | pass | yes | pass | HAM | 37 | pass |  | New | Yes | Yes
726 | LLO | yes | pass | yes | pass | BSC | 77 | pass | LLO_2 |  | Yes | No |  | 825 | LHO | yes | pass | yes | pass | BSC | 10 |  | LHO_9 | Reworked | Yes | Yes
727 | LHO | yes | pass | yes | pass | BSC | 90 | pass | LHO_9 | Reworked | Yes | Yes |  | 826 | LLO | yes | pass | yes | pass | BSC | 53 | pass | LLO_1 |  | Yes | Yes
728 | LLO | yes | pass | yes | pass | BSC | 57 | pass | LLO_2 | Reworked | Yes |  |  | 827 | LHO | yes | pass | yes | pass | HAM | 3 | pass | LHO | Reworked | Yes | Yes
729 | LLO | yes | pass | yes | pass | BSC | 66 | pass | LLO_4 |  | Yes | Yes |  | 828 | LHO | yes | pass | yes | pass | HAM | 68 | pass | LHO | New | Yes | Yes
730 | LLO | yes | pass | yes | pass | BSC | 23 | pass | LLO_1 | New | Yes | Yes |  | 829 | LHO | yes | pass | yes | pass | HAM | 38 | pass | LHO | New | Yes | Yes
731 | LLO | yes | pass | yes | pass | BSC | 80 |  | LLO |  | Yes | Yes |  | 830 | LLO | yes | pass | yes | pass | HAM | 54 | pass | LLO | New | Yes | Yes
732 | LLO | yes | pass | yes | pass | BSC | 74 | pass | LLO_4 |  | Yes | Yes |  | 831 | LLO | yes | pass | yes | pass | HAM | 9 | pass | LLO | New | Yes | Yes
733 | LHO | yes | pass | yes | pass | HAM | 72 | pass | LHO | Reworked | Yes | No |  | 832 | LHO | yes | pass | yes | pass | BSC | 45 | pass | LHO |  | Yes | Yes
734 | LHO | yes | pass |  | pass | BSC | 75 |  | LHO_BSC6 | waived | Yes |  |  | 833 | SPSR | yes | pass | yes | pass | H AM | 94 | pass |  | New | No! | Yes | Not balancing properly
735 | LHO | yes | pass | yes | pass | BSC | 79 | pass | LHO_BSC8 | waived | Yes |  |  | 834 | LHO | yes | pass | yes | pass | BSC | 70 | pass | LHO |  | Yes | Yes
736 | LHO | yes | pass | yes | pass | BSC | 8 | pass | LHO_9 |  | Yes | Yes |  | 835 | LLO | yes | pass | yes | pass | HAM | 24 | pass | LLO_5 | New | Yes
737 | LHO | yes | pass | yes | pass | HAM | 69 | pass | LHO | Reworked | Yes | No |  | 836 | LLO | yes | pass | yes | pass | BSC | 78 | pass | LLO_4 |  | Yes | Yes
738 | LLO | yes | pass | yes | pass | BSC | 81 | pass | LLO_5 |  | Yes | Yes |  | 837 | SPSR | yes | pass | yes | fail | BSC | 61 | pass | LLO_1 |  | Yes
739 | LHO | yes | pass | yes | pass | BSC | 94 | pass | LHO_BSC8 | waived | Yes |  |  | 838 | LLO | yes | pass | yes | pass | HAM | 42 | pass | LLO_3 | ??? | Yes | No
740 | LHO | yes | pass | yes | pass | BSC | 96 | pass | LHO_9 | Reworked | Yes | Yes |  | 839 | LHO | yes | pass | yes | pass | BSC | 101 | pass | LHO_BSC6 | waived | Yes
741 | LHO | yes | pass | yes | pass | BSC | 500 | pass | LHO | pass | Yes | Yes |  | 840 | LHO | yes | pass | yes | pass | BSC | 50 | pass | LHO |  | Yes | Yes
742 | SPSR | yes | pass | yes | pass | [5 empty] | Yes | Yes | bent torsion rod | 841 | LLO | yes | pass | yes | pass | BSC | 47 | pass | LLO_2 |  | Yes
743 | LHO | yes | pass | yes | pass | BSC | 102 | pass | LHO_BSC6 | waived | Yes |  |  | 842 | LLO | yes | pass | yes | pass | BSC | 71 | pass | LLO_2 |  | Yes
744 | LLO | yes | pass | yes | pass | [5 empty] | Yes | Yes | noisy signal | 843 | LHO | yes | pass | yes | pass | HAM | 71 | pass | LHO_5 |  | Yes | Yes
745 | LLO | yes | pass | yes | pass | BSC | 18 | pass | LLO_3 |  | Yes | No |  | 844 | LLO | yes | pass | yes | pass | BSC | 34 | pass | LLO_3 |  | Yes | Yes
746 | LHO | yes | pass | yes | pass | BSC | 100 | pass | LHO_BSC6 | waived | Yes |  |  | 845 | SPSR | yes | pass | yes | pass | H AM |  |  |  |  | Yes |  | mass sticking
747 | LLO | yes | pass | yes | fail | BSC | 17 | pass | LLO |  | Yes | Yes |  | 846 | LHO | yes | pass | yes | pass | BSC | 83 | pass | LHO_BSC6 | waived | Yes
748 | LLO | yes | pass | yes | pass | BSC | 73 | pass | LLO_4 |  | Yes | Yes |  | 847 | SPSR | yes | pass | yes | pass | H AM | 84 | pass |  | New | Yes |  | defect
749 | LLO | yes | pass | yes | pass | HAM | 36 | pass | LLO | New | Yes | Yes |  | 848 | LHO | yes | pass | yes | pass |  |  |  | LHO |  |  | Yes
750 | LLO | yes | pass | yes | pass | BSC | 72 | pass | LLO |  | Yes | Yes |  | 849 | SPSR | yes | pass | yes | pass | [6 empty] | Yes
751 | LHO | yes | pass | yes | pass | HAM | 23 | pass | LHO | New | Yes | No |  | 850 | LLO | yes | pass | yes | pass | BSC | 24 | pass | ready to ship | waived | yes | Yes
752 | LLO | yes | pass | yes | pass | HAM | 89 | pass | LLO | New | Yes | Yes |  | 851 | LLO | yes | pass | yes | pass | BSC | 63 | pass | LLO |  | Yes | Yes
753 | LLO | yes | pass | yes | pass | HAM | 96 | pass | India_2 | New | Yes | Yes |  | 852 | LHO | yes | pass | yes | pass | BSC | 54 | pass | LHO |  | Yes | Yes
754 | LHO | yes | pass | yes | pass | BSC | 51 | pass | LHO_3 |  | Yes | Yes |  | 853 | LLO | yes | pass | yes | pass | BSC | 504 | pass |  |  | Yes | Yes
755 | LHO | yes | pass | yes | pass | BSC | 87 | pass | LHO |  | Yes | Yes |  | 854 | LHO | yes | pass | yes | pass | HAM | 58 | pass | LHO | Reworked | Yes | Yes
756 | LHO | yes | pass | yes | fail | BSC | 69 | pass | LHO |  | Yes | Yes |  | 855 | LHO | yes | pass | yes | pass | BSC | 93 | pass | LHO_9 |  | Yes | Yes
757 | LHO | yes | pass | yes | pass | HAM | 3 | pass | LHO_4 | New | Yes | Yes |  | 856 | LLO | yes | pass | yes | pass | BSC | 28 |  | LLO_5 |  | Yes | Yes
758 | LLO | yes | pass | yes | pass | BSC | 35 | pass | LLO |  | Yes | Yes |  | 857 | LHO | yes | pass | yes | pass | HAM | 91 | pass | LHO | Reworked | Yes | Yes
759 | LHO | yes | pass | yes | pass | HAM | 28 | pass | LHO | Rework | Yes | Yes |  | 858 | LLO | yes | pass | yes | pass | BSC | 103 | pass | LLO_3 |  | Yes | Yes
760 | LLO | yes | pass | yes | pass | BSC | 6 | pass | LLO |  | Yes | Yes |  | 859 | LLO | yes | pass | yes | pass | HAM | 20 | pass |  | New | Yes | Yes
761 | LHO | yes | pass | yes | pass | BSC | 501 | pass | LHO | waived | Yes | Yes |  | 860 | LHO | yes | pass | yes | pass | BSC | 13 | pass | LHO |  | Yes | Yes
762 | LHO | yes | pass | yes | pass | BSC | 12 | pass | LHO |  | Yes | Yes |  | 861 | Lab | yes | pass | yes | pass | [6 empty] | Yes
763 | LLO | yes | pass | yes | pass | HAM | 51 | pass | India_1 | New | Yes | Yes |  | 862 | LLO | yes | pass | yes | pass | BSC | 43 | pass | LLO |  | Yes | Yes
764 | LLO | yes | pass | yes | pass | BSC | 25 | pass | LLO_5 |  | Yes | Yes |  | 863 | Geotech | yes | fail
765 | SPSR | yes | pass | yes | pass | [5 empty] | Yes | Yes | fell over on flow bench while locked | 864 | LLO | yes | pass | yes | pass | BSC | 503 | pass | LLO_5 |  | Yes | Yes
766 | LHO | yes | pass | yes | pass | HAM | 81 | pass | LHO | Rework | Yes | Yes |  | 865 | LHO | yes | pass | yes | pass | BSC | 67 | pass | LHO |  | Yes | Yes
767 | LHO | yes | pass | yes | pass | HAM | 59 | pass | LHO | New | Yes |  |  | 866 | LLO | yes | pass | yes | pass | BSC | 44 | pass | LLO_4 |  | Yes | Yes
768 | LLO | yes | pass | yes | pass | BSC | 58 | pass | LLO |  | Yes | Yes |  | 867 | LLO | yes | pass | yes | pass | HAM | 84 | pass |  | New | Yes | Yes
769 | LLO | yes | pass | yes | pass | HAM | 25 | pass | India_1 | New | Yes | Yes |  | 868 | LHO | yes | pass | yes | pass | BSC | 59 | pass | LHO | waived | Yes | Yes
770 | LHO | yes | pass | yes | pass | BSC | 64 | pass | LHO |  | Yes | Yes |  | 869 | LHO | yes | pass | yes | pass | BSC | 30 | pass | LHO | waived | Yes | Yes
771 | LLO | yes | pass | yes | pass | BSC | 99 | pass | LLO_5 |  |  | Yes |  | 870 | LHO | yes | pass | yes | pass | BSC | 97 | pass | LHO |  | Yes | Yes
772 | LHO | yes | pass | yes | pass | BSC | 42 | pass | LHO |  | Yes | Yes |  | 871 | SPSR | yes | pass | yes | pass | [6 empty] | Yes | mass indicator not working
773 | LHO | yes | pass | yes | pass | HAM | 50 | pass | LHO | Rework | Yes | Yes |  | 872 | LLO | yes | pass | yes | pass | BSC | 38 | pass | LLO_1 |  | Yes | Yes
774 | LLO | yes | pass | yes | pass | HAM | 40 | pass | LLO | Reworked | Yes | Yes |  | 873 | LHO | yes | pass | yes | pass | BSC | 82 | pass | LHO_9 |  | Yes | Yes