LIGO Laboratory / LIGO Scientific Collaboration

LIGO-M060045-00-M	ADVANCED LIGO	28 April 2006

Advanced LIGO Risk Management Plan

Carol Wilkinson, David Shoemaker

Distribution of this document:

LIGO Scientific Collaboration

This is an internal working note

of the LIGO Scientific Collaboration.

The report prepared by ARES Corporation under the

direction of Advanced LIGO Project Management

| California Institute of Technology LIGO Project – MS 18-34 1200 E. California Blvd. Pasadena, CA 91125 Phone (626) 395-2129 Fax (626) 304-9834 E-mail: info@ligo.caltech.edu | Massachusetts Institute of Technology LIGO Project – NW17-161 175 Albany St Cambridge, MA 02139 Phone (617) 253-4824 Fax (617) 253-7014 E-mail: info@ligo.mit.edu |
| --- | --- |
| LIGO Hanford Observatory P.O. Box 1970 Mail Stop S9-02 Richland WA 99352 Phone 509-372-8106 Fax 509-372-8137 | LIGO Livingston Observatory P.O. Box 940 Livingston, LA 70754 Phone 225-686-3100 Fax 225-686-7189 |

http://www.ligo.caltech.edu/

CHANGE CONTROL LOG

| Section Number | Change | Date | Editor |
| --- | --- | --- | --- |

Table of Contents

1.0	INTRODUCTION	1

2.0	Risk Management Methodology	1

2.1	Definitions	1

2.2	Risk Management Process	2

2.2.1	Identify Risks	3

2.2.2	Categorize and Evaluate Risks	3

2.2.3	Mitigate Risks	3

2.2.4	Monitor and Review Risks	4

2.2.5	Communicate Risk Information	4

3.0	Risk Management Roles and Responsibilities	4

4.0	Risk Management Tools	5

4.1	Advanced LIGO Project Risk Register and Advanced LIGO Major Threat List	5

4.2	Uncertainty Analysis	5

5.0	Training	6

APPENDICES

APPENDIX A

ADVANCED LIGO RISK REGISTER - SAMPLE

APPENDIX B

ADVANCED LIGO MAJOR THREAT LIST – SAMPLE

ADVANCED LIGO MAJOR THREAT LIST – SAMPLE

APPENDIX C

GUIDELINES FOR RISK CATEGORIZATION AND EVALUATION

APPENDIX D

RISK MANAGEMENT TEAM MEETING SAMPLE AGENDA

APPENDIX E

RISK MANAGEMENT Training form

Figures

Figure 2-1.  Risk Management Process.	2

Figure 4-1.  Uncertainty Analysis Process.	6

Tables

Table 3-1. Advanced LIGO Project Risk Management Responsibilities.	5

# INTRODUCTION

This Risk Management Plan describes principles and processes to continuously manage risks in an analytical, forward-looking, structured, and informative manner.  Implementation of this Risk Management Plan supports successful completion of the Advanced Laser Interferometer Gravitational Wave Observatory (LIGO) Project by:

Increasing the probability that the Project will conclude successfully,

Identifying risks early and implementing mitigation actions in a timely manner, and

Ranking and evaluating risks to focus limited resources on those that have the highest potential impact on the Project.

From the inception of the Advanced LIGO Project, risks were identified and strategies to mitigate these risks incorporated into Project planning.  Mitigation strategies included reforming comprehensive prototyping, implementing formal design review processes, providing in-process spares, pursuing alternative technologies, and starting procurement early for long lead items.  This plan provides a formalized approach to continue management of previously identified risks and to actively identify and manage new risks.

# Risk Management Methodology

## Definitions

Risk - Any unplanned event or circumstance that, if it occurred, would have a negative consequence to the Advanced LIGO Project.  Risk is a measure of the potential inability to achieve overall Project objectives within defined scope, cost, schedule, and performance constraints.  The two components of risk include the probability of failing to achieve a particular outcome, and the consequence of failing to achieve that outcome.  Risks are “Unusual events" that are not common and may include such things as: losing a sole source vendor, experiencing an unexpected failure mode of a component, or exposing design flaws during integration that require a major redesign and re-engineering.

Risk Management – An organized, systematic, decision-making process that efficiently identifies risks, categorizes and evaluates risks, and effectively reduces or eliminates threats to achieving Project objectives.  Risk management is concerned with future events, whose exact outcome is unknown, and how to manage these uncertainties by identifying and examining a range of possible outcomes.  The alternative to risk management is crisis management, a resource-intensive process that is normally constrained by a restrictive set of available options.

## Risk Management Process

The Risk Management Process consists of the five major elements described below and depicted in Figure 2-1.  The process is iterative and serves to continuously manage risk.

Identify the event or circumstance (and their sources) that pose a risk.

Categorize the risks relative to four Project objectives (cost, schedule, scope, and performance).

Evaluate the risks to assess the probability, the consequences, and the overall risk rank.

Develop and approve risk mitigation strategies and monitor progress.

Communicate the risk, its impact, the mitigation strategies, and the effectiveness of the mitigation process to Project team-members.

Figure 2-1.  Risk Management Process.

| Internal External | Cost Schedule Scope Performance | Risk Characteristics Risk Ranking Critical Risks | Accept Mitigation Action | Meetings Risk Register Review |
| --- | --- | --- | --- | --- |

A Risk Register is the main tool used to implement the Advanced LIGO Risk Management Processes.  A sample (or “snapshot in time”) of the Advanced LIGO Risk Register (Risk Register) is shown as Appendix A.  The highest priority risks from the Risk Register are also documented on a Major Threat List.  A sample (or “snapshot in time”) of the Advanced LIGO Major Threat List is shown as Appendix B.  Further discussion of the Risk Register and Advanced LIGO Major Threat List is contained throughout this plan and in Section 4.0, Risk Management Tools.

The major elements of the Risk Management Process and how these elements relate to the Advanced LIGO Project are discussed in the following sections.

### Identify Risks

Risk identification starts with open communication at all levels.  Any Advanced LIGO team-member may identify a risk.  The team-member communicates the risk and background information to the Project Manager (PM).  The PM reviews the risk, interfaces with cognizant team-members (as necessary), and determines if the risk should be added to the Risk Register.  If the risk is added to the register, the PM represents the risk as an “if, then” statement (to illustrate the probability and consequence components of the risk) and assigns a unique risk identification number.

### Categorize and Evaluate Risks

The PM works with cognizant team-members (as necessary) to determine the probability of occurrence, the consequences if it occurs, the correlation to the four Project objectives, and the overall “risk rank.”

Consequences are considered relative to the following four Project objectives:

Scope,

Performance,

Schedule, and

Cost.

Each risk is evaluated for its impact on each objective.  Risk consequences are rated from 1 to 5, with 1 having the least impact and 5 having the greatest impact.  Risk probabilities are also addressed on a scale of 1 to 5, with 1 being less likely to occur and 5 being most likely to occur.  An overall “risk rank” (high, medium, or low) is assigned by using a risk scoring matrix (and other Project data if appropriate) to evaluate the probability of the risk with respect to the highest impacted Project objective.  Guidelines for risk probability, risk consequence, risk scoring, and the 5 by 5 risk scoring matrix are provided in Appendix C, Guidelines for Risk Categorization and Evaluation.  Risk categorizations and evaluations are reviewed by the Risk Management Team (RMT).

### Mitigate Risks

The PM interfaces with cognizant team-members (as necessary) and the RMT to finalize risk mitigations.  Risks are mitigated using the following strategies:

Accept – Accept the risk level and continue on the current plan. There is either a very low risk, the cost of reduction/mitigation outweighs the possible risk consequence, or there is no appropriate mitigation.

Mitigation Action – These actions lessen the probability of a risk occurring and/or reduce its negative consequence on the Project if it occurs.

Mitigations associated with risks identified on the “Major Threat List” will be planned and implemented to reduce the consequences and/or probability before impacts occur.  Mitigation actions for other risks may be implemented based on RMT prioritization of mitigations with respect to cost effective management, other LIGO activities, and resource availability. The PM, with input from cognizant team-members (as necessary), is responsible for managing risk mitigations.

The PM, with support from Advanced LIGO team-members, is responsible for implementing all mitigations/actions.

### Monitor and Review Risks

Risks are monitored on a periodic basis and are reassessed as conditions change or more information becomes available.  Risks on the Major Threat List are reviewed monthly at RMT meetings.  All other risks are reviewed quarterly at RMT meetings.

The PM is responsible for revising the Risk Register as a result of RMT input relative to re-categorization, re-evaluation, and monitoring and review of mitigations (consistent with responsibilities identified in Table 3-1).

### Communicate Risk Information

Risks information is communicated to top management through RMT meetings and to all appropriate team-members through staff meetings and through review of the posted Risk Register.

# Risk Management Roles and Responsibilities

Accountability for risk management is a responsibility levied upon each individual working on the Advanced LIGO Project.  The Project Leader (PL) has overall responsibility for Advanced LIGO risk management.  Implementation and management of risk management processes is the responsibility of the PM.  The PL and PM work in conjunction with the RMT to administer Advanced LIGO risk management processes.  The RMT is chaired by the PL and consists of the following members:

Advanced LIGO PL,

Advanced LIGO PM,

Advanced LIGO System Scientist (SS),

Advanced LIGO Project System Engineering Lead (SE) , and

Any additional members appointed by the PL.

Table 3-1 describes risk management responsibilities for the Project.

Table 3-1. Advanced LIGO Project Risk Management Responsibilities.

| Project Team-Member | Responsibility | Frequency |
| --- | --- | --- |
| PL | Overall responsibility for risk management. | Continuously |
|  | Chair the RMT meetings (See Appendix D for a sample meeting agenda). | Once a month (more often if necessary) |
| PM | Point of contact for risk management process. | Continuously |
|  | Manage Advanced LIGO Project Risk Register – including management and monitoring of all risks and mitigations. | Continuously |
|  | Implement risk training. | Continuously |
|  | Provide risk management reporting for the Project. | Once a month (more often if necessary) |
|  | Provide input to RMT regarding Advanced LIGO Major Threat List. | Once a month (more often if necessary) |
|  | Provide input to RMT regarding risks not on Advanced LIGO Major Threat List. | Once a quarter |
| The RMT | Review risk management implementation. | Once a month (more often if necessary) |
|  | Review and approve risk categorizations, evaluations, and mitigations. | Once a month (more often if necessary) |
|  | Identify risks at Project and subsystem levels. | Continuously |
| Each Advanced LIGO Team-Member | Identify potential risks within their sphere of influence, communicate risks to PM, assist PM in performing risk categorizations and evaluations, and provide input regarding possible risk mitigations. | Continuously |
|  | Monitor Project risk status by reviewing the posted Risk Register. | Continuously |

# Risk Management Tools

## Advanced LIGO Project Risk Register and Advanced LIGO Major Threat List

The Risk Register is the main tool used to implement the Risk Management Processes.  It is a “living” list of risks including categorization and evaluation data as well as mitigation information.  The Advanced LIGO Major Threat List documents the highest priority risks contained on the Risk Register.  It is also a “living” document where risks appear and are removed depending on identified risks and mitigation activities.  The current Risk Register and Advanced LIGO Major Threat List are located on the Advanced LIGO Project Center Website and are maintained/controlled by the PM.

## Uncertainty Analysis

The purpose of uncertainty analyses is to quantify a level of confidence in the Project’s basis documents regarding cost and schedule.  Uncertainty, for analysis purposes, is determined from risk consequence data and Project planning data.  Uncertainties (usually with respect to estimate and schedule) are defined in terms of probability density functions (pdfs).  The uncertainty pdfs are then propagated through the Project estimate and schedule data using Monte-Carlo techniques. Uncertainty-based analyses determine the impacts to the Project from uncertainty associated with risk consequences and Project planning data.  Normally, sensitivity analyses are run as part of uncertainty analysis to provide major cost and schedule drivers that must be successfully managed to complete the Project (or Project activity) as planned.  Uncertainty analyses are performed using the methodology described above and shown in Figure 4-1 below.

Figure 4-1.  Uncertainty Analysis Process.

# Training

The PM is responsible for providing risk management training for the Advanced LIGO Project team members.  Each Subsystem Lead is required to undergo initial risk management training when this plan is approved and implemented (see Appendix E).  The PM is responsible for providing periodic risk management training to the Subsystem Leads.  The Subsystem Leads are responsible for providing informal training to the employees working in his/her subsystem.

APPENDIX A

ADVANCED LIGO RISK REGISTER - SAMPLE

ADVANCED LIGO RISK REGISTER - SAMPLE

APPENDIX B

ADVANCED LIGO MAJOR THREAT LIST – SAMPLE

ADVANCED LIGO MAJOR THREAT LIST – SAMPLE

APPENDIX C

GUIDELINES FOR RISK CATEGORIZATION AND EVALUATION

APPENDIX D

RISK MANAGEMENT TEAM MEETING SAMPLE AGENDA

Risk Management Team Meeting

Sample Agenda

The below table documents sample agenda items and correlates those items with information in the Risk Management Plan.

| Agenda Item | Corresponding Risk Management Plan Information |
| --- | --- |
| 1) Assess risk management implementation through discussions with PM | Section 3.0 - “The PL and PM work in conjunction with the RMT to administer Advanced LIGO risk management processes.” |
| 2) Approve risk categorizations/evaluations and risk mitigation activities. | Section 2.2.2 – “Risk categorizations and evaluations are reviewed by the Risk Management Team (RMT).” .Section 2.2.3 – “The PM interfaces with cognizant team-members (as necessary) and the RMT to finalize risk mitigations.” |
| 3) Discuss Risks | Section 1.0 – “Implementation of this Risk Management Plan improves the Advanced Laser Interferometer Gravitational Wave Observatory (LIGO) Project management…..” Section 2.2.4 – “Risks on the Major Threat List are reviewed monthly at RMT meetings. Medium risks (not on the Major Threat List) and low risks are reviewed quarterly at RMT meetings.” |

APPENDIX E

RISK MANAGEMENT Training form

| I have read and understand the policies and processes documented in LIGO-M060045-00-M, Advanced LIGO Risk Management Plan. By completely reviewing the document and understanding how the processes are to be implemented for the project, I have satisfied the training requirements identified in the plan. My signature below documents that I am trained. |
| --- |
| Name (Print) | Signature | Date |