## BOM
[6 empty] | W03474 | QTY: |  | 1 | [9 empty] | Last Updated: MKM2 08-23-2010
|  |  | ASSEMBLY LEVEL |  |  | PART NO. | DESCRIPTION | FINISHSIZE | QTY | TOTAL QTY. | MATERIAL | DATE DUE | TRAVELER NO. | MAKE/BUY | PURCHASE STOCK SIZE PER ASSEMBLY | DUE DATE | PO# | MATERIAL DUE BY | COMMENTS
[6 empty] | 114142-00 | OUTLINE, ADAPTER A-17
[6 empty] | 114142-00ID | FINAL INSPECTION DOCUMENT
1 | [5 empty] | 114436-00S | FINAL ASSEMBLY, ADAPTER A-17 |  | 1 | 1 | AISI 304/AISI 304L DUAL CERT PER SA240 | 12/1/2010 | W03474/1 | M
| 2 |  |  |  |  | 114296-00WS | WELDMENT, FINAL, ADAPTER A-17 |  | 1 | 1 | AISI 304/AISI 304L DUAL CERT PER SA240 | 11/24/10 | W03474/2 | M
|  | 3 |  |  |  | 114302-00S | FLANGE, LARGE, ADAPTER A-17 |  | 1 | 1 | AISI 304L PER ASME SPEC SA-182 GRADE F; MAX SULFUR CONTENT .006% | 11/17/10 | W03474/3 | M
|  |  | 4 |  |  | 114303-00S | FORGING, 44.90 ID, 80.25 OD, SMOOTH | FORGING, 2.00 THK, 44.90 ID, 80.25 OD | 1 | 1 | AISI 304L PER ASME SPEC SA-182 GRADE F; MAX SULFUR CONTENT .006% |  |  | B | FORGING, 2.00 THK, 44.90 ID, 80.25 OD | 2010-11-10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
|  | 3 |  |  |  | 114300-00WS | WELDMENT, BELLOWS AND TUBES |  | 1 | 1 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B |  | 2010-11-10
|  |  | 4 |  |  | 114306-00S | BELLOWS, 44.625 ID |  | 1 | 1 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | 114306-00S, BELLOWS (BUY TO PRINT) | - |  |  | SINGLE SOURCE: HYSPAN! CMTRS REQUIRED FOR ALL COMPONENTS! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, LIGO DOCUMENT E0900439 (LATEST VERSION), QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC 114(QA PROCUREMENT LEVEL 1), AND QP1730-10 §3. QC MUST SIGN OFF ON ALL POs BEFOR PURCHASING
|  |  | 4 |  |  | 114301-00S | ROLL-UP, ADAPTER, A-17 | ROLL-UP, .25 WALL, 45.25 ID, 17.00 LG | 2 | 2 | AISI 304/AISI 304L DUAL CERT PER SA240 | 11/3/10 | W03474/4 | M |  | -
|  |  |  | 5 |  |  | ROLL-UP, .25 WALL, 45.25 ID, 17.00 LG | ROLL-UP, .25 WALL, 45.25 ID, 17.00 LG | 2 | 2 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | 114301-00S; ROLL-UP, .25 WALL, 45.25 ID, 17.25 LG | 2010-10-27 |  |  | SINGLE SOURCE: NORCAL METAL FABRICATORS! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), QC MUST SIGN OFF ON POs BEFORE ORDERING, AND QP1730-10 §3. GNB TO MACHINE ENDS OF ROLL-UP THEN PROVIDE COMPONENTS TO HYSPAN FOR NEXT LEVEL ASSY.
[5 empty] | 6 |  | PLT, .25 THK, 143.73 WD, 17.00 LG | PLT, .25 THK, 143.73 WD, 17.00 LG | 2 | 2 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | PLT, .25 THK, 143.73 WD, 17.25 LG | 2010-10-20 |  |  | SINGLE SOURCE: A.M. CASTLE & CO.! CMTRS REQUIRED FOR ALL MATERIAL! DROP SHIP MATERIAL FROM A.M. CASTLE & CO TO NORCAL METAL FABRICATORS! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. VENDOR TO SUPPLY A 2X12" COUPON FROM THE SAME HEAT LOT AS THIS PLATE. QC MUST SIGN OFF ON POs BEFORE ORDERING.
|  |  | 4 |  |  | 114226-01S | MOUNT, TIE ROD, ADAPTER A-17 |  | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B |  | -
|  |  |  | 5 |  |  | BEAM, BOX, .50 WALL, 6.00 WD, 8.00 HI, 5.00 LG | BEAM, BOX, .50 WALL, 6.00 WD, 8.00 HI, 5.00 LG | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | BEAM, BOX, .50 WALL, 6.00 WD, 8.00 HI, 5.25 LG | -
|  |  | 4 |  |  | 114227-00S | LIFTING EYE, TIE ROD, LIGO |  | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B |  | -
|  |  |  | 5 |  |  | PLT, .38 THK, 4.00 WD, 8.00 LG | PLT, .38 THK, 4.00 WD, 8.00 LG | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | PLT, .38 THK, 4.25 WD, 8.25 LG | -
|  |  | 4 |  |  | 114232-01S | PLATE, BACKING, NUT |  | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B |  | -
|  |  |  | 5 |  |  | PLATE, 1.00 THK, 3.00 WD, 5.00 LG | PLATE, 1.00 THK, 3.00 WD, 5.00 LG | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | PLATE, 1.00 THK, 3.25 WD, 5.25 LG | -
|  |  | 4 |  |  | 114233-01S | PLATE, BACKING, NUT SMALL |  | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B |  | -
|  |  |  | 5 |  |  | PLT, .25 THK, 2.50 WD, 4.00 LG | PLT, .25 THK, 2.50 WD, 4.00 LG | 6 | 6 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | PLT, .25 THK, 2.75 WD, 4.25 LG | -
|  |  | 4 |  |  | N16C3200Z | THREADED ROD, 1-8 UNC, 20.00 LG, ZINC PLATED | ROD, THREADED, 1-8 UNC, 20.00 LG | 3 | 3 | ZINC PLATED STEEL |  |  | B | THREADED ROD, 1-8 UNC, 20.00 LG | -
|  |  | 4 |  |  | G16C0000Z | HEX NUT, 1-8, ZINC PLATED |  | 12 | 12 | ZINC PLATED STEEL |  |  | B | HEX NUT, 1-8 | -
|  | 3 |  |  |  | 114304-00S | FLANGE, SMALL, ADAPTER A-17 |  | 1 | 1 | AISI 304L PER ASME SPEC SA-182 GRADE F; MAX SULFER CONTENT .006% | 11/17/10 | W03474/5 | M
|  |  | 4 |  |  | 114305-00S | FORGING, 44 ID, 52.26 OD, GROOVED | FORGING, 1.50 THK, 44.00 ID, 52.26 OD | 1 | 1 | AISI 304L PER ASME SPEC SA-182 GRADE F; MAX SULFER CONTENT .006% |  |  | B | FORGING, 44 ID, 52.26 OD, GROOVED | 2010-11-10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
|  | 3 |  |  |  | 114260-01WS | WELDMENT, PORT, 10" CF |  | 10 | 10 | AISI 304/AISI 304L DUAL CERT PER SA240 | 11/17/10 | W03474/6 | M
|  |  | 4 |  |  | 1000-800N | (NORCAL) FLANGE, CF, 10" OD, NR, THRU HOLES |  | 10 | 10 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | (N-C) FLANGE, CF, 10" OD, NR, THRU HOLES | 2010-11-10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
|  |  | 4 |  |  | 114435-00S | TUBE, 10" CF, A-17 PORT |  | 10 | 10 | AISI 304/AISI 304L DUAL CERT PER SA240 | 11/10/10 | W03474/7 | M
|  |  |  | 5 |  |  | TUBE, 8.00 OD, .25 WALL, 3.94 LG | TUBE, 8.00 OD, .25 WALL, 3.94 LG | 10 | 10 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | TUBE, 8.00 OD, .25 WALL, 4.25 LG | 2010-11-03 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
| 2 |  |  |  |  | G-1000 | (NORCAL) GASKET, COPPER, 10" CF | (NORCAL) GASKET, COPPER, 10" CF | 10 | 10 | OFHC |  |  | B | (NORCAL) GASKET, COPPER, 10" CF | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
| 2 |  |  |  |  | 1000-000N | (NORCAL) BLANK, CF, 10" OD | (NORCAL) BLANK, CF, 10" OD | 10 | 10 | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | B | (NORCAL) BLANK, CF, 10" OD | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
| 2 |  |  |  |  | F0500000Z | WASHER, 5/16 NOM ID, 0.065 THK, ZINC PLATED | WASHER, 5/16 NOM ID, 0.065 THK | 480 | 480 | ZINC PLATED STEEL |  |  | B | WASHER, 5/16 NOM ID, 0.065 THK | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
| 2 |  |  |  |  | G05F0000Z | HEX NUT, 5/16-24, ZINC PLATED | HEX NUT, 5/16-24 | 240 | 240 | ZINC PLATED STEEL |  |  | B | HEX NUT, 5/16-24 | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
| 2 |  |  |  |  | C05F0400Z | HHCS, 5/16-24, 2.50 LG, ZINC PLATED | HHCS, 5/16-24, 2.50 LG | 240 | 240 | ZINC PLATED STEEL |  |  | B | HHCS, 5/16-24, 2.50 LG | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
1 | [6 empty] | ROD, WELD, 1/8" X 36", 50# BOX | ROD, WELD, 1/8" X 36", 50# BOX | 1 | 1 | AISI 304L |  |  | B | ROD, WELD, 1/8" X 36", 50# BOX | 11/24/10 |  |  | CMTRs REQUIRED FOR ALL MATERIAL! APPLY THE FOLLOWING: ASTM A-480, ASTM A-700, QC 108§1.1 (BUY AMERICAN), QC109 (NON-ESCORT & INSPECTION RIGHT), QC126(QA PROCUREMENT LEVEL 2), AND QP1730-10 §3. QC MUST SIGN OFF ON POs PRIOR TO ORDERING.
1 | [5 empty] | 114481-00A | Blank, 52.25" OD, SHIPPING |  | 1 | 1 | AL 6061-T6 | [7 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
1 | [5 empty] | 114497-00A | BLANK, SHIPPING, 80.25 OD, W/ APS |  | 1 | 1 | AL 6061-T6 | [7 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
1 | [5 empty] | 114492-01S | TEST FLANGE, 52.25 OD |  | 1 | 1 | [8 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
1 | [5 empty] | 114493-00S | TEST FLANGE 80.25 |  | 1 | 1 | TBD | [7 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
1 | [5 empty] | 114518-00A | CRADLE, SHIPPING |  | 1 | 1 | TBD | [7 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
1 | [6 empty] | CRATE, 88" LG, 88" WD, 48" HIGH | CRATE, 88" LG, 88" WD, 48" HIGH | 1 | 1 | TBD | [7 empty] | FOR REFERENCE ONLY; ALL SHIPPING AND TESTING COMPONENTS UNDER W03480
Formulas:
DUE DATE = [DATE DUE, row above]-7
DUE DATE = [DUE DATE, row above]-7

## LABOR
[5 empty] | Totals per dept. | 28.5 | 21.5 | 6 | 17 | 30.9 | 0 | 6.6 | 3.75 | 7.1 | 73
WORK CENTER CODES
[16 empty] | DEPT: | MACHINE | WELD | DETAIL | ASSEMBLY | WATERJET | SAW CUT | R/I | INSPECTION | PACKAGING | SUPPLY CHAIN | INDIRECT MISC. | TRAINING | GENERAL HELPER
[6 empty] | 1 | 10 | 20 | 30 | 47 | 50 | 60 | 43 | 49 |  | CODE: | 1 | 10 | 20 | 30 | 50 | 43 | 46 | 47 | 49 | 60 | 40 | 44 | 45
WORK ORDER |  |  | Description | Set-up Total | Run Total | MACHINE | WELD | DETAIL | ASSEMBLY | INSPECTION | WATERJET | SUPPLY CHAIN | SAW CUT | PACKAGING | Total By Work Order:
W03474/1 | 1 | 98 | FINAL ASSEMBLY, ADAPTER A-17 | 9.45 | 46 | 0 | 0 | 6 | 17 | 25.85 | 0 | 2.85 | 0 | 4 | 23
W03474/2 | 2 | 58 | WELDMENT, FINAL, ADAPTER A-17 | 3.5 | 16.5 | 0 | 14.5 | 0 | 0 | 3.25 | 0 | 2.25 | 0 | 0 | 14.5
W03474/3 | 3 | 52 | FLANGE, LARGE, ADAPTER A-17 | 1.5 | 11.25 | 12.5 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 12.5
W03474/4 | 4 | 57 | ROLL-UP, ADAPTER, A-17 | 0.35 | 6.1 | 0 | 0 | 0 | 0 | 0.1 | 0 | 0 | 3.25 | 3.1 | 0
W03474/5 | 5 | 52 | FLANGE, SMALL, ADAPTER A-17 | 1.5 | 11.25 | 12.5 | 0 | 0 | 0 | 0.25 | 0 | 0 | 0 | 0 | 12.5
W03474/6 | 6 | 57 | WELDMENT, PORT, 10" CF | 1 | 8.6 | 0 | 7 | 0 | 0 | 1.1 | 0 | 1.5 | 0 | 0 | 7
W03474/7 | 7 | 57 | TUBE, 10" CF, A-17 PORT | 0.75 | 3.35 | 3.5 | 0 | 0 | 0 | 0.1 | 0 | 0 | 0.5 | 0 | 3.5
Note on P6: Instructions: To add new rows, highlight the last occupied row and use the "AutoComplete" function to extend the table as many rows as needed. Departments can be changed by clicking on the cell containing the header and selecting a department from the pull-down menu. If you are getting "#REF!" errors check to make sure your worksheets are named only by the traveller number, nothing else. This worksheet only works if you name your traveller worksheets by the traveller number only (i.e. "1" or "12" not "123456-00M #1") Please do not edit any functions

## 1
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/1
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114436-00S | [5 empty] | DUE DATE |  | 12/1/2010
| Description: | FINAL ASSEMBLY, ADAPTER A-17 |  |  |  | QTY
[6 empty] | 1 | [5 empty] | Page | 1 | of | 2
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-21 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114436-00S |  | FINAL ASSEMBLY, ADAPTER A-17 | [6 empty] | A
|  | QP1730-10 |  | Contamination Control Plan | [6 empty] | B
|  | QP1750-A7 |  | Leak Test Procedure | [6 empty] | A
|  | QP1750-D2 |  | Final Cleaning Procedure | [6 empty] | A
|  | QP1750-R5 |  | Visible and UV Inspection Procedure | [6 empty] | A
|  | QP1750-A3 |  | Cleanliness Testing Procedure | [6 empty] | B
|  | QP1750-A6 |  | Bakeout procedure | [6 empty] | -
|  | QP1750-A5 |  | RGA Test Procedure | [6 empty] | -
|  | QP1750-R6 |  | Shipping Procedure | [6 empty] | -
> | Inspection Document
> | Drawing | 114146-00ID |  | Inspection Document | [6 empty] | -
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 114296-00WS |  |  | WELDMENT, FINAL, ADAPTER A-17 | [6 empty] | 1
| G-1000 |  |  | (NORCAL) GASKET, COPPER, 10" CF | [6 empty] | 10
| 1000-000N |  |  | (NORCAL) BLANK, CF, 10" OD | [6 empty] | 10
| F0500000Z |  |  | WASHER, 5/16 NOM ID, 0.065 THK, ZINC PLATED | [6 empty] | 480
| G05F0000Z |  |  | HEX NUT, 5/16-24, ZINC PLATED | [6 empty] | 240
| C05F0400Z |  |  | HHCS, 5/16-24, 2.50 LG, ZINC PLATED | [6 empty] | 240
| 114481-00A |  |  | Blank, 52.25" OD, SHIPPING | [6 empty] | 1
| 114497-00A |  |  | BLANK, SHIPPING, 80.25 OD, W/ APS | [6 empty] | 1
| 114492-01S |  |  | TEST FLANGE, 52.25 OD | [6 empty] | 1
| 114493-00S |  |  | TEST FLANGE 80.25 | [6 empty] | 1
| 114518-00A |  |  | CRADLE, SHIPPING | [6 empty] | 1
| 0 |  |  | CRATE, 88" LG, 88" WD, 48" HIGH | [6 empty] | 1
|  |  |  | O-Rings provided by LIGO | [6 empty] | AR
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
10 | 60 | Gather all parts for inspection and cleaning | [5 empty] | 0 |  | 0.25
40 | 60 | Move all components to Class 8 clean room | [5 empty] | 0.1 |  | 0.5
50 | 47 | Inspect weldment and engrave tube if it passes | [5 empty] | 0.1 |  | 0.75
Inspect with visible and UV inspection per QP1750-R5
60 | 30 | Assemble for leak check | [5 empty] | 0.75 |  | 3
70 | 20 | Leak check per QP1750-A7 | [5 empty] | 0.5 |  | 3
80 | 60 | Move to Class 5 clean room for final cleaning | [5 empty] | 0.5 |  | 0.5
90 | 20 | Disassemble blanks and port covers and clean | [5 empty] | 0.5 |  | 2
per QP1750-D2
100 | 47 | Inspect for cleanliness QP1750-R5 | [5 empty] | 0.5 |  | 2
110 | 47 | Perform cleanliness testing per QP1750-A3 | [5 empty] | 1 |  | 6
120 | 30 | Assemble all covers per the print | [5 empty] | 0.5 |  | 3
130 | 60 | Move the chamber to the Class 5 bakeout room | [5 empty] | 0.5 |  | 0.5
140 | 30 | Connect applicable pumps, test equipment, and | [5 empty] | 0.5 |  | 0.75
gauges
150 | 47 | Helium leak check per QP1750-A7, | [5 empty] | 1 |  | 5
RGA test per QP1750-A5
160 | 30 | Bakeout per QP1750-A6 | [5 empty] | 0.5 |  | 8
170 | 47 | Helium leak check per QP1750-A7, | [5 empty] | 1 |  | 5
RGA test per QP1750-A5
180 | 47 | Perform a final investigation and assemble | [5 empty] | 0.5 |  | 3
applicable paperwork
190 | 49 | Package tube for shipping per QP1750-R6 | [5 empty] | 1 |  | 3
[7 empty] | Total: | 9.45 |  | 46

## 2
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/2
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114296-00WS | [5 empty] | DUE DATE |  | 11/24/10
| Description: | WELDMENT, FINAL, ADAPTER A-17 |  |  |  | QTY
[6 empty] | 1 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-21 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114296-00WS |  | WELDMENT, FINAL, ADAPTER A-17 | [6 empty] | C
|  | QP1730-10 |  | Contamination Control Plan | [6 empty] | B
|  | QP1750-W2 |  | LIGO Welding and Repair Procedure | [6 empty] | A
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 114302-00S |  |  | FLANGE, LARGE, ADAPTER A-17 | [6 empty] | 1
| 114300-00WS |  |  | WELDMENT, BELLOWS AND TUBES | [6 empty] | 1
| 114304-00S |  |  | FLANGE, SMALL, ADAPTER A-17 | [6 empty] | 1
| 114260-01WS |  |  | WELDMENT, PORT, 10" CF | [6 empty] | 10
| 0 |  |  | WELD ROD, 1/8 DIA, 36" LONG | [6 empty] | AR
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
Gather all components in the LIGO welding room
10 | 60 | Ensure all CMTRs accompany material, and handle | [5 empty] | 0.5 |  | 1.5
per QP1730-10
PERFORM ALL WELDMENTS IN LIGO CLEAN ROOM
20 | 10 | Clean all weld wire and surfaces to be welded | [5 empty] | 0.25 |  | 1
with CO2 scrubbing
MAINTAIN ALREADY PRESENT "spider" fixtures to maintain roundness.
30 | 10 | Fit up and align the small flange and tack in place | [5 empty] | 0.5 |  | 1.5
Follow QP1730-10 and QP1750-W2
Fit up the large flange oriented per the print Adjust the location
40 | 10 | of the flange to obtain the desired length per print | [5 empty] | 0.25 |  | 1
and tack in place. Follow QP1730-10 and QP1750-W2
Tack the 10" cf ports in place per the print,
50 | 10 | taking care to note location and orientation | [5 empty] | 0.5 |  | 1
Follow QP1730-10 and QP1750-W2
60 | 47 | Inspect the assembled weldment per the print | [5 empty] | 0.25 |  | 1.5
Weld the tube together, starting with the tube seam
70 | 10 | then the flanges, bellows, and ports. | [5 empty] | 0.5 |  | 8
Follow QP1730-10 and QP1750-W2
80 | 47 | Inspect the final weldment per the print | [5 empty] | 0.5 |  | 1
110 | 60 | Move to NHA in LIGO building | [5 empty] | 0.25 |  | 0
[7 empty] | Total: | 3.5 |  | 16.5

## 3
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/3
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114302-00S | [5 empty] | DUE DATE |  | 11/17/10
| Description: | FLANGE, LARGE, ADAPTER A-17 |  |  |  | QTY
[6 empty] | 1 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-21 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114302-00S |  | FLANGE, LARGE, ADAPTER A-17 | [6 empty] | B
|  | QP1730-10 |  | Contamination Control Plan | [6 empty] | B
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 114303-00S |  |  | FORGING, 44.90 ID, 80.25 OD, SMOOTH | [6 empty] | 1
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
Verify compliance with QP1730-10, and CMTRs present
10 | 60 | Move material to the VTL | [5 empty] | 0 |  | 0
20 | 1 | Skim cut both sides of the flange for flatness | [5 empty] | 1 |  | 8
Adhere to QP1730-10
Machine in grooves, finish thickness cut, ID, and
step for roll-up. Adhere to QP1730-10
30 | 60 | Move flange to TOS | [5 empty] | 0 |  | 0
40 | 1 | Machine thru holes, slots for pump out grooves | [5 empty] | 0.5 |  | 3
per QP1730-10
50 | 47 | Inspect to print | [5 empty] | 0 |  | 0.25
60 | 60 | Move to NHA in LIGO building | [5 empty] | 0 |  | 0
[7 empty] | Total: | 1.5 |  | 11.25

## 4
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/4
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114301-00S | [5 empty] | DUE DATE |  | 11/3/10
| Description: | ROLL-UP, ADAPTER, A-17 |  |  |  | QTY
[6 empty] | 2 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-26 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114301-00S |  | ROLL-UP, ADAPTER, A-17 | [6 empty] | D
|  | QP1730-10 |  | CONTAMINATION CONTROL PLAN | [6 empty] | B
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 114301-00S; ROLL-UP, .25 WALL, 45.25 ID, 17.25 LG | [9 empty] | 2
AISI 304/AISI 304L DUAL CERT PER SA240
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
10 | 60 | Issue Material | [5 empty] | 0 |  | 0
PLACE A FIXTURE INSIDE THE ROLL-UP TO MAINTAIN ROUNDNESS AND OD
20 | 43 | Machine end as indicated on print for length, outer | [5 empty] | 0.25 |  | 3
diameter. ADHERE TO QP1730-10
30 | 47 | Inspect per print | [5 empty] | 0 |  | 0.1
40 | 49 | Package per QP1730-10 for shipment to Hyspan | [5 empty] | 0.1 |  | 3
and ship to Hyspan
[7 empty] | Total: | 0.35 |  | 6.1

## 5
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/5
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114304-00S | [5 empty] | DUE DATE |  | 11/17/10
| Description: | FLANGE, SMALL, ADAPTER A-17 |  |  |  | QTY
[6 empty] | 1 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-21 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114304-00S |  | FLANGE, SMALL, ADAPTER A-17 | [6 empty] | A
|  | QP1730-10 |  | Contamination Control Plan | [6 empty] | B
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 114305-00S |  |  | FORGING, 44 ID, 52.26 OD, GROOVED | [6 empty] | 1
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
Verify compliance with QP1730-10, and CMTRs present
10 | 60 | Move material to the VTL | [5 empty] | 0 |  | 0
20 | 1 | Skim cut both sides of the flange for flatness | [5 empty] | 1 |  | 8
Adhere to QP1730-10
Machine in grooves, finish thickness cut, ID, and
step for roll-up. Adhere to QP1730-10
30 | 60 | Move flange to TOS | [5 empty] | 0 |  | 0
40 | 1 | Machine thru holes, slots for pump out grooves | [5 empty] | 0.5 |  | 3
per QP1730-10
50 | 47 | Inspect to print | [5 empty] | 0 |  | 0.25
60 | 60 | Move to NHA in LIGO building | [5 empty] | 0 |  | 0
[7 empty] | Total: | 1.5 |  | 11.25

## 6
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/6
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114260-01WS | [5 empty] | DUE DATE |  | 11/17/10
| Description: | WELDMENT, PORT, 10" CF |  |  |  | QTY
[6 empty] | 10 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-21 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114260-01WS |  | WELDMENT, PORT, 10" CF | [6 empty] | B
|  | QP1730-10 |  | Contamination Control Plan | [6 empty] | B
|  | QP1750-W2 |  | LIGO Welding and Repair Procedure | [6 empty] | A
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| 1000-800N |  |  | (NORCAL) FLANGE, CF, 10" OD, NR, THRU HOLES | [6 empty] | 10
| 114435-00S |  |  | TUBE, 10" CF, A-17 PORT | [6 empty] | 10
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
Gather all components in the LIGO welding room
10 | 60 | Ensure all CMTRs accompany material, and handle | [5 empty] | 0 |  | 1.5
per QP1730-10
PERFORM ALL WELDMENTS IN THE LIGO CLEAN ROOM
20 | 10 | Clean all weld wire and surfaces to be welded | [5 empty] | 0.25 |  | 1
with CO2 scrubbing per QP1750-D2
Fit up and align the flange and tube
30 | 10 | and tack in place. | [5 empty] | 0.5 |  | 2.5
Follow QP1730-10 and QP1750-W2
40 | 47 | Inspect the assembled weldment per the print. | [5 empty] | 0 |  | 0.1
50 | 10 | Final weld the port per the print | [5 empty] | 0.25 |  | 2.5
Follow QP1730-10 and QP1750-W2
60 | 47 | Inspect the assembled weldment per the print. | [5 empty] | 0 |  | 1
70 | 60 | Move to NHA | [5 empty] | 0 |  | 0
[7 empty] | Total: | 1 |  | 8.6

## 7
|  |  | TRAVELER | [12 empty] | D1750-3 rev. D
[9 empty] | Work Order Number | W03474/7
QP1730-10, CONTAMINATION CONTROL PLAN, APPLIES DURING ALL STEPS!!
ONLY AUTHORIZED PERSONNEL MAY HANDLE COMPONENTS OF THIS JOB!!!
| Part Number: | 114435-00S | [5 empty] | DUE DATE |  | 11/10/10
| Description: | TUBE, 10" CF, A-17 PORT |  |  |  | QTY
[6 empty] | 10 | [5 empty] | Page | 1 | of | 1
114142-00 |  |  |  |  | Release Date:
Originator |  | MKM2 |  | Date: | 2010-07-26 |  | QA |  |  |  | Date
> | Documents Required | [9 empty] | Rev.
> | Drawing | 114435-00S |  | TUBE, 10" CF, A-17 PORT | [6 empty] | B
|  | QP1730-10 |  | CONTAMINATION CONTROL PLAN | [6 empty] | B
> | Inspection Document
> | Drawing
> | Material Required (minimum or equivalent to): | [9 empty] | QTY
| TUBE, 8.00 OD, .25 WALL, 4.25 LG | [6 empty] | AISI 304/AISI 304L DUAL CERT PER SA240 |  |  | 10
Oper. | W/C | Task | [5 empty] | Set-up |  | Run |  | Qty. Comp. |  |  | Stamp/Int.
10 | 60 | Issue Material, ensure CMTRs accompany part. | [5 empty] | 0 |  | 0
20 | 43 | CUT MATERIAL TO LENGTH PER PRINT, | [5 empty] | 0.25 |  | 0.25
ADHERE TO QP1730-10§4
30 | 1 | CLEAN UP OD OF TUBE IF NECESSARY | [5 empty] | 0.5 |  | 3
40 | 47 | INSPECT OD OF TUBE | [5 empty] | 0 |  | 0.1
50 | 60 | MOVE TO NHA in LIGO building | [5 empty] | 0 |  | 0
[7 empty] | Total: | 0.75 |  | 3.35