## E1000295-v1
CALIFORNIA INSTITUTE OF TECHNOLOGY
FORMAL DRAWING TREE REFERENCE DOCUMENT
| TITLE: | aLIGO TCS Ring Heater Assembies
for Formal Design Review
| DOCUMENT CONTROL NO.: | E1000295 |  |  | -v1
| RELATED DOC. CHANGE NO.: | E1000291 |  |  | -v1
| CONTAINING ASSEMBLIES: | D1001838 |  |  | -v1
|  | D1001895 |  |  | -v1
| AUTHOR: | M. JACOBSON
| DATE: | 2010-08-09
| PURPOSE: | This document is the formal reference for necessary revisions of each child of the stated assemblies, and the total necessary quantities for all items.
Subsystem: | RH | [19 empty] | PDR | delta-PDR | FDR | XXX
Reporter: | Mindy Jacobson
Date: | 2010-08-09 | [23 empty] | RESERVED for PROCUREMENT TRACKING
| Total No. Dwgs = | 90
| Aggregate %-complete = | 23.7778
QUANTITY
DCN | NOTES | Level | INDENTURE CHART | [6 empty] | REQ'd | SPARE | TOT. | UNITS | DWG TREE REF. NO. | DCC No. | NAME | TYPE | MODEL STATUS | DWG STATUS | SOURCE | REV. | REV. | REV. | REV.
No. | [17 empty] | % COMPLETE
EXTERNAL TO VACUUM
|  | 0 | [7 empty] | 1 |  |  | EA |  | D1002047 | aLIGO TCS RH ELEMENT WINDING ASSY | TopAssy | 90 | 0 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1000682 | [TCS] RH GLASS ROD INSULATOR | PRT | 100 | 100 | MTS | N/A | V1 | V2
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 237.6194 |  |  | IN |  |  | NICHROME WIRE, 24 BNC [DIA .5 MM] | PRT | 0 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001819 | RH ELEMENT RETAINER LEFT [9 O'CLOCK POSITION] | PRT | 90 | 90 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001858 | RH ELEMENT RETAINER RIGHT [3 O'CLOCK POSITION] | PRT | 90 | 90 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA |  | D1001849 | UPPER COPPER PLATE | PRT | 90 | 90 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA |  | D1001850 | LOWER COPPER PLATE | PRT | 90 | 90 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA |  | C-210 | SS SHCS-V #2-56 UNC 2A X .625 LONG | HW | 100 | 0 | OTS | N/A | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA |  | N-256 | SS HEX NUT #2-56 UNC 2B | HW | 100 | 0 | OTS | N/A | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1002045 | aLIGO TCS RH ELEMENT WINDING TOOL | PRT | 75 | 0 | MTS | N/A | N/A | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 |  |  | EA |  | C-406 | SS SHCS-V #4-40 UNC 2A X .375 LONG | HW | 100 | 0 | OTS | N/A | N/A
ELECTRONICS
{ } | OTS ? | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ? |  |  | EA |  | DXXXXXXX | aLIGO TCS RH POWER SUPPLY | ASSY | 0 | 0 |  | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | RH POWER SUPPLY ASSY HARDWARE | HW | 0 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | BOARD LAYOUT |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | GERBER FILES |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | SCEMATICS |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | WIRING DIAGRAMS |  | 0 | 0 | MTS | N/A
{ } |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ? |  |  | EA |  | DXXXXXXX | aLIGO TCS RH DRIVER | ASSY | 0 | 0 |  | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | RH DRIVER ASSY HARDWARE | HW | 0 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | BOARD LAYOUT |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | GERBER FILES |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | SCEMATICS |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | WIRING DIAGRAMS |  | 0 | 0 | MTS | N/A
{ } |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ? |  |  | EA |  | DXXXXXXX | aLIGO TCS RH A-D CONVERTER | ASSY | 0 | 0 |  | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | RH A-D CONVERTER ASSY HARDWARE | HW | 0 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | BOARD LAYOUT |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | GERBER FILES |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | SCEMATICS |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | WIRING DIAGRAMS |  | 0 | 0 | MTS | N/A
{ } |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ? |  |  | EA |  | DXXXXXXX | aLIGO TCS RH D-A CONVERTER | ASSY | 0 | 0 |  | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | RH D-A CONVERTER ASSY HARDWARE | HW | 0 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | BOARD LAYOUT |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | GERBER FILES |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | SCEMATICS |  | 0 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  |  | EA |  |  | WIRING DIAGRAMS |  | 0 | 0 | MTS | N/A
{ } |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ? |  |  | ? |  | DXXXXXXX | aLIGO TCS RH IN-AIR CABLE ASSY | ASSY | 0 | 0 |  | N/A
[18 empty] | 0 | 0 |  | N/A
[18 empty] | 0 | 0 |  | N/A
{ } |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | EA |  | D1001517 | aLIGO TCS RH IN-VAC CABLE ASSY | ASSY | 50 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001518 | UPPER RH SEGMENT TO LOWER QUAD TERM BLOCK | ASSY | 75 | 0 | MTS | N/A | N/A | V1
| OMEGA | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | PN EXGG-4CU-26S | Ceramic Pt RTD + Wire PN EXGG-4CU-26S | PRT | 0 | 0 | OTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | EA |  | PN 111155 | PEEK CABLE TIE, ACCUGLASS PN 111155 | PRT | 0 | 0 | OTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 39 |  |  | IN |  | PN 112140 | SHIELDED 4-TWISTED PAIR WIRE, ACCUGLASS PN 112140 | PRT | 100 | 0 | MTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  | PN 111022 | USER END 400 CONNECTOR ASSY | PRT | 100 | 100 | OTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  |  | UHV MALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001519 | LOWER RH SEGMENT TO LOWER QUAD TERM BLOCK | ASSY | 75 | 0 | MTS | N/A | N/A | V1
| OMEGA | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | PN EXGG-4CU-26S | Ceramic Pt RTD + Wire PN EXGG-4CU-26S | PRT | 0 | 0 | OTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | EA |  | PN 111155 | PEEK CABLE TIE, ACCUGLASS PN 111155 | PRT | 0 | 0 | OTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | XX |  |  | IN |  | PN 112140 | SHIELDED 4-TWISTED PAIR WIRE, ACCUGLASS PN 112140 | PRT | 100 | 0 | MTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  | PN 111022 | USER END 400 CONNECTOR ASSY | PRT | 100 | 100 | OTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  |  | UHV MALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001520 | LOWER QUAD TERM BLOCK TO UPPER QUAD TERM BLOCK | ASSY | 75 | 0 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1001755 | CUSTOM BRKT, 25D CONNECTOR INTERFACE | PRT | 100 | 0 | MTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  |  | UHV FEMALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | XX |  |  | IN |  | PN 112143 | SHIELDED 12-TWISTED PAIR WIRE, ACCUGLASS PN 112143 | PRT | 100 | 0 | OTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | EA |  |  | HARDWARE | HW | 0 | 0 | OTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  |  | UHV MALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001521 | UPPER QUAD TERM BLOCK TO FEED-THROUGH | ASSY | 75 | 0 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1001756 | CUSTOM BRKT, 25D CONNECTOR INTERFACE | PRT | 100 | 0 | MTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  |  | UHV FEMALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | XX |  |  | IN |  | PN 112143 | SHIELDED 12-TWISTED PAIR WIRE, ACCUGLASS PN 112143 |  | 100 | 0 | OTS | N/A
| EMERY'S MODEL | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  |  | UHV MALE 25D CONNECTOR | PRT | 100 | 0 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  |  | EA |  |  | HARDWARE |  | 0 | 0 | OTS | N/A
INTERNAL TO VACUUM
E900345-v1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | EA |  | D0901269 | ADV_LIGO_TCS_RING_HEATER_AND_SHIELD_ASSEM | TopAssy | 100 | 100 | MTS | v2 |  |  |  | 29227.5
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 1 | D0902351 | ADLIGO TCS RING HEATER SHIELD | PRT | 100 | 100 | MTS | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 2 | D0902408 | ADLIGO TCS RING HEATER BACK PLATE RH | PRT | 100 | 90 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 3 | D0902409 | ADLIGO TCS RING HEATER BACK PLATE LH | PRT | 100 | 90 | MTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA | 4 | D0902410 | ADLIGO TCS RING HEATER BLOCK | PRT | 100 | 90 | MTS | N/A
| WATLOW (?) | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 5 | D0901279 | TCS_RING_HEATER_ELEMENT | PRT | 100 | 0 | OTS | N/A
| QTY INCL (1) SPR | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 9 |  |  | EA | 6 |  | #4-40X.188 FLT HD SKT SCR, SST [18-8 SST] | HW | 100 | 0 | OTS
E900345-v1 | LASTI retrofit assy | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | EA |  | D0902447 | LASTI TCS RING HEATER INSTALLATION RETROFIT | ASSY | 100 | 100 | MTS | V1 | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | { REF } | D0902351 | ADLIGO TCS RING HEATER SHIELD | PRT | 100 | 100 | MTS | V1
{ } | CONSTRAINT | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA | { } | D1000270 | TCS ALLOWABLE RH ELEMENT ENVELOPE | VOL | 100 | 100 | OTS | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 1 | D0902448 | LASTI TCS RING HEATER BACK PLATE RH | PRT | 100 | 100 | MTS | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA | 2 | D0902449 | LASTI TCS RING HEATER BACK PLATE LH | PRT | 100 | 100 | MTS | V1
| DWG.TR E900344-V1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA | { REF } | D0902450 | LASTI TCS RING HEATER BLOCK | PRT | 100 | 100 | MTS | V1
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 |  |  | EA | { } |  | FH SCR, PHILIPS, #4-40 X 3/16 LG, SST | HW | 100 | 0 | OTS
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 4 |  |  | EA | { } |  | FH SCR, PHILIPS, #2-56 X 3/16 LG, SST | HW | 100 | 0 | OTS
{ } | QTYs ARE PER OPTIC | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 |  |  | EA |  | D1000978 | ALIGO [TCS] RING HEATER ASSY | TopAssy | 90 | 0 | MTS | N/A | V1 | N/A
E1000154-v1 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1000969 | ALIGO TCS MONOLITH RH SHIELD | PRT | 100 | 90 | MTS | N/A | V2 | N/A |  | 83400
{ } | CONSTRAINT | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1000270 | TCS ALLOWABLE RH ELEMENT ENVELOPE | VOL | 100 | 100 | OTS | N/A | V1
| either this OR D1000945 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001187 | TCS RING HEATER ELEMENT ASSEMBLY, LASTI | ASSY | 50 | 0 | MTS | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1000682 | [TCS] RH GLASS ROD INSULATOR | PRT | 100 | 100 | MTS | N/A |  |  |  | 3000
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  | D1001063 | GLASS ROD RETAINER | PRT | 90 | 0 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 60 |  |  | IN |  |  | NICHROME WIRE, 24 BNC [DIA .5 MM] | PRT | 0 | 0 | OTS | N/A
| either this OR D1001187 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1000945 | ALIGO TEST MASS RING HEATER ASSEMBLY [M.A._UF] | HW | 90 | 90 | MTS | N/A | V1 |  |  | 120000
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  | D1000970 | ALIGO TEST MASS RING HEATER SUPPORT BLOCK | PRT | 100 | 90 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  | D1000956 | ALIGO TEST MASS RING HEATER WIRE INTERSECTION BLOCK | PRT | 100 | 90 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | EA |  | D1001016 | ALIGO TEST MASS RING HEATER WIRE PLATE | PRT | 100 | 90 | MTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1000943 | ALIGO TEST MASS RING HEATER INNER RING | PRT | 100 | 90 | MTS | N/A | V2 | N/A |  | 18750
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | D1000944 | ALIGO TEST MASS RING HEATER OUTER RING | PRT | 100 | 90 | MTS | N/A | V2 | N/A |  | 18750
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 3 |  |  | EA |  |  | SS FHCS 2-56 X .25 L | HW | 100 | 0 | OTS | N/A
| Ortech | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  |  | EA |  |  | ORTECH CERAMIC SET SCREW 2-56 X .25 L | HW | 100 | 0 | OTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | EA |  |  | SS VENTED SHCS 2-56 X .1875 L | HW | 100 | 0 | OTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 |  |  | IN |  |  | INSULATED COPPER WIRE, 28 AWG | PRT | 100 | 0 | OTS | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 2 |  |  | EA |  | Dxxxxxxx | IN-LINE UHV CONNECTOR ASSY | ASSY | 100 | 0 | MTS | N/A | N/A | V1
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  |  | EA |  | PN 100171 | ACCUGLASS CONNECTOR 100171 | PRT | 100 | 0 | OTS | N/A | N/A
|  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  |  | EA |  | D1001516 | WIRE GUIDE BUSHING | PRT | 100 | 0 | MTS | N/A | N/A | V1
| PER OPTIC QTY | 0 | [7 empty] | 1 | 1 | 2 | EA |  | D1002027 | aLIGO SYS-TCS INTEGRATION OF RH WITH TM | TopAssy | 90 | 0 | MTS | N/A | N/A | V1
E1000291 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | EA | E1000295 | D1001838 | aLIGO [TCS] UPPER SEGMENT RING HEATER ASSY | ASSY | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | EA |  | D1001679 | ALIGO TCS UPPER MONOLITH RH SHIELD | PRT | 100 | 90 | MTS | N/A | N/A | V1 |  | 45000
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1000682 | [TCS] RH GLASS ROD INSULATOR | PRT | 100 | 100 | MTS | N/A | V1 | V2
| McMASTER, ASTMB267/B344 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 19.8016 | 19.8016 | 39.6032 | FT |  |  | NICHROME WIRE, 24 BNC [DIA .5 MM] | PRT | 0 | 0 | OTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1001819 | RH ELEMENT RETAINER LEFT [9 O'CLOCK POSITION] | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1001858 | RH ELEMENT RETAINER RIGHT [3 O'CLOCK POSITION] | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | D1001849 | UPPER COPPER PLATE | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | D1001850 | LOWER COPPER PLATE | PRT | 100 | 90 | MTS | N/A | N/A | V1
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | C-210 | SS SHCS-V #2-56 UNC 2A X .625 LONG | HW | 100 | 0 | OTS | N/A | N/A
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | N-256 | SS HEX NUT #2-56 UNC 2B | HW | 100 | 0 | OTS | N/A | N/A
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 6 | EA |  | FA-404 | SS FSHCS-V #4-40 UNC 2A X .25 LONG | HW | 100 | 0 | OTS | N/A | N/A
| COONER -CalTech STOCK | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 24 | IN |  | CZ1105 | PFA COATED 28 AWG Cu WIRE, 2x 6 IN LENGTH | PRT | 0 | 0 | OTS | N/A | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | PN 100170 | ACCUGLASS PIN CONTACT 100170, MALE TYPE T-1, CRIMPED | PRT | 100 | 100 | OTS | N/A | N/A
E1000291 |  | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 | 1 |  | 1 | EA | E1000295 | D1001895 | aLIGO [TCS] LOWER SEGMENT RING HEATER ASSY | ASSY | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 |  | 1 | EA |  | D1001680 | ALIGO TCS UPPER MONOLITH RH SHIELD | PRT | 100 | 90 | MTS | N/A | N/A | V1 |  | 45000
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1000682 | [TCS] RH GLASS ROD INSULATOR | PRT | 100 | 100 | MTS | N/A | V1 | V2
| McMASTER, ASTMB267/B344 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 19.8016 | 19.8016 | 39.6032 | FT |  |  | NICHROME WIRE, 24 BNC [DIA .5 MM] | PRT | 0 | 0 | OTS | N/A
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1001819 | RH ELEMENT RETAINER LEFT [3 O'CLOCK POSITION] | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 1 | 1 | 2 | EA |  | D1001858 | RH ELEMENT RETAINER RIGHT [9 O'CLOCK POSITION] | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | D1001849 | LOWER UPPER PLATE | PRT | 100 | 90 | MTS | N/A | N/A | V1
|  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | D1001850 | LOWER COPPER PLATE | PRT | 100 | 90 | MTS | N/A | N/A | V1
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | C-210 | SS SHCS-V #2-56 UNC 2A X .625 LONG | HW | 100 | 0 | OTS | N/A | N/A
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | N-256 | SS HEX NUT #2-56 UNC 2B | HW | 100 | 0 | OTS | N/A | N/A
| UC COMPONENTS | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 2 | 6 | EA |  | FA-404 | SS FSHCS-V #4-40 UNC 2A X .25 LONG | HW | 100 | 0 | OTS | N/A | N/A
| COONER -CalTech STOCK | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 12 | 12 | 24 | IN |  | CZ1105 | PFA COATED 28 AWG Cu WIRE, 2x 6 IN LENGTH | PRT | 0 | 0 | OTS | N/A | N/A
| AccuGlass Inc | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | EA |  | PN 100170 | ACCUGLASS PIN CONTACT 100170, MALE TYPE T-1, CRIMPED | PRT | 100 | 100 | OTS | N/A | N/A
N/A = NOT APPLICABLE
Note on Q119: Mindy Jacobson: [2-FEB-10] WATLOW p/n TESTED TO DATE: 125CH24A14X-806 (CABLE, 275W, 240Vac) RAN2010S (TUBULAR 400W, 240Vac)